TITAN 2 PROJECT · DAILY REPORT

Construction Coordinator Daily Report — Saturday, August 15, 2026

Site:  MPLX Titan Gas Plant, Jal, NM

Owner:  Azota Gas Processing, Ltd.

Report No.:  DR-2026-08-15

Prepared By:  Construction Coordinator — Titan 2

Weather:  Not recorded

Crews On Site:  Not recorded

## SUMMARY OF THE DAY

No field notes were recorded for this day. Per the Friday plan, this was the day the stabilizer compressor precision leveling was scheduled for the early morning, the tower scaffolding crews were to begin their first night shift toward the 08-24 hard date, and WICK manway/vessel work was planned over the weekend — completion of these was not documented and statuses in the register are carried, not verified. The open action item register is carried forward unchanged from DR-2026-08-14.

## WORK PERFORMED / PROGRESS TODAY

- Not recorded — no field notes were captured for this day.

## INSPECTIONS & TESTS

- None recorded.

- Scheduled: stabilizer precision leveling was scheduled this morning; WICK manway/vessel work planned this weekend; Kodiak pre-commissioning starts 08-17.

## ISSUES / DELAYS (3 OPEN)

- Rio 8 HMI comms — Cisco switch on loan to Pelham; replacement part remains a critical open item.

- Heater shell bolting/sealant — OPF procedure and clamshell sealant identification still outstanding.

- Stabilizer flange torque — Mock's torquing program unconfirmed; missing studs previously observed on some flanges.

Coordinator note: This is a minimal report — no field notes were recorded for this day. Statuses shown in the register are carried, not verified for this date.

## OPEN ACTION ITEMS

| # | Action | Area | Responsible / With | Status |
| --- | --- | --- | --- | --- |
| 1 | Gallup vessel inspection — Teams meeting 08-18 at 14:00 to align the agenda with the other trades, onsite kickoff to follow; night work starts 08-24. | Inspections | Coordinator / Gallup / CM | In Progress |
| 2 | Heater shells — obtain the correct bolting procedure from OPF (current-rev GA and erection manual, P.O. 24250-133; not in Procore) and determine what sealant is used where the two clamshell halves come together. | Heaters | Coordinator / OPF | Open |
| 3 | Support WICK's on-site inspection of the heaters and concrete foundations. | Heaters | Coordinator / WICK | Open |
| 4 | Coordinate with M4 for final pump alignment and inspection ahead of tie-in sign-off — paused until ready for final alignment. | Pumps | Coordinator / M4 | On Hold |
| 5 | Get with Mock to go around the entire site and cover all open flanges or flanges with missing covers — Mock night crew starting on it (a couple on the Kodiaks, a couple on the towers). | Site | Coordinator / Mock | In Progress |
| 6 | Kodiak shade covers and acid gas awnings — awnings at 50%, acid gas platforms at 68%, concrete pads complete at 100%. | Kodiak / Acid Gas | AR foreman | In Progress |
| 7 | Stabilizer compressor interconnect piping — most runs complete; small bolt-ups and final torque remaining. | Piping | Mock / MACH | In Progress |
| 8 | Follow up with Kodiak on Monday to confirm whether the catalysts are installed and whether they stay in for the burn-in or come out. | Kodiak | Coordinator / Kodiak | Due 08-17 |
| 9 | Have Mock haul the labeled aerial boxes for the Kodiak sweet gas compressors to the Conex box. | Kodiak | Mock | Open |
| 10 | Secure the shim packages and filters to prevent loss. | Kodiak | Field team | Open |
| 11 | CNG trailered fuel gas for turbine pre-commissioning — on hold as a contingency in case fuel gas is unavailable (no black-start generator required for the trailer suction). | Turbines | Coordinator / CNG | On Hold |
| 12 | Follow up with the AR foreman on the piping estimation and clarify who procures the materials. | Piping | Coordinator / AR | Open |
| 13 | SEC compressor deficiencies — repair bent catwalk and damaged grating, remove tripping-hazard mounting brackets from the control panels, fix platforms, and add platforms on the east side. | SEC | AR foreman | In Progress |
| 14 | Measurement review — Measurement on site 08-18 to go over all received measurement equipment against Morgan Anderson's list; identify which meter skids serve the pipeline connections. | Equipment | Coordinator / Measurement | Sched. 08-18 |
| 15 | Tower scaffolding — starts Saturday night 08-15 and runs nights until complete; hard completion date 08-24; OSHA-compliant manway access; contractor to leave time for cleanup. | Towers | Scaffold contractor | In Progress |
| 16 | Precision-level the three stabilizer compressors with machinist levels — rescheduled to 08-15; crew ready early before the heat. | Equipment | Leveling crew / Mock | Sched. 08-15 |
| 17 | Bidell compressor grout — forms were pulled to re-blow dust and sand from under the compressor (wind kept blowing it back in); re-prep, re-form, and grout the units, then move to the stabilizer area. | Compressors | Eagle / grout crew | In Progress |
| 18 | Instrument tracking Excel (on-site / missing / long-lead / out-of-scope) — construction managers reviewing; red-line decisions through Manny. | I&E | CMs / Manny | In Progress |
| 19 | Smooth out the dirt around the acid gas control panel foundations (skid steer) — some progress observed in the field today but not complete. | Acid Gas | AR foreman | In Progress |
| 20 | Compile the tank and pump account for the SEC, acid gas, and stabilizer compressors; determine oil types and quantities; submit the BOM to the oil supplier. | Compressors | Coordinator | Open |
| 21 | Ground and bond the newly set day tanks, staircases, and platforms — scope sits with Azota or Epic. | Kodiak | Azota / Epic | Open |
| 22 | Confirm whether the 4-inch ESD valve is sufficiently sized for the upsized 6-inch fuel gas line; get confirmation on the bridle level switches and add two 4-inch 600-rated strainers to the list — construction manager following up. | Fuel Gas | CM / Engineering | In Progress |
| 23 | Ensure the pipeline connection points (flanges, meter skids) are installed before the pipeline construction team arrives. | Pipeline & Plant | Coordinator | Open |
| 24 | Kodiak pre-commissioning begins — support startup activities. | Kodiak | Kodiak | Sched. 08-17 |
| 25 | Heater foundations — H-49200 (area 16): forms stripped, clips still to grind off, foundation forms still to remove. H-59200 (area 17): forms complete and ready to pour. | Civil | Civil crew | In Progress |
| 26 | Finish backfilling the adjacent foundation once the congestion/equipment access issue is resolved. | Civil | Civil crew | Open |
| 27 | Re-confirm the formal levelness of stabilizer compressors C-51150 and C-51175 after the 08-15 precision leveling and re-issue the levelness documentation for all three units before any alignment sign-offs. | Equipment | Coordinator / Leveling crew | Open |
| 28 | Determine Kodiak's plan to remove all paint and tape from the sight glasses and any other visual components on their skids. | Kodiak | Coordinator / Kodiak | Open |
| 29 | Establish a staging area with Mock for all tower scaffolding — supervisor walk first thing in the morning to set the staging spot and mark the no-go areas. | Towers | Coordinator / Mock | Open |
| 30 | CRITICAL — Track the Cisco switch removed from Rio 8 and sent to Pelham for HMI comms; make sure the replacement part is ordered through ops and installed when it arrives. | I&E | Coordinator / Ops | Open |
| 31 | Confirm Mock's torquing program on the stabilizer compressors — how torqued flange-ups are marked and verified; a few studs are missing on some flanges. | Piping / QC | Coordinator / Mock | Open |

## PLAN FOR NEXT WORK DAY — SUN 08-16

- WICK manway/vessel work continues over the weekend.

- Tower scaffolding night shifts continue toward the 08-24 hard date.

- Prepare for the Kodiak catalyst follow-up and pre-commissioning start on Monday 08-17.

Minimal report issued for the record: no Plaud recording or field notes exist for this day. The open action item register (1-31) is carried forward unchanged from DR-2026-08-14; statuses are as last recorded, not verified for this date.