TITAN 2 PROJECT · DAILY REPORT

Construction Coordinator Daily Report — Monday, August 17, 2026

Site:  MPLX Titan Gas Plant, Jal, NM

Owner:  Azota Gas Processing, Ltd.

Report No.:  DR-2026-08-17

Prepared By:  Construction Coordinator — Titan 2

Weather:  Not recorded

Crews On Site:  Not recorded

## SUMMARY OF THE DAY

A field recording exists for this day in Plaud but has not yet been transcribed, so field activities and completions are not documented here — this report will be reissued once the recording is processed. Scheduled for this day: the Kodiak catalyst follow-up (whether the catalysts are in and staying for burn-in) and the start of Kodiak pre-commissioning, with tower scaffolding continuing on nights toward the 08-24 hard date. The open action item register (1-36) is carried forward from DR-2026-08-16, including the chain-fall incident follow-ups.

## WORK PERFORMED / PROGRESS TODAY

- Not yet documented — the 08-17 Plaud recording is awaiting transcription; this report will be updated when its summary is available.

## INSPECTIONS & TESTS

- None recorded.

- Scheduled: Kodiak catalyst check and pre-commissioning start today; measurement equipment review 08-18; tower program kickoff 08-24.

## ISSUES / DELAYS (3 OPEN)

- Rio 8 HMI comms — Cisco switch on loan to Pelham; replacement part remains a critical open item.

- Heater shell bolting/sealant — OPF procedure and clamshell sealant identification still outstanding.

- Stabilizer flange torque — Mock's torquing program unconfirmed; missing studs previously observed on some flanges.

Coordinator note: Weekend recap — a chain fall failed 08-16 lowering suction scrubber piping on the 640 train (no injuries; grinder-struck link suspected) and a full-site stand-down was held; follow-ups are register items 32-36.

## OPEN ACTION ITEMS

| # | Action | Area | Responsible / With | Status |
| --- | --- | --- | --- | --- |
| 1 | Gallup vessel inspection — Teams meeting 08-18 at 14:00 to align the agenda with the other trades, onsite kickoff to follow; night work starts 08-24. | Inspections | Coordinator / Gallup / CM | In Progress |
| 2 | Heater shells — obtain the correct bolting procedure from OPF (current-rev GA and erection manual, P.O. 24250-133; not in Procore) and determine what sealant is used where the two clamshell halves come together. | Heaters | Coordinator / OPF | Open |
| 3 | Support WICK's on-site inspection of the heaters and concrete foundations. | Heaters | Coordinator / WICK | Open |
| 4 | Coordinate with M4 for final pump alignment and inspection ahead of tie-in sign-off — paused until ready for final alignment. | Pumps | Coordinator / M4 | On Hold |
| 5 | Get with Mock to go around the entire site and cover all open flanges or flanges with missing covers — Mock night crew starting on it (a couple on the Kodiaks, a couple on the towers). | Site | Coordinator / Mock | In Progress |
| 6 | Kodiak shade covers and acid gas awnings — awnings at 50%, acid gas platforms at 68%, concrete pads complete at 100%. | Kodiak / Acid Gas | AR foreman | In Progress |
| 7 | Stabilizer compressor interconnect piping — most runs complete; small bolt-ups and final torque remaining. | Piping | Mock / MACH | In Progress |
| 8 | Follow up with Kodiak on Monday to confirm whether the catalysts are installed and whether they stay in for the burn-in or come out. | Kodiak | Coordinator / Kodiak | Due 08-17 |
| 9 | Have Mock haul the labeled aerial boxes for the Kodiak sweet gas compressors to the Conex box. | Kodiak | Mock | Open |
| 10 | Secure the shim packages and filters to prevent loss. | Kodiak | Field team | Open |
| 11 | CNG trailered fuel gas for turbine pre-commissioning — on hold as a contingency in case fuel gas is unavailable (no black-start generator required for the trailer suction). | Turbines | Coordinator / CNG | On Hold |
| 12 | Follow up with the AR foreman on the piping estimation and clarify who procures the materials. | Piping | Coordinator / AR | Open |
| 13 | SEC compressor deficiencies — repair bent catwalk and damaged grating, remove tripping-hazard mounting brackets from the control panels, fix platforms, and add platforms on the east side. | SEC | AR foreman | In Progress |
| 14 | Measurement review — Measurement on site 08-18 to go over all received measurement equipment against Morgan Anderson's list; identify which meter skids serve the pipeline connections. | Equipment | Coordinator / Measurement | Sched. 08-18 |
| 15 | Tower scaffolding — starts Saturday night 08-15 and runs nights until complete; hard completion date 08-24; OSHA-compliant manway access; contractor to leave time for cleanup. | Towers | Scaffold contractor | In Progress |
| 16 | Precision-level the three stabilizer compressors with machinist levels — rescheduled to 08-15; crew ready early before the heat. | Equipment | Leveling crew / Mock | Sched. 08-15 |
| 17 | Bidell compressor grout — forms were pulled to re-blow dust and sand from under the compressor (wind kept blowing it back in); re-prep, re-form, and grout the units, then move to the stabilizer area. | Compressors | Eagle / grout crew | In Progress |
| 18 | Instrument tracking Excel (on-site / missing / long-lead / out-of-scope) — construction managers reviewing; red-line decisions through Manny. | I&E | CMs / Manny | In Progress |
| 19 | Smooth out the dirt around the acid gas control panel foundations (skid steer) — some progress observed in the field today but not complete. | Acid Gas | AR foreman | In Progress |
| 20 | Compile the tank and pump account for the SEC, acid gas, and stabilizer compressors; determine oil types and quantities; submit the BOM to the oil supplier. | Compressors | Coordinator | Open |
| 21 | Ground and bond the newly set day tanks, staircases, and platforms — scope sits with Azota or Epic. | Kodiak | Azota / Epic | Open |
| 22 | Confirm whether the 4-inch ESD valve is sufficiently sized for the upsized 6-inch fuel gas line; get confirmation on the bridle level switches and add two 4-inch 600-rated strainers to the list — construction manager following up. | Fuel Gas | CM / Engineering | In Progress |
| 23 | Ensure the pipeline connection points (flanges, meter skids) are installed before the pipeline construction team arrives. | Pipeline & Plant | Coordinator | Open |
| 24 | Kodiak pre-commissioning begins — support startup activities. | Kodiak | Kodiak | Sched. 08-17 |
| 25 | Heater foundations — H-49200 (area 16): forms stripped, clips still to grind off, foundation forms still to remove. H-59200 (area 17): forms complete and ready to pour. | Civil | Civil crew | In Progress |
| 26 | Finish backfilling the adjacent foundation once the congestion/equipment access issue is resolved. | Civil | Civil crew | Open |
| 27 | Re-confirm the formal levelness of stabilizer compressors C-51150 and C-51175 after the 08-15 precision leveling and re-issue the levelness documentation for all three units before any alignment sign-offs. | Equipment | Coordinator / Leveling crew | Open |
| 28 | Determine Kodiak's plan to remove all paint and tape from the sight glasses and any other visual components on their skids. | Kodiak | Coordinator / Kodiak | Open |
| 29 | Establish a staging area with Mock for all tower scaffolding — supervisor walk first thing in the morning to set the staging spot and mark the no-go areas. | Towers | Coordinator / Mock | Open |
| 30 | CRITICAL — Track the Cisco switch removed from Rio 8 and sent to Pelham for HMI comms; make sure the replacement part is ordered through ops and installed when it arrives. | I&E | Coordinator / Ops | Open |
| 31 | Confirm Mock's torquing program on the stabilizer compressors — how torqued flange-ups are marked and verified; a few studs are missing on some flanges. | Piping / QC | Coordinator / Mock | Open |
| 32 | Chain fall incident (08-16) — locate the other broken chain link and deliver it to the safety department for a full inspection. | Safety | Coordinator / Safety | Open |
| 33 | Obtain and file a picture of the chain fall operator's card (Alexander). | Safety | Coordinator | Open |
| 34 | Confirm outcomes from the full-site stand-down, including any new company-wide policies or procedural updates. | Safety | Coordinator / Safety | Open |
| 35 | Define controls to prevent accidental grinder strikes on lifting equipment (storage, marking, proximity controls, training). | Safety | Safety / Supervisors | Open |
| 36 | Inspect the chain fall that has been hanging in the rack for two to three months — tag, certify, or remove it from service. | Safety | Supervisors | Open |

## PLAN FOR NEXT WORK DAY — TUE 08-18

- Tower coordination meeting with Gallup, WICK, Legacy, and MPLX.

- Measurement equipment review against Morgan Anderson's list.

- Continue tower scaffolding nights toward the 08-23 access target.

Interim report: the 08-17 Plaud field recording exists but has not been transcribed; content will be added and this report reissued once the summary is generated in the Plaud app. Register (1-36) carried from DR-2026-08-16; statuses are as last recorded, not verified for this date. DR-2026-08-18 and later reports add the tower-program items as 37-46.