TITAN 2 PROJECT · DAILY REPORT

Construction Coordinator Daily Report — Tuesday, August 18, 2026

Site:  MPLX Titan Gas Plant, Jal, NM

Owner:  Azota Gas Processing, Ltd.

Report No.:  DR-2026-08-18

Prepared By:  Construction Coordinator — Titan 2

Weather:  Not recorded

Crews On Site:  Not recorded (tower coordination meeting day — Gallup, WICK, Legacy, and MPLX represented)

## SUMMARY OF THE DAY

The tower inspection, cleaning, and closure coordination meeting was held with Gallup, WICK, Legacy, and MPLX. The program kicks off onsite 08-24 at 16:00 CT for all night-shift contractors, covering orientation and JSA review. The sequence runs tower by tower starting at T-43-700, with two newly added TG steel columns; scaffolding and access are targeted complete before 08-24, with drone aerials to be distributed. The workflow is a day/night handoff: Gallup works nights — opening manways, internal inspection (loose components, valve blockages), light cleanup, and closing after approval, at roughly two shifts per tower — while WICK inspects on days, tunneling each tower top to bottom for the final cleanliness buy-off against the engineering drawings. Legacy provides ventilation (pulling air through the towers) and a rescue plan per entry, with a separate day-shift rescue standby needed for WICK; up to three towers may run simultaneously. Vessel entries are restricted to roughly 06:00-10:00 for heat. Gallup will bring spare manway studs, bolts, washers, and gaskets (charged only for what is used) against the risk of damaged stud bolts. Nightly handoff meetings will track clean-and-close status per vessel; final closure authority rests with Manny and the inspection team.

## WORK PERFORMED / PROGRESS TODAY

- Tower program coordination: full sequence-of-operations meeting held; day/night handoff, tower sequence, and responsibilities agreed among Gallup (night internal work), WICK (day inspections), Legacy (ventilation and rescue), and MPLX.

- Access and readiness: scaffolding targeted complete by 08-23; rescue rigging may pull forward to 08-21-08-23 if scaffolding finishes early; drone aerial imagery to be shared for review.

- Materials: Gallup to stage extra manway hardware and gaskets; cool gaskets to be identified, ordered, and staged; manway cover quote being rechecked for Manny.

- Communications: follow-up email with the confirmed tower sequence and handoff expectations to go out today; nightly handoff meetings established with a daily deficiency list and call chain.

## INSPECTIONS & TESTS

- None performed today — coordination and planning day for the tower program.

- Scheduled: tower internal inspections begin from the 08-24 kickoff (Gallup nights, WICK days, entries about 06:00-10:00); Legacy ventilation in place by 08-22 and rescue plans by 08-23.

## ISSUES / DELAYS (4 OPEN)

- Manway stud bolts — damaged studs are expected on some manways; Gallup will carry spare hardware and gaskets so night work is not held up.

- Heat window — vessel entries limited to roughly 06:00-10:00, compressing WICK's day-shift inspection time; early 04:30 starts possible only with prior notice.

- Rio 8 HMI comms — Cisco switch still on loan to Pelham; replacement part remains a critical open item.

- Heater shell bolting/sealant — OPF procedure and clamshell sealant identification still outstanding.

Coordinator note: Weekend safety recap — a chain fall failed on 08-16 while lowering suction scrubber piping on the 640 train (no injuries or damage; a prior grinder strike on a link is suspected). A full-site stand-down was held. Follow-ups: recover the broken link for Safety, file the operator card, inspect the long-hanging chain fall in the rack, and define controls against grinder strikes on lifting gear.

## OPEN ACTION ITEMS

| # | Action | Area | Responsible / With | Status |
| --- | --- | --- | --- | --- |
| 1 | Tower inspection program with Gallup — coordination meeting held 08-18; onsite kickoff 08-24 at 16:00 CT for all night-shift contractors (orientation + JSA review); sequence starts at T-43-700 plus two newly added TG steel columns; night work by Gallup, about two shifts per tower. | Inspections | Coordinator / Gallup / CM | In Progress |
| 2 | Heater shells — obtain the correct bolting procedure from OPF (current-rev GA and erection manual, P.O. 24250-133; not in Procore) and determine what sealant is used where the two clamshell halves come together. | Heaters | Coordinator / OPF | Open |
| 3 | Support WICK's on-site inspection of the heaters and concrete foundations. | Heaters | Coordinator / WICK | Open |
| 4 | Coordinate with M4 for final pump alignment and inspection ahead of tie-in sign-off — paused until ready for final alignment. | Pumps | Coordinator / M4 | On Hold |
| 5 | Get with Mock to cover all open flanges or flanges with missing covers across the site. | Site | Coordinator / Mock | In Progress |
| 6 | Kodiak shade covers and acid gas awnings — awnings at 50%, acid gas platforms at 68%, concrete pads complete (status as of 08-14). | Kodiak / Acid Gas | AR foreman | In Progress |
| 7 | Stabilizer compressor interconnect piping — small bolt-ups and final torque remaining. | Piping | Mock / MACH | In Progress |
| 8 | Follow up with Kodiak to confirm whether the catalysts are installed and whether they stay in for the burn-in or come out. | Kodiak | Coordinator / Kodiak | Open |
| 9 | Have Mock haul the labeled aerial boxes for the Kodiak sweet gas compressors to the Conex box. | Kodiak | Mock | Open |
| 10 | Secure the shim packages and filters to prevent loss. | Kodiak | Field team | Open |
| 11 | CNG trailered fuel gas for turbine pre-commissioning — on hold as a contingency in case fuel gas is unavailable. | Turbines | Coordinator / CNG | On Hold |
| 12 | Follow up with the AR foreman on the piping estimation and clarify who procures the materials. | Piping | Coordinator / AR | Open |
| 13 | SEC compressor deficiencies — repair bent catwalk and damaged grating, remove tripping-hazard mounting brackets, fix platforms, add platforms on the east side. | SEC | AR foreman | In Progress |
| 14 | Measurement review — go over all received measurement equipment against Morgan Anderson's list; identify which meter skids serve the pipeline connections. | Equipment | Coordinator / Measurement | In Progress |
| 15 | Tower scaffolding — access targeted complete by 08-23, ahead of the 08-24 kickoff; drone aerial images to be distributed for review; contractor to leave time for cleanup. | Towers | Scaffold contractor | In Progress |
| 16 | Precision-level the three stabilizer compressors with machinist levels (rescheduled to 08-15 — completion to be confirmed). | Equipment | Leveling crew / Mock | Open |
| 17 | Bidell compressor grout — re-prep after wind-blown sand, re-form, and grout the units, then move to the stabilizer area. | Compressors | Eagle / grout crew | In Progress |
| 18 | Instrument tracking Excel (on-site / missing / long-lead / out-of-scope) — construction managers reviewing; red-line decisions through Manny. | I&E | CMs / Manny | In Progress |
| 19 | Smooth out the dirt around the acid gas control panel foundations (skid steer). | Acid Gas | AR foreman | In Progress |
| 20 | Compile the tank and pump account for the SEC, acid gas, and stabilizer compressors; determine oil types and quantities; submit the BOM to the oil supplier. | Compressors | Coordinator | Open |
| 21 | Ground and bond the newly set day tanks, staircases, and platforms — scope sits with Azota or Epic. | Kodiak | Azota / Epic | Open |
| 22 | Confirm whether the 4-inch ESD valve is sufficiently sized for the upsized 6-inch fuel gas line; bridle level switches and two 4-inch 600-rated strainers — construction manager following up. | Fuel Gas | CM / Engineering | In Progress |
| 23 | Ensure the pipeline connection points (flanges, meter skids) are installed before the pipeline construction team arrives. | Pipeline & Plant | Coordinator | Open |
| 24 | Kodiak pre-commissioning — support startup activities (start was scheduled 08-17). | Kodiak | Kodiak | In Progress |
| 25 | Heater foundations — H-49200: grind remaining clips and remove foundation forms; H-59200: forms complete, ready to pour. | Civil | Civil crew | In Progress |
| 26 | Finish backfilling the adjacent foundation once the congestion/equipment access issue is resolved. | Civil | Civil crew | Open |
| 27 | Re-confirm the formal levelness of stabilizer compressors C-51150 and C-51175 after precision leveling and re-issue the levelness documentation for all three units before any alignment sign-offs. | Equipment | Coordinator / Leveling crew | Open |
| 28 | Determine Kodiak's plan to remove all paint and tape from the sight glasses and other visual components on their skids. | Kodiak | Coordinator / Kodiak | Open |
| 29 | Scaffolding staging area with Mock — keep the staging spot and no-go areas enforced through the tower build. | Towers | Coordinator / Mock | In Progress |
| 30 | CRITICAL — Track the Cisco switch removed from Rio 8 and sent to Pelham for HMI comms; make sure the replacement part is ordered through ops and installed when it arrives. | I&E | Coordinator / Ops | Open |
| 31 | Confirm Mock's torquing program on the stabilizer compressors — how torqued flange-ups are marked and verified; a few studs are missing on some flanges. | Piping / QC | Coordinator / Mock | Open |
| 32 | Chain fall incident (08-16) — locate the other broken chain link and deliver it to the safety department for a full inspection. | Safety | Coordinator / Safety | Open |
| 33 | Obtain and file a picture of the chain fall operator's card (Alexander). | Safety | Coordinator | Open |
| 34 | Confirm outcomes from the full-site stand-down, including any new company-wide policies or procedural updates. | Safety | Coordinator / Safety | Open |
| 35 | Define controls to prevent accidental grinder strikes on lifting equipment (storage, marking, proximity controls, training). | Safety | Safety / Supervisors | Open |
| 36 | Inspect the chain fall that has been hanging in the rack for two to three months — tag, certify, or remove it from service. | Safety | Supervisors | Open |
| 37 | Send the follow-up email summarizing the 08-18 tower meeting — confirmed tower sequence, decisions, contacts, and handoff expectations — to all stakeholders. | Towers | Coordinator | Due 08-18 |
| 38 | Organize the 08-24 onsite kickoff (16:00 CT) and confirm every night-shift contractor has completed both the general and MPLX-specific orientations. | Towers | Coordinator | Due 08-24 |
| 39 | Identify, order, and stage the cool gaskets on site for the tower manway closures. | Towers | Coordinator | Due 08-23 |
| 40 | Legacy — rescue plan for each tower entry (by 08-23) and ventilation pulling air through the towers (by 08-22); Sam to produce the ventilation plan diagram and coordinate installation with the scaffold builders. | Towers | Legacy / Sam | Open |
| 41 | Arrange the day-shift rescue standby for WICK entries; plan rigging for up to three towers at once; if scaffolding finishes early, schedule rescue rigging 08-21 to 08-23. | Towers | Coordinator / Legacy | Open |
| 42 | Recheck the quote and status for the manway covers and provide it to Manny. | Towers | Chris Snyder | Due 08-21 |
| 43 | Provide Gallup the internal drawings for the remaining columns and obtain the tower manufacturer contact information for issue mitigation. | Towers | Coordinator / Project team | Due 08-24 |
| 44 | Distribute the pre-filled SIF/ship templates to Gallup and Safety for contacts and work steps. | Towers | Manny / Gallup / Safety | Due 08-22 |
| 45 | Run the nightly/evening handoff meetings (Gallup nights to WICK days) with the clean-and-close status per vessel; publish the daily deficiency list and the first/second/third-call contact chain to all teams. | Towers | Coordinator / Manny | Open |
| 46 | Hold the morning-only vessel entry window (about 06:00-10:00 for heat); give the night-shift lead prior notice for any 04:30-06:00 early starts. | Towers | Scheduling / Safety | Open |

## PLAN FOR NEXT WORK DAY — WED 08-19

- Send the tower-sequence follow-up email if not out; begin working the kickoff checklist (orientations, drawings, manufacturer contacts).

- Continue tower scaffolding toward the 08-23 access-complete target.

- Chase the cool gaskets order and the manway cover quote for Manny.

- Confirm Legacy's ventilation plan (Sam's diagram) is coordinated with the scaffold builders.

- Continue Bidell grout re-prep, acid gas dirt work, and the stabilizer torque/levelness follow-ups.

Compiled from the 08-18 Plaud recording of the tower inspection, cleaning, and closure coordination meeting, with the 08-16 incident-review recording (chain fall, safety stand-down) summarized in the coordinator note. Weather and crew counts were not recorded in the source notes. Register numbering continues the re-sequenced register from DR-2026-08-14: items 32-36 are the chain-fall incident follow-ups carried from DR-2026-08-16, and the new tower-program items are 37-46. Statuses on items 5-31 are carried from 08-14 — the 08-17 field recording has not been transcribed yet, so completions from Saturday through Monday are not yet reflected.