HAYFIELD PROJECT · DAILY REPORT

Construction Coordinator Daily Report — Friday, August 21, 2026

Site:  Hayfield

Owner:  Not recorded

Report No.:  DR-2026-08-21

Prepared By:  Construction Coordinator — Hayfield

Weather:  Not recorded — extreme-heat precautions in effect

Crews On Site:  Jones (~61), Valley (~32), Apache (15:00-01:00 shift), NBI, night painting crew; day and night shifts running

## SUMMARY OF THE DAY

The weekly coordination meeting worked through a flange class discrepancy, site safety, sign-in accountability, blow case piping, electrical tasks, and a backlog of approvals. On the 22-20 east and west units the model calls for Class 300 flanges, but the drawings, BOM, and this morning's field verification all confirm Class 150 installed with gaskets only and no orifice plates — the line is fuel gas service, where Class 150 is likely appropriate; the P&IDs will be cross-referenced and the findings sent to Brian and Ryan Stone. The night crew reassembled equipment and ran final torque, with the day crew finishing torque, inspection verification, and the reports/maps for Levi to upload to Procore. Blow case material is ordered (valves and approvals pending), pipe is being blasted and painted, and the new routing is set: Train 2 stays 2-inch to the tie-in, then a 3-inch header to the thermal oxidizers with an interconnect to Train 1's blow case. Earlier backward-line issues are corrected — the Train 1 fix was X-rayed 08-19 and hydrotests are complete. Civil starts Monday 08-24 after embed-plate delays, and tower-two scaffolding will be dismantled for tower one. Safety focus: barricade tagging on all four sides, a near walk-in between skids (no more cone-only gaps), heat discipline with the hospital 90 minutes out, a requested platform safety review, and no lighting at all in the slug catcher area — flagged critical for final sign-off. The single sign-in sheet is failing and will be replaced by rosters per contractor now and an operator-controlled sheet with roll call at brownfield go-live.

## WORK PERFORMED / PROGRESS TODAY

- Torque / reassembly: night crew reassembled equipment and performed final torque; day crew completing final torque, inspection verification, and torque reports/maps for Levi to upload to Procore.

- 22-20 flange verification: field verification completed this morning — both east and west units confirmed Class 150 with gaskets only, no orifice plates; documentation and stakeholder email in progress.

- Blow case piping: material ordered (valves pending); pipe on site being blasted and painted; demo of the existing 2-inch pipe planned per the new Train 2 / thermal oxidizer configuration.

- Piping corrections: backward-line issues corrected — Train 2 rack fixed with a spool; Train 1 fix X-rayed 08-19; Train 1 hydrotests complete and the Train 2 added piece tested.

- Safety: barricade standards reinforced (tags all four sides, no cone-only gaps after the near walk-in between skids); heat briefing with hydration plan; day/night housekeeping handoff standard set.

- Site accountability: sign-in process overhaul agreed — signage, per-contractor rosters, headcount cross-checks, a QR-code prototype, and an operator-controlled sheet with roll call for brownfield operations.

- Scheduling: civil work starts Monday 08-24 (embed-plate fabrication delays); night painters possibly off after Saturday, returning Monday; Apache crew continues 15:00-01:00.

## INSPECTIONS & TESTS

- Field flange verification on the 22-20 east and west units (Class 150 confirmed installed).

- Train 1 hydrotests complete; Train 2 added piece tested; Train 1 spool fix X-rayed 08-19.

- Scheduled: blow case weld X-ray Wednesday 08-26; NDE oversight with PT (first and final pass) required for any golden welds on hydrotested lines.

## ISSUES / DELAYS (4 OPEN)

- Slug catcher lighting — no lighting at all in the area; must be addressed before final sign-off (critical).

- PO-before-work bottleneck — the punch list and the blow case change order are held behind formal PO approval while the field is ready to work; BSV/PSV 1.5-inch modifications also on hold pending approval.

- Sign-in accountability — the single sheet is failing (illegible names, out-of-order entries, non-compliance, long lines); interim rosters go in while the QR and operator-controlled processes are stood up.

- Barricade gaps between skids — a near walk-in occurred where only cones were used; NBI and all vendors being held to the full barricade standard with tags on all four sides.

Coordinator note: Heat is a standing risk — the nearest hospital is 90 minutes away, so hydration discipline and early symptom recognition are being briefed to every crew. Shift tension over housekeeping was addressed: each crew leaves its area clean for the oncoming shift.

## OPEN ACTION ITEMS

| # | Action | Area | Responsible / With | Status |
| --- | --- | --- | --- | --- |
| 1 | 22-20 east/west flange class discrepancy — model shows Class 300 but drawings, BOM, and field verification (08-21) confirm Class 150 installed, no orifice plates (gaskets only); cross-reference the P&IDs for required class and orifice plate spec, confirm fuel gas pressure limits support Class 150, and send the findings summary to Brian / Ryan Stone with references. | Piping | Coordinator / Engineering | In Progress |
| 2 | Resolve the email-sending issues and forward the 08-20 email for context so all stakeholders receive the flange-discrepancy updates; update the BOM and drawings if discrepancies remain after engineering confirms. | Admin | Coordinator | Open |
| 3 | Barricades — tags on all four sides site-wide; notify NBI and all vendors of the barricade standards and active RT zones (no cone-only gaps between skids after the near walk-in incident); remove the unnecessary barricades at the reboiler. | Safety | Safety (Danny) / Vendors | In Progress |
| 4 | Sign-in overhaul — post mandatory sign-in/out signage at all entry points; run interim pre-printed alphabetized daily rosters per contractor (Jones ~61, Valley ~32) with in/out time columns; cross-check daily headcounts from contractor leads against the sheets; build the QR-code sign-in prototype (name, company, phone, timestamp, operations view for muster); align the final brownfield policy — single sheet controlled by the operator with control-room roll call. | Site Ops | Coordinator / Site Admin / Operations | In Progress |
| 5 | Enforce housekeeping handoff standards between day and night shifts — each crew cleans its work area for the oncoming shift; document exceptions. | Site Ops | General supers (day/night) | Open |
| 6 | Complete final torque on all designated connections with inspection verification; submit the torque reports and maps to Levi for Procore upload. | Mechanical | Mechanical lead / Levi | In Progress |
| 7 | Blow case piping — confirm material approvals and place the remaining valve orders; continue blasting/painting the pipe and stage for installation; demo the designated 2-inch pipe per the new configuration (Train 2 stays 2-inch to the tie-in, 3-inch header to the thermal oxidizers, interconnect to the Train 1 blow case). | Piping | Mechanical lead / Procurement / Piping crew | In Progress |
| 8 | Schedule the X-ray of the blow case welds for Wednesday 08-26; any golden welds on hydrotested lines require NDE oversight with PT on the first and final passes — no welding without QC present. | QC / NDE | QC-NDE coordinator (Ed's team) | Sched. 08-26 |
| 9 | Walk down the completed valve-orientation and spool corrections on Train 1 and Train 2 — Train 1 fix X-rayed 08-19, hydrotests complete; Train 2 rack fixed with a spool and the added piece tested. | Piping | Mechanical lead / Ops rep | Open |
| 10 | BSV/PSV 1.5-inch tie-in modifications — prepare the work package; work is on hold until approval is granted. | Mechanical | Engineering / Mechanical lead | On Hold |
| 11 | Maintain heat-safety measures — brief crews on symptoms and the hydration plan; nearest hospital is 90 minutes away. | Safety | Safety lead | Open |
| 12 | Confirm the night-crew schedule changes — painters potentially off after Saturday 08-22 and back Monday 08-24; Apache crew continues 15:00-01:00; communicate updates to all stakeholders. | Scheduling | Scheduling / Planner | Open |
| 13 | Excavation permit — none planned 08-21; issue the permit before any excavation is added to scope. | Permitting | Permitting coordinator | Open |
| 14 | Discuss bringing in a night-shift safety person. | Safety | Management | Open |
| 15 | Bring in the second painting crew once the change order is approved. | Painting | Mechanical lead | On Hold |
| 16 | CBO crew returns Monday 08-24 for the precast work on approved change orders. | Civil | CBO | Sched. 08-24 |
| 17 | Dismantle the scaffolding on the second tower to reuse the material on the first tower. | Towers | Scaffold crew | Open |
| 18 | Figure out how to access and inspect the trays in the bottom half of the tower. | Towers | Coordinator | Open |
| 19 | Conduct a safety review of all platforms — verify the modifications meet clearance standards. | Safety | Safety team | Open |
| 20 | Verify the thermal well at TI-640 by the RTD and install one if missing. | E&I | Electrical team | Open |
| 21 | Dress up and zip-tie the capillary tube to the pipe. | E&I | Electrical team | Open |
| 22 | Replace the bad fuse in MCC bucket 13L and procure a spare fuse for 13H. | E&I | Electrical team | Open |
| 23 | Follow up on the approval status of the punch list and the blow case change order; print and distribute the punch list to all inspection teams. | Admin | Coordinator / Ethan | In Progress |
| 24 | Investigate the pipe interfering with the grating installation on the coalescer filter platform. | Mechanical | Mechanical lead | Open |
| 25 | Build a custom platform for access to the latch valve and its bypass. | Structural | AR team | Open |
| 26 | Get an answer on whether to use all eight PITs on the HPA pumps or only the four supplied by the vendor. | E&I | Operations / Management | Open |
| 27 | Compile the list of missing instruments for Train 2. | E&I | Mechanical lead | Open |
| 28 | Install the level switches on the thermal lock bridle — waiting on the change order. | E&I | Mechanical lead | On Hold |
| 29 | Sort out and install the new sight glasses for the cash tanks. | E&I | Mechanical lead | Open |
| 30 | CRITICAL — Address the complete lack of lighting in the slug catcher area; required for final sign-off. | Electrical | Electrical / Mechanical lead | Open |

## PLAN FOR NEXT WORK DAY — SAT 08-22

- Send the 22-20 flange findings email to Brian / Ryan Stone; continue the P&ID cross-reference for the orifice plate requirement.

- Interim sign-in rosters and entry signage in place; headcount cross-check against the sheets.

- Dismantle tower-two scaffolding for reuse on tower one; work the platform safety review.

- Continue blow case pipe blast/paint and the 2-inch demo; night painters' potential last shift before returning Monday.

- Distribute the punch list to the inspection teams; keep pressing the punch list and blow case change order approvals.

First daily report for the Hayfield project, compiled from the 08-21 weekly coordination meeting recording (flange class discrepancy, site safety, sign-in process, blow case piping, electrical tasks, and approvals). The action item register starts fresh at 1-30 with related meeting to-dos consolidated; owners not named in the notes are marked by role. Site owner and weather were not recorded in the source notes.