TITAN 2 PROJECT · DAILY REPORT

Construction Coordinator Daily Report — Monday, August 10, 2026

Site:  MPLX Titan Gas Plant, Jal, NM

Owner:  Azota Gas Processing, Ltd.

Report No.:  DR-2026-08-10

Prepared By:  Construction Coordinator — Titan 2

Weather:  Not recorded

Crews On Site:  Eagle (grouting), AR (piping / catwalks), dehy assembly crew; counts not recorded

## SUMMARY OF THE DAY

Epoxy grout was poured on the recirculation pumps, and Eagle is on site for roughly two weeks (through about 08-24) to finish grout on the train 4 and train 5 recirculation pumps before forming and pouring the compressor bases at one compressor per day. Grouting sequence was coordinated with Eagle so the AGI compressor forming and pours (crew mobilizing 08-11, about two weeks to ready) do not clash with other groups. Stabilizer compressors C-51150 and C-51175 were checked for level, width, and length; a formal levelness report will be attached to the daily log. SEC compressor catwalks were walked down with the AR foreman, who will repair the bent catwalk and damaged grating and add bracing. Vessel-inspection paperwork was routed to Safety for review so WICK can be approved to work on site. Train 4 dehy assembly was expected complete by end of day.

## WORK PERFORMED / PROGRESS TODAY

- Pumps / Grouting: epoxy grout poured on the recirculation pumps; Eagle continuing grout work on the train 4 and train 5 recirculation pumps, on site through approximately 08-24.

- Compressor bases: plan set for follow-on crews to form and then pour the compressor bases, completing one compressor per day; crew scheduling coordinated to avoid conflicts during the pours.

- AGI compressors: grouting coordinated with Eagle to avoid clashes with other groups; Eagle crew mobilizing 08-11 to start forming the AGIs using a pump — forming, pouring, and cure to readiness estimated at about two weeks (through approximately 08-25).

- Stabilizer compressors (C-51150, C-51175): level, width, and length checked on both set units; formal report on levelness to be attached to the daily log. Crane schedule for setting the last stabilizer still to be verified.

- SEC compressors: walked the catwalks with the AR foreman and identified the deficiencies (bent catwalk, damaged grating); AR will make the repairs and install supports/bracing.

- Piping: AR foreman on site for a piping estimation; material procurement responsibilities to be clarified.

- Dehy (Train 4): assembly crew working; completion expected by end of day.

- Equipment list: equipment/measurement list ordered by Morgan for Titan 2 compiled and emailed to the team; shared with Azota to cross-reference against their inventory and purchase records to confirm what is on site.

- Kodiak units: day-tank placement to be selected with Kurt (safe, out-of-the-way location); decision pending on whether to install access platforms on the units — climbing them without platforms is a safety concern.

## INSPECTIONS & TESTS

- Vessel-inspection package reviewed with Chris and submitted to Safety for review and approval of WICK's on-site vessel inspection work.

- Stabilizer compressor level checks performed on C-51150 and C-51175; formal levelness report to follow.

- Scheduled: WICK vessel inspections to begin once Safety approves the work package.

## ISSUES / DELAYS (4 OPEN)

- SEC catwalk damage — bent catwalk and damaged grating are a safety concern; AR foreman has the deficiencies in hand and will repair and add supports.

- Kodiak access safety — no platforms on the units; climbing them is hazardous, and the platform-installation decision is still pending.

- Heater shell bolting procedure — still outstanding from OPF (P.O. 24250-133); shell assembly remains held.

- Hydro-test schedule unconfirmed — still awaiting Azota's plan; staged fabrication work held.

Coordinator note: Any new personnel arriving for the upcoming concrete pours (Eagle follow-on crews, forming/pour crews) must complete the site-specific safety orientation before starting work.

## OPEN ACTION ITEMS

| # | Action | Area | Responsible / With | Status |
| --- | --- | --- | --- | --- |
| 1 | Follow up with Gallup on the proposal for the fuel gas rerouting scope of work. | Fuel Gas | Coordinator / Gallup | Open |
| 2 | Obtain feedback from WICK on which manways need to be opened for vessel inspections. | Inspections | WICK | Awaiting |
| 3 | Obtain the correct bolting procedure for the new heater shells — request current-rev GA and erection manual from OPF (P.O. 24250-133); not in Procore. | Heaters | Coordinator / OPF | Open |
| 4 | Support WICK's on-site inspection of the heaters and concrete foundations. | Heaters | Coordinator / WICK | Open |
| 5 | Check stabilizer Odell units for east/west and north/south level with a machinist level — C-51150 and C-51175 checked for level, width, and length today. | Equipment | Field team | Done |
| 6 | Coordinate with M4 for final pump alignment and inspection ahead of tie-in sign-off. | Pumps | Coordinator / M4 | Open |
| 7 | Confirm Azota's plan and schedule (day/night) for hydro-testing the fabricated components. | Hydro-Test | Coordinator / Azota | Blocking |
| 8 | Clarify with Gallup whether a man-lift or scaffolding will be used for the contactor and amine still column inspections (man-lift preferred). | Inspections | Coordinator / Gallup | Open |
| 9 | Cover the suction inlets on the Kodiak units to prevent debris entry. | Kodiak | Field team | Open |
| 10 | Verify whether skid-mounted panels need shade covers to prevent overheating. | Kodiak | TBD | Open |
| 11 | Determine whether the control panel stairs require welding or can use existing brackets. | Kodiak | TBD | Open |
| 12 | Identify who is responsible for welding the stairs, if required. | Kodiak | TBD | Open |
| 13 | Verify who is responsible for providing and adding oil and coolant to the Kodiak units. | Kodiak | TBD | Open |
| 14 | Determine the status of the interconnect piping and whether additional parts are expected. | Kodiak | TBD | Open |
| 15 | Check whether catalysts are still in the exhaust systems and whether they must be removed for the 24-hour burn-in. | Kodiak | TBD | Open |
| 16 | Label the blue aerial boxes for their respective units. | Kodiak | Field team | Open |
| 17 | Store the labeled aerial boxes in the conics box. | Kodiak | Field team | Open |
| 18 | Secure the shim packages and filters to prevent loss. | Kodiak | Field team | Open |
| 19 | Complete the formal levelness report for stabilizer compressors C-51150 and C-51175 and attach it to the daily log. | Equipment | Coordinator | Open |
| 20 | Obtain the C&G quote so turbine testing and running can begin. | Turbines | Coordinator / C&G | Open |
| 21 | Follow up with the AR foreman on the piping estimation and clarify who procures the materials. | Piping | Coordinator / AR | Open |
| 22 | Repair the bent catwalk and damaged grating on the SEC compressors and install supports/bracing — deficiencies walked down with AR foreman today. | SEC | AR foreman | In Progress |
| 23 | Verify the crane schedule for setting the last stabilizer. | Equipment | Coordinator / Rigging | Open |
| 24 | Cross-reference the Titan 2 equipment/measurement list (ordered by Morgan) against Azota's inventory and purchase records to confirm what is on site. | Equipment | Azota | Open |
| 25 | Meet with Kurt to select a safe, out-of-the-way location for the Kodiak day tanks. | Kodiak | Coordinator / Kurt | Open |
| 26 | Decide whether to install access platforms on the Kodiak units (safety of climbing without platforms) or leave as-is. | Kodiak | TBD | Open |
| 27 | Ensure all new personnel arriving for the concrete pours complete the site-specific safety orientation. | Site Safety | Coordinator | Open |
| 28 | Obtain Safety's approval of the vessel-inspection package so WICK can start on-site vessel inspection work. | Inspections | Safety | Awaiting |

## PLAN FOR NEXT WORK DAY — TUE 08-11

- Eagle crew mobilizes to begin forming the AGI compressors (pump placement); confirm site access and readiness.

- Continue Eagle grout work on the train 4 and train 5 recirculation pumps.

- AR foreman to begin SEC catwalk/grating repairs and bracing.

- Chase the C&G quote for turbine testing and the crane schedule for the last stabilizer set.

- Coordinate crew scheduling around the upcoming compressor-base pours; run safety orientation for incoming personnel.

- Follow up with Safety on approval of the WICK vessel-inspection package.

Compiled from the 08-10 Plaud recordings: daily report notes (epoxy grouting, turbine quotes, grating repairs), construction coordination on the concrete pour and crew scheduling, AGI grouting and compressor catwalk coordination, the Kodiak day-tank and platform discussion, and field notes on the SEC catwalk walk-down and the WICK vessel-inspection safety submittal. Weather and crew counts were not recorded in the source notes. Responsible parties marked TBD to be assigned at next coordination meeting.