TITAN 2 PROJECT · DAILY REPORT

Construction Coordinator Daily Report — Friday, August 14, 2026

Site:  MPLX Titan Gas Plant, Jal, NM

Owner:  Azota Gas Processing, Ltd.

Report No.:  DR-2026-08-14

Prepared By:  Construction Coordinator — Titan 2

Weather:  Windy — blowing sand noted in the field

Crews On Site:  Mock, Eagle (grout), AR (platforms/awnings), civil crews; scaffolding crew arriving tonight; inspector Manuel Morales on site; counts not recorded

## SUMMARY OF THE DAY

The open action item register was walked down and cleaned up: the Legacy rescue team item is complete, the bridge/shell cutoff item was removed, the Bidell panel umbilical rework and the slug catcher end-cap investigation are done, and the list is re-sequenced 1-31 as directed. AR reports acid gas platforms at 68%, awnings at 50%, and concrete pads complete at 100%. The Bidell grout forms had to be pulled because wind kept blowing sand back under the compressor after cleaning — prep will be redone. Stabilizer leveling is rescheduled to Saturday morning 08-15 before the heat, and the interconnect piping is mostly complete with small bolt-ups and final torque remaining, though a few studs are missing on some flanges and Mock needs to confirm its torquing program. Tower scaffolding starts Saturday night and runs nights to a hard completion date of 08-24, with a staging-area walk with Mock set for first thing in the morning. On the heaters, H-49200 forms are stripped (clips to grind, foundation forms to remove) and H-59200 forms are complete and ready to pour. The Cisco switch from Rio 8 was sent to Pelham to help their HMI comms — flagged as a critical open item to get the replacement in and installed.

## WORK PERFORMED / PROGRESS TODAY

- Action-item review: register walked down by number — completions closed out, one item removed, dates updated, and the list re-sequenced 1-31.

- Acid gas compressors: AR progress — platforms 68%, awnings 50%, concrete pads 100%; dirt smoothing around the control panel foundations shows some progress but is not complete.

- Bidell compressors: grout forms pulled — dust and sand were not fully blown out from under the compressor and wind kept re-contaminating the surface; prep to be redone before grout.

- Stabilizer compressors: interconnect piping mostly complete with small bolt-ups and a final torque pass remaining; a few studs observed missing on flanges; torquing program (marking/verification) to be confirmed with Mock; precision leveling rescheduled to early Saturday 08-15.

- Heaters: H-49200 (area 16) — concrete forms stripped; clips still to be ground off and foundation forms removed. H-59200 (area 17) — forms complete and ready to pour.

- Towers / scaffolding: scaffolding crew arrives tonight; work starts Saturday night and runs nights until done, hard date 08-24; coordination set with Mock for a morning staging-area walk and no-go areas; contractor told to leave time for cleanup.

- Flange protection: Mock night crew to cover open flanges across the site (a couple on the Kodiaks, a couple on the towers).

- I&E / comms: Cisco switch removed from Rio 8 and sent to Pelham to help with HMI comms; replacement to be ordered through ops — tracked as a critical item.

## INSPECTIONS & TESTS

- Field walk-down performed — observations recorded on the acid gas panel dirt work, heater form status, stabilizer flange studs, and Bidell grout prep. Inspector Manuel Morales introduced on site.

- Scheduled: stabilizer precision leveling early 08-15; WICK manway/vessel work over the weekend 08-15–08-16; Kodiak catalyst follow-up and pre-commissioning start 08-17; measurement equipment review 08-18; Gallup Teams meeting 08-18 at 14:00.

## ISSUES / DELAYS (4 OPEN)

- Wind and blowing sand — re-contaminated the cleaned surfaces under the Bidell compressors; grout forms pulled and prep must be redone.

- Rio 8 HMI comms — the Cisco switch was pulled and loaned to Pelham; Rio 8 needs the replacement part ordered and installed (critical).

- Stabilizer flange torque — studs missing on some flanges and no confirmed marking/verification program from Mock yet; final torque pass pending.

- Heater shell bolting/sealant — OPF procedure still outstanding, and the sealant used between the clamshell halves needs to be identified.

Coordinator note: With scaffolding crews arriving tonight and running nights through 08-24, the morning staging walk with Mock needs to happen before their first shift so the no-go areas are marked ahead of material deliveries.

## OPEN ACTION ITEMS

| # | Action | Area | Responsible / With | Status |
| --- | --- | --- | --- | --- |
| 1 | Gallup vessel inspection — Teams meeting 08-18 at 14:00 to align the agenda with the other trades, onsite kickoff to follow; night work starts 08-24. | Inspections | Coordinator / Gallup / CM | In Progress |
| 2 | Heater shells — obtain the correct bolting procedure from OPF (current-rev GA and erection manual, P.O. 24250-133; not in Procore) and determine what sealant is used where the two clamshell halves come together. | Heaters | Coordinator / OPF | Open |
| 3 | Support WICK's on-site inspection of the heaters and concrete foundations. | Heaters | Coordinator / WICK | Open |
| 4 | Coordinate with M4 for final pump alignment and inspection ahead of tie-in sign-off — paused until ready for final alignment. | Pumps | Coordinator / M4 | On Hold |
| 5 | Get with Mock to go around the entire site and cover all open flanges or flanges with missing covers — Mock night crew starting on it (a couple on the Kodiaks, a couple on the towers). | Site | Coordinator / Mock | In Progress |
| 6 | Kodiak shade covers and acid gas awnings — awnings at 50%, acid gas platforms at 68%, concrete pads complete at 100%. | Kodiak / Acid Gas | AR foreman | In Progress |
| 7 | Stabilizer compressor interconnect piping — most runs complete; small bolt-ups and final torque remaining. | Piping | Mock / MACH | In Progress |
| 8 | Follow up with Kodiak on Monday to confirm whether the catalysts are installed and whether they stay in for the burn-in or come out. | Kodiak | Coordinator / Kodiak | Due 08-17 |
| 9 | Have Mock haul the labeled aerial boxes for the Kodiak sweet gas compressors to the Conex box. | Kodiak | Mock | Open |
| 10 | Secure the shim packages and filters to prevent loss. | Kodiak | Field team | Open |
| 11 | CNG trailered fuel gas for turbine pre-commissioning — on hold as a contingency in case fuel gas is unavailable (no black-start generator required for the trailer suction). | Turbines | Coordinator / CNG | On Hold |
| 12 | Follow up with the AR foreman on the piping estimation and clarify who procures the materials. | Piping | Coordinator / AR | Open |
| 13 | SEC compressor deficiencies — repair bent catwalk and damaged grating, remove tripping-hazard mounting brackets from the control panels, fix platforms, and add platforms on the east side. | SEC | AR foreman | In Progress |
| 14 | Measurement review — Measurement on site 08-18 to go over all received measurement equipment against Morgan Anderson's list; identify which meter skids serve the pipeline connections. | Equipment | Coordinator / Measurement | Sched. 08-18 |
| 15 | Tower scaffolding — starts Saturday night 08-15 and runs nights until complete; hard completion date 08-24; OSHA-compliant manway access; contractor to leave time for cleanup. | Towers | Scaffold contractor | In Progress |
| 16 | Precision-level the three stabilizer compressors with machinist levels — rescheduled to 08-15; crew ready early before the heat. | Equipment | Leveling crew / Mock | Sched. 08-15 |
| 17 | Bidell compressor grout — forms were pulled to re-blow dust and sand from under the compressor (wind kept blowing it back in); re-prep, re-form, and grout the units, then move to the stabilizer area. | Compressors | Eagle / grout crew | In Progress |
| 18 | Instrument tracking Excel (on-site / missing / long-lead / out-of-scope) — construction managers reviewing; red-line decisions through Manny. | I&E | CMs / Manny | In Progress |
| 19 | Smooth out the dirt around the acid gas control panel foundations (skid steer) — some progress observed in the field today but not complete. | Acid Gas | AR foreman | In Progress |
| 20 | Compile the tank and pump account for the SEC, acid gas, and stabilizer compressors; determine oil types and quantities; submit the BOM to the oil supplier. | Compressors | Coordinator | Open |
| 21 | Ground and bond the newly set day tanks, staircases, and platforms — scope sits with Azota or Epic. | Kodiak | Azota / Epic | Open |
| 22 | Confirm whether the 4-inch ESD valve is sufficiently sized for the upsized 6-inch fuel gas line; get confirmation on the bridle level switches and add two 4-inch 600-rated strainers to the list — construction manager following up. | Fuel Gas | CM / Engineering | In Progress |
| 23 | Ensure the pipeline connection points (flanges, meter skids) are installed before the pipeline construction team arrives. | Pipeline & Plant | Coordinator | Open |
| 24 | Kodiak pre-commissioning begins — support startup activities. | Kodiak | Kodiak | Sched. 08-17 |
| 25 | Heater foundations — H-49200 (area 16): forms stripped, clips still to grind off, foundation forms still to remove. H-59200 (area 17): forms complete and ready to pour. | Civil | Civil crew | In Progress |
| 26 | Finish backfilling the adjacent foundation once the congestion/equipment access issue is resolved. | Civil | Civil crew | Open |
| 27 | Re-confirm the formal levelness of stabilizer compressors C-51150 and C-51175 after the 08-15 precision leveling and re-issue the levelness documentation for all three units before any alignment sign-offs. | Equipment | Coordinator / Leveling crew | Open |
| 28 | Determine Kodiak's plan to remove all paint and tape from the sight glasses and any other visual components on their skids. | Kodiak | Coordinator / Kodiak | Open |
| 29 | Establish a staging area with Mock for all tower scaffolding — supervisor walk first thing in the morning to set the staging spot and mark the no-go areas. | Towers | Coordinator / Mock | Open |
| 30 | CRITICAL — Track the Cisco switch removed from Rio 8 and sent to Pelham for HMI comms; make sure the replacement part is ordered through ops and installed when it arrives. | I&E | Coordinator / Ops | Open |
| 31 | Confirm Mock's torquing program on the stabilizer compressors — how torqued flange-ups are marked and verified; a few studs are missing on some flanges. | Piping / QC | Coordinator / Mock | Open |

## PLAN FOR NEXT WORK DAY — SAT 08-15

- Precision-level the stabilizer compressors early, before the heat.

- Morning staging-area walk with the Mock supervisor; scaffolding crews begin tower scaffolding at night.

- Mock night crew continues covering open flanges site-wide.

- Re-prep the Bidell compressor grout surfaces (blow out sand) and re-form.

- WICK manway/vessel work over the weekend.

- Grind the H-49200 clips and remove the foundation forms; H-59200 ready to pour.

Compiled from the 08-14 Plaud daily report recording (action-item walk-down and field observations). Register housekeeping per coordinator's direction: completed/removed items closed out (old 45 complete; old 47 removed; old 48 and 51 done) and the full register re-sequenced 1-31 in order — old numbering is retired as of this report. Old-to-new mapping for reference: 1→1, 3→2, 4→3, 6→4, 9→5, 10→6, 14→7, 15→8, 16→9, 18→10, 20→11, 21→12, 22→13, 24→14, 30→15, 31→16, 35→17, 36→18, 38→19, 41→20, 42→21, 43→22, 44→23, 46→24, 49→25, 50→26, 52→27; new items 28-31.