## Summary
Hayfield Ridge Amine Facility — P&ID Redline Punch List & BOM Review
MPLX / Kinder Morgan Treating LP · Lea County, NM · Report date 2026-08-09 · Source: field-redlined P&ID set, 40 sheets (HAY-PID-01001…08005)
P&IDs reviewed | 40
Sheets with redlines | 39
Total punch items | 430
Critical | 86
High | 279
Medium | 48
Low | 17
BOM line items | 72
Engineering questions | 18
Punch items closed | 0
Punch items open | 430
Items by discipline | Items | Closed
Piping | 200 | 0
Mechanical | 27 | 0
I&E | 82 | 0
Electrical | 33 | 0
Civil | 14 | 0
Structural | 8 | 0
Engineering | 48 | 0
Operations | 13 | 0
Vendor | 5 | 0
How to use
• Each discipline has its own tab (sorted CRITICAL first) — sign off there: yellow columns Status / Closed By / Date Closed (example format: Closed / J. Smith / 2026-08-12). Summary counts update automatically.
• "Punch List (All)" is the read-only master index of all 430 items organized by P&ID; every item appears on exactly one discipline tab.
• Two combined Civil/Electrical items (01001-31, 02015A-06 grout + ground) are filed under Civil — the grounding part is Electrical scope.
• Priority: CRITICAL = before pressure test/commissioning/startup/safety · HIGH = before mechanical completion · MED = before turnover · LOW = documentation.
• BOM: "Verify in Piping Material Specification" (V-PMS) means the drawing does not state rating/material — order to the governing line class. Qty "±" requires field count.
• Descriptions quote the field redline text; item keys (e.g. 02011-02) match the published report page and PDF.

## Punch List (All)
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority
01001-01 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 2"-IA-7001-L2 | PCV-1001/-1002 | “Install (Inlet/outlet)” — install the two 1" IA take-off valves/drops feeding PCV-1001 & PCV-1002. | Piping | HIGH
01001-02 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Slug catcher area | X-11001/X-12001 | “Install Platforms (2)” — install two access platforms. | Structural | MED
01001-03 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Inlet gas | PIT-1001 | “Wire” — pull/terminate instrument wiring. | Electrical | HIGH
01001-04 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | 16" CSO valve | “Rotate Handle Due South” — reorient valve handle. | Piping | MED
01001-05 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | Inlet spec blind | “Roll after PSSR” — red-drawn spectacle blind at inlet 16" CSO valve; roll to open position after PSSR. | Operations | CRITICAL
01001-06 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | Outlet spec blind | “Roll after PSSR” — second red-drawn spectacle blind on outlet gas header to 16" launcher; roll after PSSR. | Operations | CRITICAL
01001-07 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | — | Red-drawn 1" valve w/ plug teed off outlet header at the blind — install. | Piping | HIGH
01001-08 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | — | “U/G” at OUTLET GAS HEADER TO 16" LAUNCHER flag — record underground transition (as-built). | Engineering | LOW
01001-09 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | — | “U/G” break-arc right of ESD station — record underground segment (as-built). | Engineering | LOW
01001-10 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | SV-1001, ZSO/ZSC-1001 | “Wire + Tubing” — complete wiring and pneumatic tubing at inlet ESD valve station. | I&E | CRITICAL
01001-11 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | SV-1002, ZSO/ZSC-1002 | “Wire + Tubing” — complete wiring and tubing at outlet ESD valve station. | I&E | CRITICAL
01001-12 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Inlet PSV vent | — | Red-drawn ½" valve w/ cap labeled “½"” on vent tailpipe below inlet PSV — install. | Piping | HIGH
01001-13 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | — | Red-drawn small-bore valve + cap on stub near 16"x10" control valve cloud — install. | Piping | HIGH
01001-14 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 3"-GH-0015-A2AS | PSV-1001 | “Confirm” — verify relief set pressure 1430 PSIG (fire) against nameplate/certs. | Mechanical | CRITICAL
01001-15 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 3"-GH-0017-A2AS | PSV-1003 | “Confirm” — verify relief set pressure (X-12001) against nameplate/certs. | Mechanical | CRITICAL
01001-16 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0003-F2AS | — | Red-drawn valve + blind flange on stub at elbow — install. | Piping | HIGH
01001-17 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0006-F2AS | — | Red-drawn vertical valve + cap teed up off line — install. | Piping | HIGH
01001-18 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Outlet gas | PIT-1002 | “Wire” — pull/terminate instrument wiring. | Electrical | HIGH
01001-19 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-11001 level bridle | LIT-1001 | “4x2 / Remove” + strike on ½" valve between LIT-1001 and control override — remove valve; verify 4"x2" reducer requirement. | I&E | HIGH
01001-20 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-12001 level bridle | LIT-1002 | Same markup as 01001-19 at X-12001 — remove ½" valve; verify 4"x2" reducer. | I&E | HIGH
01001-21 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-11001 bridle | LS-1001 | Red “2"” (twice) at bridle isolation valves — verify/upsize isolation valves to 2". | Piping | MED
01001-22 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-12001 bridle | LS-1002 | Red “2"” (twice) — same verification at X-12001 bridle. | Piping | MED
01001-23 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0002-F2AS-1½"H-ET | X-11001 | Red-drawn drain valve + plug on stub — install. | Piping | HIGH
01001-24 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0005-F2AS-1½"H-ET | X-12001 | Red-drawn drain valve + plug on stub — install. | Piping | HIGH
01001-25 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0003-F2AS-1½"H-ET | LV-1001 bypass | “Missing” (×2, pink highlight) — 4" cone strainer and 4" FD (“SIZE HOLD”) on NC bypass not installed. Install; engineering to release size hold. | Piping | CRITICAL
01001-26 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0006-F2AS-1½"H-ET | LV-1002 bypass | “Missing” (×2) — same missing 4" cone strainer + FD (SIZE HOLD) at X-12001 letdown bypass. | Piping | CRITICAL
01001-27 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Letdown loop | LY/LV-1001 | “Wire” — complete loop wiring. | I&E | HIGH
01001-28 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Letdown loop | LY/LV-1002, LSH/LSLL-1002 | “Wire” — complete loop wiring incl. level safety switches. | I&E | CRITICAL
01001-29 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Signal runs, X-11001 | — | Red slashes across dashed signal lines + “Wire” — pull signal wiring. | Electrical | HIGH
01001-30 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0004-F2AS-1½"H-ET | — | “Install pipe shoes (3)” — install three pipe shoes. | Piping | HIGH
01001-31 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Vessel saddles | X-11001/X-12001 | “Grout + Ground” — grout saddles and install grounding. | Civil / Elec | HIGH
01001-32 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | IA header drops | SC#1 / SC#2 | “Add valves (2) – SC#1 + SC#2” — add one IA isolation valve per slug catcher. | Piping | HIGH
01001-33 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 12"-GH-0010-F2AS | PT-1001A | Red cloud + “Wire” + leader re-tapping PT-1001A onto the 12" line — relocate tap, wire transmitter. | I&E | HIGH
01001-34 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 12"-GH-0010-F2AS | FE/FT-1001, TW/TE-1001 | Large hatched cloud over meter-run instruments + sketch of orifice run: “Installing Orifice Meter or RO + FIT ?” — engineering to confirm metering design; install per answer. (Eng. Question Q1) | Engineering | HIGH
01001-35 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | FV-1001 cloud | FV/FY-1001 | “Add” — red-drawn valves: 2" (×2) + ½" (×1) — install. | Piping | HIGH
01001-36 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Left of FV cloud | — | “U/G” break-arcs — record underground segments (as-built). | Engineering | LOW
01001-37 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 3"-LH-0011-F2AS-1½"H-ET | — | Red “2"-LH-0009-F2AS-1H-ET” added above unlabeled line; flag corrected to “Coalescing Filter / HAY-PID-02101”; “Δ 3x2” at branch — correct line tags on drawing; verify 3"x2" reducer at branch. | Engineering | MED
01001-38 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 2"-DR-7003-F2AS | — | Red-drawn new line + off-page flag to Liquid Blowcase (HAY-PID-07004) — add line to drawing; verify field tie-in (matches 07004 sheet markup). | Engineering | MED
01001-39 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Adjacent riser | PT-1001B | Red cloud + curved arrow — relocate PT-1001B tap to adjacent riser. | I&E | HIGH
01001-40 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 1"-GH-3006-F2AS | — | Red/pink highlight along line to Dehy Train I & II + “U/G” — record underground routing (as-built). | Engineering | LOW
01001-41 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Blowdown drain, X-12001 | — | “Wire + Tubing” — complete wiring/tubing in blowdown drain area. | I&E | HIGH
01001-42 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4" FC valve | ZSO/ZSC-1007 | “wire” — wire position switches on ESD blowdown valve. | I&E | CRITICAL
01001-43 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Near 4" FC station | — | “U/G” + break-arc — record underground transition (as-built). | Engineering | LOW
01003-01 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 10"-GH-0021-F2AS | V-22001 inlet | “Missing U-bolt (2)” — install two 10" U-bolts at inlet ESD station. | Piping | HIGH
01003-02 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 10"-GH-0021-F2AS | — | “Secure 2 U-bolt / Missing 1 U-bolt” — secure two existing U-bolts, install one missing. | Piping | HIGH
01003-03 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | Inlet ESD valve | SV-1004 | “Tubing” — complete pneumatic tubing at solenoid/quick-connect. | I&E | CRITICAL
01003-04 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-GH-0022-F2AS | — | “Add Gate Valve” — install 2" gate valve in bypass leg of inlet station. | Piping | HIGH
01003-05 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 top | — | “Add platform (AR)” — access platform as required. | Structural | MED
01003-06 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 3"-GH-0031-A2AS vent | V-22001 PSV | “Missing” + pink highlight over ENTIRE PSV package (PSV, 3" vent to ATM, 1½"-GH-0030-F2AS inlet, ½" bleed) — supply & install complete relief assembly (set per V-22001, 1435 PSIG design). | Mechanical | CRITICAL
01003-07 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-GH-0027-F2AS / 10"-GH-0026-F2AS | — | Pink/red triangle on 1" vent valve at junction (to Coalescing Filter) — verify/install 1" valve. | Piping | HIGH
01003-08 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | LIT-1004 | Red “LT” circle + “3X2” capped-stub sketch — mount LIT-1004 on 3"x2" reducer with cap. | I&E | HIGH
01003-09 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-21001 bridle | LIT-1003 / LSH-1003 | “Remove” + strike — remove ½" valve/plug between instruments. | I&E | HIGH
01003-10 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-21001 bridle | — | Red “3"” (twice) at bridle isolation valves — verify/upsize to 3". | Piping | MED
01003-11 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | LIT-1004 | “Remove” + strike — remove ½" valve at V-22001 bridle. | I&E | HIGH
01003-12 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | — | Red “3"” (twice) — verify/upsize bridle isolation valves to 3". | Piping | MED
01003-13 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 manway | MW | “Torque” — torque manway bolting to spec. | Mechanical | HIGH
01003-14 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 skirt | — | “Ground” — install vessel grounding. | Electrical | HIGH
01003-15 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0010-F2AS boot drain | — | Red-drawn ½" valve + plug teed off 2" boot-drain stub — install. | Piping | HIGH
01003-16 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0009-F2AS area | Bridle drain | “Missing 3" blind + ½" valve” — install 3" blind flange (w/ gasket & bolting) and ½" valve at bridle drain below lower nozzle. | Piping | CRITICAL
01003-17 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0009-F2AS | — | “Shim pipe shoe” — shim shoe downstream of V-22001 outlet valve. | Piping | HIGH
01003-18 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0009-F2AS | ESD-1004 | “Missing pipe shoe + shim” — install shoe + shim at FC letdown station. | Piping | HIGH
01003-19 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | Drain leg | — | “lift pipe & put shoe on beam” (1) — reset shoe onto beam. | Piping | HIGH
01003-20 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0010-F2AS | 2" FC (SIZE HOLD) | “lift pipe & put shoe on beam” (2) — reset shoe at letdown station. | Piping | HIGH
01003-21 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | ESD-1004 | ZSO/ZSC-1004 | “Tubing + lower latching switch to grade (Tubing)” — run tubing; relocate latching switch to grade. | I&E | CRITICAL
01003-22 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0009-F2AS | — | Red note “2"-LH-0009-F2AS / P&ID-02001” + circled 1 — line continues to HAY-PID-02001; update drawing continuity (mate of 02001-14). | Engineering | LOW
01003-23 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 3"-LH-0011-F2AS-1"H-ET | — | Red “3” size prefix added; flag sheet number struck, “02101” written — correct line size & continuation sheet on drawing. | Engineering | LOW
02001-01 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 10"-GH-0028-F2AS | — | Red sketch: two tap valves w/ bleeds flanking orifice-flange pair + “RO + FIT ?” — engineering to confirm whether RO + flow transmitter go here; install per answer. (Eng. Question Q2) | Engineering | HIGH
02001-02 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Filter inlet | FV S-1100 | “Remove Wood block” — remove shipping block from 10" FC valve. | Operations | CRITICAL
02001-03 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | S-1100 relief | PSV-1100 | “Missing” + pink highlight over full assembly (PSV set 1440 PSIG fire, 2" TO ATM tail, 2"x1" reducer, ½" bleed, 2" CSO block) — supply & install. | Mechanical | CRITICAL
02001-04 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Meter Skid #1 | Mustang SCS panel | “Conduit Installed, Need to pull wire” — pull & terminate wire to heated enclosure/stream splitter. | Electrical | HIGH
02001-05 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Level controller | LC S-1100B | “Rotate Due West” — reorient controller. | I&E | MED
02001-06 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Level controller | LC S-1100A | “Rotate Due East” — reorient controller. | I&E | MED
02001-07 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-C-0201-F2AS-1.5"H-ET | LCV-1100B | “Shoes” — install two pipe shoes on 2" condensate lines at station. | Piping | HIGH
02001-08 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Shutdown valve | SDV-1100, ZSO/ZSC-1100 | “Tubing” — complete pneumatic tubing. | I&E | CRITICAL
02001-09 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Below LC-1100A | — | “Tubing” — complete tubing on vertical 2" run/header connections. | I&E | HIGH
02001-10 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | LCV-1100A station | — | “shoe” — install one pipe shoe. | Piping | HIGH
02001-11 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | S-1100 | — | “Ground vessel + skid” — install grounding. | Electrical | HIGH
02001-12 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | S-1100 skirt | — | “Grout” — grout vessel base. | Civil | HIGH
02001-13 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Inlet riser u/s N1 | — | Red “½"” + arrowhead at coupling — install ½" valve/plug at open coupling. | Piping | HIGH
02001-14 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-LH-0009-F2AS | — | Red “2"-LH-0009-F2AS / P&ID-01003” + tie of 2"-C-0201 drop into gas outlet header — update drawing; verify field tie-in (mate of 01003-22). | Engineering | MED
02001-15 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-LH-0009-F2AS-1"H-ET | — | “U/G” + break — record underground segment of gas outlet header (as-built). | Engineering | LOW
02001-16 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Outlet header flag | — | Sheet number struck, “01001” written — correct continuation flag. | Engineering | LOW
02002-01 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | T-1 relief | PSV T-1 | “Confirm” — verify set pressure 1440 PSIG (fire) against nameplate. | Mechanical | CRITICAL
02002-02 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | 2"-V-0033-A2 | PSV vent | “Missing” + pink highlight — install 2" PSV vent tailpipe to ATM. | Piping | CRITICAL
02002-03 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | Same tailpipe | — | “Add Brace” — brace/support the vent tailpipe. | Piping | HIGH
02002-04 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | T-1 column | PDT T-1 | “Missing” + pink highlight along full ½" SS tubing run (top to bottom tap) — install dP impulse tubing (~55 ft + fittings). | I&E | HIGH
02002-05 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | 6"-LA-0025-F2 | — | “Secure U-bolt” — secure U-bolt on lean amine line near N3. | Piping | HIGH
02002-06 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | T-1 manway M1 (18") | — | “Torque after Inspection” — torque lower manway after internal inspection. | Mechanical | HIGH
02002-07 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | 8"-G-0103-F2AS | 8" CV60N | “Rotate 90° so Valve is Horizontal” — reorient inlet valve. | Piping | MED
02002-08 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | Lower head, near N9 | — | “Remove” + X — remove 2" capped valve/stub. | Piping | HIGH
02002-09 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | T-1 skirt | — | “Grout” — grout baseplate. | Civil | HIGH
02002-10 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | 6"-RA-0009-F2AS-SR | RO T-1 | “Confirm” — verify restriction orifice bore 1.5" per datasheet. | I&E | HIGH
02003-01 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 relief | PSV V-1 | “Confirm” — verify set pressure 1440 PSIG (fire, 1D2 orifice) against nameplate. | Mechanical | CRITICAL
02003-02 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | PSV V-1 tailpipe | — | “Add Brace” — brace 2" atmospheric vent riser. | Piping | HIGH
02003-03 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 nozzle N3 (2") | PI V-1 | “Remove” + X — remove small gauge/bleed valve at N3 between PI isolation and vessel. | I&E | HIGH
02003-04 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 manway M1 (18") | — | “Torque” — torque manway cover. | Mechanical | HIGH
02003-05 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 skirt | — | “Grout” — grout vessel base. | Civil | HIGH
02003-06 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | LV V-1 area | — | “Install platform” — access platform for level valve/instrument area. | Structural | MED
02003-07 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | 1"-C-0008-F2AS-SR | RO V-1 | “Missing” + pink highlight over printed “CHOKE NIPPLE / 3/8" BORE” — install 1" choke nipple, 3/8" bore, on condensate to flash tank. | Piping | CRITICAL
02003A-01 | HAY-PID-02003A | E | Gas Cooler AC-4 (400 GPM Amine Plant) | Louver actuator run | TY AC-4 | “Tubing” — install pneumatic tubing from TY AC-4 to automated louver actuator. | I&E | HIGH
02004-01 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | 8"-RA-0010-F2AS-SR | — | Red-drawn ½" valve + cap labeled “½"” on top of rich amine run — install high-point vent. | Piping | HIGH
02004-02 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 relief | PSV V-2 | “Confirm” — verify set pressure 150 PSIG (6R8) against nameplate. | Mechanical | CRITICAL
02004-03 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | PCV V-2B station | u/s bleed | Red “1"” + cap mark — change upstream bleed valve to 1", cap outlet. | Piping | HIGH
02004-04 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | PCV V-2B station | d/s bleed | Printed ¾" struck, “1"” + cap — change downstream bleed to 1", cap outlet. | Piping | HIGH
02004-05 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 nozzle M4 (4") | — | Small red check at flange pair (KMTD/MPLX break) — field verification mark; confirm intent/torque status. | Mechanical | MED
02004-06 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LG V-2A bridle, N8 | 2" GVTONT CSO | Red “CB10” — change upper bridle valve spec GVTONT → CB10 (retain CSO). | Piping | HIGH
02004-07 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LG V-2A bridle, N9 | 2" GVTONT CSO | Red “CB10” — change lower bridle valve to CB10. | Piping | HIGH
02004-08 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LIT V-2 standpipe | LIT V-2 | “Secure Wire” (two arrows) — secure wire/heat-trace along bridle standpipe. | Electrical | HIGH
02004-09 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LIT V-2 bridle | LIT V-2 | “Wire” — complete/terminate wiring at transmitter. | Electrical | HIGH
02004-10 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | 1"-DR-0003-A2AS | — | “Remove By MPLX” + X — remove flanged drain valve adjacent saddle. | Piping | HIGH
02004-11 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 saddles | — | “Grout (2)” — grout both saddles. | Civil | HIGH
02004-12 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 level end | — | “Install Platform” — access platform at level-instrument end. | Structural | MED
02005-01 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-V-0060-A2AS | Skid edge | “Add 2" valve / (CSO)” — install 2" CSO valve at skid-edge vent to drain system. | Piping | HIGH
02005-02 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 relief | PSV F-1 | “Confirm” — verify set 150 PSIG (fire, 1½F2). | Mechanical | CRITICAL
02005-03 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 degasser | — | “Missing ½" Tubing” + pink highlight — install ½" SS tubing run (check valve to ½"-V-0060-A1 tie-in). | I&E | HIGH
02005-04 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | Skid #1 limit (west) | — | Red-drawn 2" valve w/ X at skid boundary above rich-amine entry — pictorial for 02005-05; install with it. | Piping | HIGH
02005-05 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6"-RA-0012-A2-1.5"H-SR | — | “Add 2" check + Block” — install 2" check valve + 2" block valve at scope break (flush/aux connection). | Piping | HIGH
02005-06 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 inlet meter | FE F-1 | “Confirm” — verify orifice bore 2.0". | I&E | HIGH
02005-07 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 meter run | — | Red-drawn ¾" valve + plug below FE F-1 — install vent/bleed. | Piping | HIGH
02005-08 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6"-RA-0013-A2-1.5"H-SR | — | Red-drawn ¾" valve + plug near F-1 outlet riser — install drain/vent. | Piping | HIGH
02005-09 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-2 degasser | — | “Tighten ½" Tubing Ferrule” — tighten compression fitting. | I&E | HIGH
02005-10 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 1"-V-0071-A1 | PSV F-2 tail | “Doesn't Exist.” + X on printed 1" CSO valve — valve shown on drawing is not in field. | Piping | CRITICAL
02005-11 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 1"-V-0071-A1 | — | “Needs to Be Added Inside Skid limits.” — install the missing 1" CSO valve + tailpipe work inside skid. | Piping | CRITICAL
02005-12 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6" outlet header | — | Red-drawn valve + plug (size unmarked, ~¾") on header toward L/R exchanger — install low-point drain. | Piping | HIGH
02005-13 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-DR-0100-A1/A2 | — | Red continuation flag “2-DR-0100-A2 / HAY-PID-02016” at west end of drain header — correct drawing continuity; verify field tie-in. | Engineering | MED
02005-14 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-DR-0100-A1 (east) | — | Red emphasis chevrons on printed drain flag — verify/connect continuation to HAY-PID-02006. | Piping | MED
02006-01 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 6"-LA-0022-A1 | TI/TW E-1D | Red cloud + tag “E-1D” on unlabeled TI/TW bubble — install & tag temperature indicator with thermowell on E-1 lean amine outlet. | I&E | HIGH
02006-02 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 6" crossover branch | — | Red-drawn valve + plug (no size) upstream of 6" block valve — install vent/drain bleed. | Piping | HIGH
02006-03 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 2"-DR-0100-A2 (west) | — | Red “2-DR-0100-A2” filled into blank continuation flag over HAY-PID-02005 — correct drawing (mate of 02005-13). | Engineering | LOW
02006-04 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 2"-DR-0100-A1 (east) | — | Red emphasis on printed flag to HAY-PID-02007 — verify continuation/tie-in. | Piping | MED
02007-01 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0018-A1-1.5"H | P-1A discharge | Red “½"” + drawn valve between check and block — install ½" valve (vent/gauge). | Piping | HIGH
02007-02 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0019-A1-1.5"H | P-1B discharge | Red “½"” + drawn valve — install ½" valve. | Piping | HIGH
02007-03 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 1"-V-0076-A1 | 1" C1203F LSD | “Dosn't Exist.” [sic] + cloud — printed 1" shutdown valve not in field; reconcile install vs drawing revision. (Eng. Question Q13) | Engineering | HIGH
02007-04 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 1"-V-0076-A1 branch | ½" CB203 | “plug” — install ½" plug on open connection below valve near PSV F-4. | Piping | HIGH
02007-05 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0021-A1-1.5"H | 6" CV10 | “Dosn't Exist.” + cloud — printed 6" valve on lean amine outlet not in field; reconcile. (Eng. Question Q13) | Engineering | HIGH
02007-06 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 2"-DR-0100-A1 (east) | — | “Removed” + cloud + cut marks — drain header terminus piping removed in field; update drawing / confirm extent. | Engineering | MED
02007-07 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 2"-AFD-8402-APG-1.5"H-ET | — | “Remove 2x4 & Adjust support” — remove temporary lumber, install permanent support. | Piping | HIGH
02007-08 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | Spare-filter bridges | PDI F-4B / F-4C | Red tick marks on both PDI balloons — verify gauges installed/functional. | I&E | MED
02008-01 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-AFD-8406-APG-1.5"H-ET | — | “Add shoes (4)” — install four pipe shoes on antifoam line at skid-edge run. | Piping | HIGH
02008-02 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-W-8305-A2AS-1.5"H-ET | X-2 | “Missing” + pink highlight — install MPLX-supplied 2" static mixer X-2 (Note 1). | Mechanical | HIGH
02008-03 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | Notes block | — | Pink highlight on note “1) SUPPLIED BY MPLX.” — cross-reference to 02008-02 (locate MPLX-supplied material). | Operations | MED
02008-04 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-RF-0035-A2-1.5"H-ET-SR | LV T-2 | Red “¾” + drawn valve below line — install ¾" drain/bleed between block and check. | Piping | HIGH
02008-05 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-RF-0035-A2-1.5"H-ET-SR | Skid limit | Red “2" / Add” + drawn gate valve — install 2" block valve at Skid #1 limit crossing. | Piping | HIGH
02009-01 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 12"-AG-0031-A2AS-1.5"H | PSV T-2 | “Confirm” — verify pilot-operated PSV set 100 PSIG. | Mechanical | CRITICAL
02009-02 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 10"-LA-0017-A2-1.5"H | — | Red “1"” ×3 + drawn valves — install two 1" high-point vents and one 1" drain on lean amine to reboiler. | Piping | HIGH
02009-03 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | LG T-2A MAG bridle | — | “Missing” — install ½" CB203 vent (top) and ½" CB203 drain (bottom) on gauge bridle. | I&E | HIGH
02009-04 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 2"-DA-2001-A2-1.5"H-ET, N11 | 2" CB10 | Red “CSC” beside printed CSO — car-seal-closed per field; reconcile CSO vs CSC with engineering. (Eng. Question Q10) | Operations | CRITICAL
02009-05 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Nozzle C2 gauges | PI T-2B, TI T-2B | Red range edits “0-100#” / “50-200F” — verify/replace gauges to marked ranges. | I&E | MED
02009-06 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 2"-DA-2002-A2-1.5"H-ET, N14 | 2" CB10 | Red “CSC” — same car-seal reconciliation at bottom drain. | Operations | CRITICAL
02009-07 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | T-2 manway M2 (20") | — | “Torque After Inspection” — torque after internal inspection. | Mechanical | HIGH
02009-08 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | T-2 skirt | — | “Grout” — grout base ring. | Civil | HIGH
02009-09 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Lower T-2, N9 area | — | “Install platform” — access platform at reflux line/valve area. | Structural | MED
02009-10 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Still-bottoms bridle | LIT T-2B | “Electrical Cover” — install missing transmitter housing cover. | Electrical | HIGH
02009-11 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Acid gas PV loop | PY T-2 / PV T-2 | “Tubing” — install instrument air tubing (I/P to valve). | I&E | HIGH
02009-12 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 14"-AG-0033-A2AS-SR PCV station | — | “Install platform” — access platform at 8" acid gas control station. | Structural | MED
02010-01 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | 8"-LA-0022-A2 relief riser | PSV AC-1 | “Missing” + pink highlight — install PSV AC-1 (2"x1½", set 150 PSIG, check-valve-failure case) and relief route via 3"-V-0102-A2. | Mechanical | CRITICAL
02010-02 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | PSV AC-1 inlet riser | 2" CV10 | Red “CSO” — car-seal-open the isolation valve. | Operations | CRITICAL
02010-03 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | AC-1 louver run | TY AC-1C | “Tubing” — install I/P-to-louver-actuator tubing. | I&E | HIGH
02010-04 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | AC-2 louver run | TY AC-2C | “Tubing” — install tubing to AC-2 louver actuator. | I&E | HIGH
02010-05 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | AC-2A/B area | — | “Cleanup Area” — housekeeping. | Operations | MED
02011-01 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 3"-V-0073-A2 | — | Red “3" / Add” + drawn gate valve — install 3" block valve before the drain-system flag. | Piping | HIGH
02011-02 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 3"-V-0073-A2 | PSV P-3C path | “Discharge Pressure? Goes to 165# MAWP Vessel” — engineering must verify 1440 PSIG relief routing to low-pressure drain vessel. (Eng. Question Q3) | Engineering | CRITICAL
02011-03 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | Relief | PSV P-3C | “Confirm” — verify pilot-operated PSV set 1440 PSIG (blocked flow). | Mechanical | CRITICAL
02011-04 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | PSV P-3C station | — | “Missing” + pink highlight — install ½"x⅜" SS tubing run to P-3A discharge valve string. | I&E | HIGH
02011-05 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-G2 | PIT P-3A2 | Red bubble + two drawn root valves at new tap between CV90 and check — relocate PIT P-3A2 tap here; install two small-bore root valves. | I&E | HIGH
02011-06 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A discharge cluster | PI/PIT P-3A2 | “Wire” + cloud — pull/terminate wiring. | Electrical | HIGH
02011-07 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A suction | PI/PIT P-3A1 | “Wire” — wire loop. | Electrical | HIGH
02011-08 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0024-G2 | PI/PIT P-3D | “Wire” + cloud + tap arcs — wire P-3B discharge instruments; relocate tap (mirror of 02011-05). | I&E | HIGH
02011-09 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3B suction | PI/PIT P-3C | “Wire” — wire loop. | Electrical | HIGH
02011-10 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A flanges | — | “Bolt up After Alignment” — final bolt-up of 4" 900# discharge spool and 6" 150# suction flange after alignment. | Mechanical | HIGH
02011-11 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3B flanges | — | “Bolt up After Alignment” — same at P-3B. | Mechanical | HIGH
02011-12 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-G2 | 6" CV90 | “Valve Handle” — install missing handwheel at P-3A discharge block. | Piping | HIGH
02011-13 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0024-G2 | 6" CV90 | “Valve Handle” — install missing handwheel at P-3B discharge block. | Piping | HIGH
02011-14 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-F2 | FIT/FIC P-3 | “Missing” + pink highlight — install FIT P-3 dP transmitter, both impulse manifold valve sets, and tubing on common discharge meter. | I&E | CRITICAL
02011-15 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-F2 | FE P-3 | “Confirm” — verify orifice bore 3.5" per datasheet. | I&E | HIGH
02011-16 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A suction drop | 6" cone strainer | Red doodle at temporary strainer — verify installed; remove after flushing per commissioning plan. | Piping | HIGH
02011-17 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3B suction drop | 6" cone strainer | Same verification at P-3B. | Piping | HIGH
02012-01 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 level bridles | LG/LT E-2A, E-2B | Large cloud: “Change all of Them to Gate Valves” — replace all bridle isolation valves (½", ¾" CB203; 2" CB10 CSO) with gate valves; count in field before ordering. | Piping | HIGH
02012-02 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 platform | — | “Platform Grating” — install missing grating at reboiler platform. | Structural | HIGH
02012-03 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 shell relief | PSV E-2 | “Missing” + cloud — install 2"x1" thermal PSV, set 150 PSIG. | Mechanical | CRITICAL
02012-04 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 bridles | LT E-2A / E-2B | “Wire” — wire both level transmitters. | Electrical | HIGH
02012-05 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 1"-V-0094-A2 area | TIT E-2E | “Wire” — wire temperature transmitter. | Electrical | HIGH
02012-06 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 1"-V-0094-A2 | — | “Secure” — support/secure 1" drain line. | Piping | HIGH
02012-07 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 24"-LA-0029-A2-1.5"H | — | “1"⌀ — Needs plug” — plug open 1" stub next to TE/TW E-2E. | Piping | CRITICAL
02012-08 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 supports | — | “Grout supports” — grout at containment. | Civil | HIGH
02012-09 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | TCV E-2 station | — | “Shim pipe shoes (3)” — shim three shoes at hot-oil control station. | Piping | HIGH
02012-10 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 shell (S4–S1) | — | Red-drawn 2" valve at shell connection — install (field addition). | Piping | HIGH
02012-11 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | TCV E-2 station | — | Red “6"” at four station valves — verify actual valve sizes vs drawing; revise drawing or valves. (Eng. Question Q9) | Engineering | MED
02012-12 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 3"-GH-7008-A2 meter | FQI H-1 | “Wire” — wire fuel-gas metering cluster. | Electrical | HIGH
02013-01 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 2"-GH-7004-A2 | — | Red-drawn 2" valve u/s of PCV-100 — install 2" fuel gas isolation valve. | Piping | HIGH
02013-02 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 2"-FG-2220-A2 | FE/FIT-100 | “Missing / Need RO + FIT / wire pulled” + pink highlight — install restriction orifice FE-100 and transmitter FIT-100; terminate pulled wire. | I&E | CRITICAL
02013-03 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | VCU-101 stack | Bird screen | “Remove plastic/wood” — remove shipping covers from stack outlet. | Operations | CRITICAL
02013-04 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | VCU-101 burner | BS-101/102/103, FR-101/103 | “Wire (By Zeeco)” — flame scanner/rod wiring to JB-101, vendor scope. | Vendor | CRITICAL
02013-05 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 14"-AG-0033-A2AS-SR | — | Red-drawn high-point vent (valve + plug) before KOD-301 — install (likely 1"; verify size). | Piping | HIGH
02013-06 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 | PSV-301, PG-301, LSHH/LSH/LSL/LSLL-301 | “Missing wire pulled” + pink highlight — install PSV-301 (set 100 psig, vent SIZE HOLD), PG-301 + ½" MNV, full level-switch stack; terminate wiring. | I&E | CRITICAL
02013-07 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 top | — | Red-drawn valve at PSV/inlet nozzle connection — install small-bore valve. | Piping | HIGH
02013-08 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 drain | — | Red-drawn 2" valve at drain termination d/s of flame arrestor — install. | Piping | HIGH
02013-09 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 14" vent header, NOTE 7 | — | “14" Add” + drawn valve + pink highlight — install 14" 150# valve d/s of XV-301. | Piping | CRITICAL
02013-10 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-401 | PSV-401, PG-401, LSHH…LSLL-401 | “Missing wire pulled” + pink highlight — install PSV-401 (set 15 psig), PG-401, level-switch stack; terminate wiring. | I&E | CRITICAL
02013-11 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-401 overhead 3" line | — | “Add / 3"” + drawn valve d/s of XV-401 — install 3" 150# valve. | Piping | CRITICAL
02013-12 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-401 skid | — | “Grout (2)” — grout two base points. | Civil | HIGH
02013-13 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | VCU-101 / BL-101 base | — | “Grout” — grout base. | Civil | HIGH
02013-14 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | Blower | BL-101 | “wire + ground” — power wiring and grounding. | Electrical | HIGH
02014-01 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | Fuel gas supply (L) | — | “Tubing” — install ¼" fuel-gas supply tubing run. | I&E | HIGH
02014-02 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | Diffuser feed | DIF-001A | “Missing Tubing” + pink highlight — install tubing PY-1001A → diffuser at condenser inlet. | I&E | HIGH
02014-03 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | D — system by-pass vent | — | Cloud: “Missing / Not on ISOs / SKID LIMITS” — fabricate/install 2" NPT bypass-vent piping; add to ISOs. (Eng. Question Q6) | Piping | HIGH
02014-04 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 2"-PV-2053-A2 | — | “Add 2" Valve (CSO)” — install at condenser vapor outlet near PSV-1100A. | Piping | HIGH
02014-05 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | ½" tubing from 2"-GH-7006-A2 | PCV-2002A | Red X + pink highlight — install PCV-2002A regulator (set 100 psig) with tubing (see -11). | I&E | HIGH
02014-06 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 1"-GI-7001-F2AS | — | “1" Add valve” — install 1" valve in flame-arrestor branch. | Piping | HIGH
02014-07 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 3"-PV-3001-A2 | — | “3" Add valve” — install 3" valve at skid edge. | Piping | HIGH
02014-08 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | TK-1200A | LG-1200A | “Missing” + pink highlight — install gauge glass + 2×¾" isolation, ½" vent, ½" drain valves. | I&E | HIGH
02014-09 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | TK-1200A east head | — | “plug” — plug open 1½" connection. | Piping | CRITICAL
02014-10 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 2" NPT bypass-vent run | — | “Missing” + cloud/pink — fabricate/install segment from D vent past HZZ-1100A to BTEX outlet drop near SP-1100A. | Piping | HIGH
02014-11 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | Motive gas (P) circuit | — | “Missing Tubing” — install ½" tubing riser + header to ABV-1000A and ½"-PV-2054-A2. | I&E | HIGH
02014-12 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | Condenser liquid outlet | ABV-1200A | “Wire” — wire actuated 3-way valve. | Electrical | HIGH
02014-13 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | V-7000A vent/condensate | LS-1000A / CV-001 | “Tubing” — install tubing for reset/vent circuit to B outlet. | I&E | HIGH
02014-14 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 2"-DA-2051-A2-1.5"H-ET | — | “2" Add Valve” — install 2" valve in drain to slop tank. | Piping | HIGH
02115-01 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 2"-GH-7005-A2 | — | Red-drawn 2" valve u/s of PCV-103 — install 2" fuel gas isolation valve. | Piping | HIGH
02115-02 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 2"-FG-2222-A2 | FE/FIT-101 | “Missing / RO? / wire pulled” + pink highlight — install FE-101 orifice + FIT-101; terminate pulled wire. | I&E | CRITICAL
02115-03 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | VCU-102 stack | Bird screen | “Remove Wood/Plastic” — remove shipping covers. | Operations | CRITICAL
02115-04 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | VCU-102 burner | BS-104/105/106, FR-106 | “wire (By Zeeco)” — flame scanner wiring to JB-101, vendor scope. | Vendor | CRITICAL
02115-05 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 14"-AG-0040-A2AS-SR | — | Red-drawn high-point vent (valve + plug) before KOD-302 — install (verify size). | Piping | HIGH
02115-06 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 | PSV-302, PG-302, LSHH…LSLL-302 | “Missing” + pink highlight — install PSV-302 (set 100 psig, vent SIZE HOLD), PG-302 + ½" MNV, level-switch stack. | I&E | CRITICAL
02115-07 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 14" inlet drop | — | Red-drawn valve at inlet connection — install (size per connection; verify). | Piping | HIGH
02115-08 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 bridle | LG-302 | “Missing” — install gauge glass + 2×1" BAV isolation valves + ½" vents. | I&E | HIGH
02115-09 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 2" drain | — | Red-drawn valve + termination at open end — install 2" valve (+ flame arrestor per KOD-301 pattern). | Piping | HIGH
02115-10 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 14"-VF-0023-A2 | — | “Install U-bolt” — install 14" U-bolt on vent header. | Piping | HIGH
02115-11 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 14"-VF-0023-A2, NOTE 7 | — | “14" Add” + drawn valve d/s of XV-302 — install 14" 150# valve. | Piping | CRITICAL
02115-12 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-402 | PSV-402, LSHH…LSLL-402 | “Missing” + pink highlight — install PSV-402 (set 15 psig) + level-switch stack. | I&E | CRITICAL
02115-13 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-402 overhead → 3"-VF-0003-A2 | — | “3" Add” + drawn valve d/s of XV-402 — install 3" 150# valve. | Piping | CRITICAL
02115-14 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | Detonation arrestors | TE-402 / TE-403 | “wire (pulled)” — terminate TE-402/403 (TAHH @ 250°F). | I&E | CRITICAL
02115-15 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | VCU-102 inlet area | — | “Install 1" IA Plug This Area” — locate open IA connection, install 1" plug. | Piping | HIGH
02115-16 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-402 skid | — | “Grout (2)” — grout two base points. | Civil | HIGH
02115-17 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | VCU-102 / BL-102 base | — | “Grout” — grout base. | Civil | HIGH
02115-18 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | Blower | BL-102 | “Wire + Ground” — power wiring and grounding. | Electrical | HIGH
02015A-01 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | 8"-HM-108A-C2-1.5"H | TE/TI/TY-27001A | “Wire” — wire inlet temperature loop. | Electrical | HIGH
02015A-02 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater outlet | TE-27002A | “Wire” — wire control thermocouple (TIC-27002A loop). | Electrical | CRITICAL
02015A-03 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater outlet detail | PI-27002A | Cloud + pink: “Missing / Not on ISO's” — outlet pressure-gauge assembly (0-160 psig, ½" NPT valve, siphon) missing; shipped-loose per Note 8, MPLX installs. | I&E | HIGH
02015A-04 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | 8"-HM-187-C2-1.5"H | — | “Missing PI, Requires Tap on 8"” — hot-tap/weld ½" threadolet on 8" outlet line for the PI. (with -03) | Piping | HIGH
02015A-05 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Coil feed runs | FE-27003A/-04A/-05A | “Torque (By Sigma Thermal ?)” — torque three 4" 300# orifice-flange sets; confirm responsibility. (Eng. Question Q8) | Vendor | CRITICAL
02015A-06 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater/stack skid | — | “Grout + ground” — grout base, install grounding. | Civil / Elec | HIGH
02015A-07 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Combustion blower | — | “Shim Blow Motor & Remove straps” — shim motor, remove shipping straps. | Mechanical | HIGH
02015A-08 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater electrical | — | “Missing 2" seal off cover” — install. | Electrical | HIGH
02015A-09 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater instruments | — | “Remove instrumentation plastic” — remove shipping wrap. | Operations | MED
02015A-10 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater electrical | — | “Missing 2-1" & 2-2" electrical Covers” — install two 1" and two 2" covers. | Electrical | HIGH
02015A-11 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Blower 8" flange | — | “Bolt up Blower 8" (by Sigma Thermal ? Need Garlock gasket)” — bolt up; procure 8" Garlock gasket; confirm responsibility. (Eng. Question Q8) | Vendor | CRITICAL
02015A-12 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Notes block | Note 8 | Pink highlight on “SHIPPED LOOSE BY SIGMA THERMAL AND INSTALLED IN PIPING BY MPLX” — locate all shipped-loose items and install. | Operations | HIGH
02015B-01 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-106 | — | Red tick at tee — marks tap point for 1" side-stream supply (see -02). | Piping | MED
02015B-02 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-106 → filter | SSI-30001A | Red “1"” + drawn field routing from 6" return header to filter — install 1" side-stream supply piping. | Piping | HIGH
02015B-03 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | Filter hookup | SSI-30001A | Red-drawn loop through filter inlet/outlet (1" 3000# SW nozzles) — re-route/complete filter piping per sketch. | Piping | HIGH
02015B-04 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | SSI-300017 riser | — | Red trace at header crossing — crossing only (no connection); as-built clarification. | Engineering | LOW
02015B-05 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-110 | — | Red “1"” + drawn drop — tie side-stream return into discharge header as 1" drop (branch fitting required). | Piping | HIGH
02015C-01 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | ¼"-GH-2001-A2 | PCV-2001 | “Missing (¾" valve installed on Adjacent 3" FG pipe)” + pink highlight — blanket-gas regulator station (set 30 psig) not installed as drawn; field deviation exists. Install per design / reconcile. (Eng. Question Q5) | I&E | CRITICAL
02015C-02 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | To nozzle C3 | — | “¼" Tubing Missing” + pink highlight — install blanket-gas tubing across scope breaks to tank top. | I&E | CRITICAL
02015C-03 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzles C1, C3 | — | Red checks on both 150# RF flanges — complete/verify hookups (with -02). | Piping | HIGH
02015C-04 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 1½"-PV-0003-A2 | PSV-45001A | “Confirm” — verify set 25 PSIG. | Mechanical | CRITICAL
02015C-05 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzle C6 | LSL-45001A | “Wire” — wire low-level interlock (wiring by MPLX, Note 6). | Electrical | CRITICAL
02015C-06 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzle C7 | TP-E6 | Cloud: “Where to?” / “Don't Exist – Not on ISO's” — test point connection absent and unrouted; engineering to clarify. (Eng. Question Q4) | Engineering | HIGH
02015C-07 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 8"-HM-187-C2-1.5"H | — | Cloud + “Missing” — install 8" loop/seal (gooseneck) assembly with plug/blind at skid boundary. | Piping | HIGH
02015C-08 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 8"-HM-180 / 8"-HM-187 | FCV-45001A | Cloud + pink: “Doesn't Exist – Not on ISO's” / “Missing” — 8" control-valve station absent entirely; engineering to confirm requirement, then procure/install. (Eng. Question Q4) | Engineering | CRITICAL
02015D-01 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | ¼"-GH-2001-A2 branch | — | “Missing (see 2015C)” + pink highlight — install fuel-gas blanket branch off 3"-GH-7008-A2 (pairs with 02015C-01/-02). | Piping | CRITICAL
02015D-02 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | 1½"-80-NG-204 | XV-20003A | Pink highlight — burner main-gas vent valve assembly (1½" XV, FO orifice, vent gooseneck) missing; install (vent piping by MPLX, Note 2). | I&E | CRITICAL
02015D-03 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | ¾"-80-NG-205 | XV-20006A | “Missing” (two-headed arrow, also to -02) — pilot-gas vent valve assembly (¾" XV w/ solenoid, FO orifice, gooseneck) missing; install. | I&E | CRITICAL
02016-01 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | ½"-C-7001-F2AS | — | “upsize to 1" and/or support” — upsize condensate line to 1" and/or add supports; engineering to confirm. (Eng. Question Q11) | Engineering | HIGH
02016-02 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | ½"-C-7001-F2AS | — | “Add” + drawn valve before drop to N4 — install isolation valve. | Piping | HIGH
02016-03 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | Drop to N4 (½") | — | Red fitting stack “1x½” — install union/flange pair, valve, 1"x½" swage at N4. | Piping | HIGH
02016-04 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 N3 | PI-2001 | “Install” — install pressure indicator. | I&E | HIGH
02016-05 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | 3" drop to N1 | — | “3" Add” + drawn valve — install 3" valve on vent header drop. | Piping | HIGH
02016-06 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 right head | LG bridle | “Add” — install external level-gauge bridle: standpipe, gauge, ½" top + ½" bottom isolation valves. | I&E | HIGH
02016-07 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 | TI/TW-2001 | “Delete” + hatched cloud — remove from scope (with ¾" nozzle). | Engineering | MED
02016-08 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 | LG-2001 | Hatched cloud — delete (replaced by external bridle -06). | Engineering | MED
02016-09 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 left head | — | Hatched cloud over small capped fitting — delete. | Engineering | MED
02016-10 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 truck-out | — | Red-drawn 2" line: “Elevate, Keep within Containment, Add Truck Connection” — install elevated 2" truck-out w/ 2" valve + capped truck connection. | Piping | HIGH
02016-11 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2002 right head | LG-2002 | “Missing” + pink highlight — install level gauge (½"×½"). | I&E | HIGH
02016-12 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2002 drain | — | Red-drawn pump-out w/ “½"x2"” swage: “Elevate & Keep within Containment” — install per sketch (2" pipe, valve, cap). | Piping | HIGH
02016-13 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2002 header drops | — | Red routing clarifications (break squiggles at 1½"-PV-0002/0003-A2 × 1"-DA-0001-A2 / 1"-V-0094-A2 crossings) — verify as-built tie-in locations; update drawing. | Engineering | MED
03001-01 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Upper gauge glass | LG-3201A | “Add Isolation Valves” — install ¾" isolation valve at top connection. | Piping | HIGH
03001-02 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Upper gauge glass | LG-3201A | Same note — install ¾" isolation valve at bottom connection. | Piping | HIGH
03001-03 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | PSV mount | PSV-3200A | Red “1½"” + drawn nozzle at vessel wall — verify PSV connection nozzle size 1½" vs printed 1"x1". (Eng. Question Q12) | Engineering | HIGH
03001-04 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Glycol drain (F) | RO-3201A | Printed bore struck; red “0.1505"” — orifice bore 0.1505"; procure/verify plate. | I&E | HIGH
03001-05 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | RO-3201A flanges | — | “Bleed Rings” — install bleed ring(s) with bleed valves at orifice flanges. | Piping | HIGH
03001-06 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | PSV vent stack | SP-3200A | “Secure” — secure/support atmospheric vent stack (SIZE HOLD noted). | Piping | HIGH
03001-07 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Lower gauge glass | LG-3200A / TW-3200A | “Add Isolation Valves” — install ¾" isolation valve at upper tap. | Piping | HIGH
03001-08 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Lower gauge glass | LG-3200A | Same note — install ¾" isolation valve at lower tap (nozzle G). | Piping | HIGH
03001-09 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | MAF-3200A skirt | — | “Grout” — grout base. | Civil | HIGH
03001-10 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Nozzles E (1" liq outlet), D (1½"-RG-3001-F2) | — | Red hash ticks at vendor termination points (Note 3: piping beyond termination not provided) — complete downstream tie-ins. | Piping | HIGH
03001-11 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Nozzles C (lean glycol), H (1"-GH-3012-F2) | — | Red hash ticks at vendor termination points — complete downstream tie-ins. | Piping | HIGH
03001-12 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | 8"-GH-3004-F2 | — | Red-drawn 1" plugged valve assembly (stem, valve, flange bars, plug) — install 1" valved+plugged branch (vent/sample) on dry gas line. | Piping | HIGH
03001-13 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Liquid outlet (E) | RO-3202A | Bore struck; red “0.1505"” — orifice bore 0.1505"; procure/verify plate. | I&E | HIGH
03001-14 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | IA to LCV-3200A | — | Red-drawn IA detail: 1" plugged tee valve + “plug”, 1" end valve — install per sketch. | I&E | HIGH
03001-15 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | IA line | — | “U-bolt” — install U-bolt supports on IA supply run. | Piping | HIGH
03002-01 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Vessel relief | PSV-1240A | “Confirm” — verify set 1440 PSIG (E orifice). | Mechanical | CRITICAL
03002-02 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 8"-GH-3005-F2 | — | Red-drawn 1" valve on stub at elbow above nozzle B — install 1" high-point vent. | Piping | HIGH
03002-03 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 8"-GH-3005-F2 meter run | FE/FIT/UIT-1240A | “Missing / Need RO + FIT / Wire pulled” + pink highlight — install orifice plate + FIT-1240A; terminate pulled wire. | I&E | CRITICAL
03002-04 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Meter run | TE-1240A | “Wire” — wire temperature element. | Electrical | HIGH
03002-05 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | FV-1240A manifold | — | Red marks at two ½" bypass/vent valves — install ½" plugs/caps (or valves); confirm intent in field. | Piping | MED
03002-06 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Vessel connection | PI-1240A | “Add valve” — install ½" gauge isolation valve. | Piping | HIGH
03002-07 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Manway M1 (18" 600#) | — | “Torque” — torque manway. | Mechanical | HIGH
03002-08 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Level bridle | LSH-1240A | “Hookup (Wire or Tubing?)” — complete hookup; engineering to confirm electric vs pneumatic. (Eng. Question Q14) | I&E | HIGH
03002-09 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Gauge glass | LG-1240A | “Add Isolation valves” — install ¾" valve, upper connection. | Piping | HIGH
03002-10 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Gauge glass | LG-1240A | Same — install ¾" valve, lower connection. | Piping | HIGH
03002-11 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Vessel skirt | — | “Do we Need this platform?” — RFI to engineering on service platform. (Eng. Question Q15) | Engineering | MED
03002-12 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Base ring | — | “Grout” — grout base. | Civil | HIGH
03002-13 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 2"-DA-3004-F2 | RO-1240A | “XX” bore struck; red “0.7394"” — orifice bore 0.7394"; procure/verify plate. | I&E | HIGH
03002-14 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 2"-DA-3019-F2 | RO-1241A | Same — bore 0.7394"; procure/verify plate. | I&E | HIGH
03002-15 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 1"-V-0054-A2 | — | “1" Add valve (CSO)” — install 1" CSO valve on PSV-3001 vent to catch tank. | Piping | CRITICAL
03002-16 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Below PSV-3001 | — | “Add ½" bleed valve (CSO)” — install at 1" CSO isolation (SIZE HOLD noted). | Piping | HIGH
03002-17 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Outlet gas GC | AE/AT/AI-1240A | Red cloud over analyzer package + arc to 16" corner — complete GC package hookup (with -18). | I&E | HIGH
03002-18 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 16"-GH-3006-F2AS | ¾" Note-6 tap | “Missing Tap + Tubing” — install analyzer probe tap (GENIE probe) + sample tubing to GC. | I&E | HIGH
03002-19 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 16" riser / 2"-DA-3003-F2-1.5"H-ET | — | “U/G” breaks + red trace to PCV-3001 — record underground transition; verify slop-header tie-in. | Engineering | MED
03003-01 | HAY-PID-03003 | F | Glycol Region (55 MMSCFD Dehy Train-I) | FA-4000A ¾" conn. | TW/TI-4002 | “Missing” + pink highlight — install thermowell + temperature indicator. | I&E | HIGH
03003-02 | HAY-PID-03003 | F | Glycol Region (55 MMSCFD Dehy Train-I) | EBC-4001A stack, nozzle L | — | “plug” — install 1" plug in BTEX vapour glow plug connection. | Piping | HIGH
03003-03 | HAY-PID-03003 | F | Glycol Region (55 MMSCFD Dehy Train-I) | BBC-4000A reboiler | LG-4000 | “Add Isolation Valves” — install both 1"x½" gauge isolation valves. | Piping | HIGH
03004-01 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | Flash-gas line → 1"-V-0046-A2 | 1" H5S | “Missing” + cloud — install 1" H5S check valve. | Piping | HIGH
03004-02 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | MBD-2000A upper gauge | LG-2001A | “Add Isolation valves” — install both ½" tubing-gauge isolation valves. | Piping | HIGH
03004-03 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | MBD-2000A lower gauge | LG-2000 | “Add Isolation Valves” — install both isolation valves. | Piping | HIGH
03004-04 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1"A00-PSV-02 | PSV-1200 | “Add valve. (CSO)” “1"” — install 1" CSO valve on charcoal-filter PSV discharge (set 125 psig). | Piping | CRITICAL
03004-05 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1"A00-PSV-04 | PSV-1300 | “Add Valve (CSO)” “1"” — install 1" CSO valve on sock-filter PSV discharge. | Piping | CRITICAL
03004-06 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1½" A00-GR-04 | 1½" W2ZU | “valve in wrong spot” / “Has to move” — relocate valve from MAJ-1200A outlet nozzle to marked position on vertical branch. | Piping | HIGH
03004-07 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1"A00-PSV-06 | PSV-1400 | “Add valve (CSO)” “1"” — install 1" CSO valve on PSV-1400 discharge. | Piping | CRITICAL
03004-08 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1½"-RG-3001-F2 | — | “1½" Add Valve” — install 1½" isolation valve at Cimarron/MPLX scope break (rich glycol). | Piping | HIGH
03004-09 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1½"-LG-3001-F2 | — | “1½" Add Valve” — install 1½" isolation valve at scope break (lean glycol). | Piping | HIGH
04001-01 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | TK-41001 | LIT/LSH-4001 | “Wire” — wire level transmitter + switch. | Electrical | HIGH
04001-02 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | TK-41002 | LIT/LSH-4002 | “Wire” — wire. | Electrical | HIGH
04001-03 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | TK-41003 | LIT/LSH-4003 | “Wire” — wire. | Electrical | HIGH
04001-04 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | TK-41004 | LIT/LSH-4004 | “Wire” — wire. | Electrical | HIGH
04001-05 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | PVRV risers, C3 (×4) | Enardo ES-660-HF | “6X4” ×4 — install 6"x4" transition/reducer at each tank's PVRV riser. | Piping | HIGH
04001-06 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Tank bottoms (×4) | — | Red-drawn 1" valve at each tank near manway — install four 1" drain/water-draw valves. | Piping | HIGH
04001-07 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | C4 nozzles (×4) | — | Red triangle at each 4" side nozzle — verify blinded; install 4" blind flanges if open. | Piping | HIGH
04001-08 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 2"-DA-2101-A2-1.5"H-ET | — | Red-drawn new 2" HT drain line + 2" valve + capped riser at containment (P&ID ref blank) — install; engineering to assign tie-in/sheet ref. | Piping | HIGH
04001-09 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 2"-DA-2[6]81-A2-1.5"H-ET [digits unclear] | — | Second red-drawn 2" HT drain line + 2" valve, tie-in “HAY-P&ID 02013” — install; verify line number with engineering. | Piping | HIGH
04001-10 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Drain headers | — | Red tie-in routing arrows into 2"-DA-3003-A2 / 4"-DA-3023-A2 / 2"-DA-2051-A2 junctions — verify as-built tie-in points; update drawing. | Engineering | MED
04001-11 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Containment, south of TK-41002 | — | “Remove wood” — remove dunnage from containment. | Operations | MED
04001-12 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 4" transfer line | ESD-4001, ZSC/ZSO-4001, SV-4001 | “Wire” — wire ESD valve solenoid + position switches. | I&E | CRITICAL
04001-13 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | All four tanks | — | “Ground All Tanks” — ground/bond TK-41001–41004. | Electrical | CRITICAL
04001-14 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Grounding station | — | “Missing” — supply & install grounding station assembly. | Electrical | CRITICAL
04001-15 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 4"-DA-4010-A2-1"H-ET | — | “Install Enviro Box” — install environmental containment box at 4" valve/spec-blind station. | Piping | MED
07001-01 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 wet receiver | PSV-7005 | “Remove” + cloud + X — remove PSV-7005 manifold (set 155 psig) and adjoining PI-7004/½" valve. Engineering to confirm relief philosophy change. (Eng. Question Q16) | Engineering | CRITICAL
07001-02 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 top, 6" nozzle | — | “VENT” + drawn gooseneck along 1½"-IA-7036-L2 — install atmospheric vent in lieu of removed PSV. | Piping | CRITICAL
07001-03 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | ½"-IA-7040-L2 | — | Red X-hatch — delete/remove line + ½" SS tube run below VS-70004. | Piping | HIGH
07001-04 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 bottom drain | Timer drain | Red “1"” + magenta — install/upsize drain train to 1". | Piping | HIGH
07001-05 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 dry receiver | PSV-7003 | “Remove” + cloud + X — remove PSV assembly (set 155 psig). (Eng. Question Q16) | Engineering | CRITICAL
07001-06 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 top nozzle | — | “Vent” + “← PI” — install gooseneck vent + pressure gauge at top (1½"-IA-7032-L2). | Piping | HIGH
07001-07 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 shell | PI-7001 | Red cloud — relocate PI-7001 to top nozzle (with -06). | I&E | HIGH
07001-08 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 bottom drain | Timer drain | Red “1"” — upsize drain train to 1". | Piping | HIGH
07001-09 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 dry receiver | PSV-7001 | “Remove” + cloud + X — remove PSV assembly. (Eng. Question Q16) | Engineering | CRITICAL
07001-10 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 top nozzle | — | “Vent” + “PI” — install vent + PI (1½"-IA-7035-L2). | Piping | HIGH
07001-11 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 shell | PI-7002 | Red cloud — relocate to top (with -10). | I&E | HIGH
07001-12 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 bottom drain | Timer drain | Red “1"” — upsize drain train to 1". | Piping | HIGH
07001-13 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 / VS-70002 | Spare nozzles | “Missing plugs” — install NPT plugs in open spare nozzles. | Piping | CRITICAL
07001-14 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | 3"-IA-7006-L2 | PSV-7002 | “Missing” + large cloud — install COMPLETE relief station: PSV-7002 (1"x2", set 121 psig), 2" CSO block, 2"x1" reducer, ½" bleed, vent pipe. | Mechanical | CRITICAL
07001-15 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | 3"-IA-7006/7007-L2 | PCV-7001/-7002 | “Missing” — install four missing ½" valves at regulator manifold (set 110 psig). | Piping | HIGH
07001-16 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | 3"-IA-7006-L2 | — | “3" U-bolt” — install at air distribution flag. | Piping | HIGH
07001-17 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | Vessels + building | — | “Ground 3 Vessels + Building” — install grounding. | Electrical | HIGH
07001-18 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | ½" SS tube runs | — | “Missing ½" Tubing” + magenta — install tubing: skid boundary to timer drains, below VS-70004, and to TK-70001 hookup. | I&E | HIGH
07001-19 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | TK-70001 | Hose connection | Red cloud + strikes over “HOSE CONNECTION”/2" valve/2"-IA-7042-L2 — remove hose connection; update drawing. | Piping | HIGH
07001-20 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | TK-70001 | LG-7001 | “Missing” + magenta — install level gauge + two 1" isolation valves. | I&E | HIGH
07001-21 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | TK-70001 discharge | — | “Elevate & Keep Within Containment” “2"” — install elevated 2" line w/ valve, end hook inside containment. | Piping | HIGH
07001-22 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | TK-70001 outlet | — | Red “1X2” + drawn expander at containment boundary — install 1"x2" swage. | Piping | HIGH
07002-01 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 4"-GH-3007-F2 | — | “Add Support @ Double 90°” — install pipe support at vertical double-elbow drop (near PI/PCV-7101/7102). | Piping | HIGH
07002-02 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Methanol pumps title block | P-500A–D | Red cloud + “✱✱” — all four methanol pumps flagged; see Q7 (meaning of asterisks to be confirmed). | Engineering | MED
07002-03 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Pump discharge | P-500A | Red “✱” at discharge assembly — pump flagged for attention (Q7). | Engineering | MED
07002-04 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Pump discharge | P-500B | Red “✱” — flagged (Q7). | Engineering | MED
07002-05 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Pump discharge | P-500C | Red “✱” — flagged (Q7). | Engineering | MED
07002-06 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Pump discharge | P-500D | Red “✱” — flagged (Q7). | Engineering | MED
07002-07 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Skid connection E | 1"-PL-7002-A2 | Cloud: “Connect, IA Currently Hooked up Here” — instrument air is wrongly connected to the methanol inlet port; remove IA, connect methanol supply. Cross-connection hazard. | Piping | CRITICAL
07002-08 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Skid conn. E → SG-7 | — | “Connect + support OVHD 1" IA” — run and support 1" overhead instrument-air line to the skid (correct IA landing). | Piping | CRITICAL
07002-09 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Supply gas to instrumentation | PCV-501, SG-1…SG-6 | Red “✱✱” at header — cross-reference flag (with -02/-08); confirm intent. | Engineering | MED
07002-10 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | V-100 overhead | PCV-100A, PI-101A | Cloud + “Missing” — install instrument-gas regulator set: PCV-100A, PI-101A (0-150#), ¼" valve, tubing, TO SG-7 takeoff. | I&E | HIGH
07002-11 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Above LCV-100 | — | Red “¼"” + drawn valve — install ¼" valve upstream of LCV-100 (size ¼" vs ¾" to be verified). | Piping | HIGH
07002-12 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Below LCV-100 | — | Red “¼"” + drawn valve above 1" DSS spec break — install ¼" bleed. | Piping | HIGH
07002-13 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | D/s LCV-200 | — | Red “¼"” + drawn valve at 2" DSS break — install ¼" valve. | Piping | HIGH
07002-14 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | D/s LCV-300 | — | Red “¾"” + drawn valve at 2" DSS break — install ¾" valve (size to be verified). | Piping | HIGH
07002-15 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | V-300 overhead 2"-PG-300-03 | Methanol inj. pt | Cloud: “not connected inside skid.” — complete ¼" methanol-injection tie-in from pump 4. | Piping | HIGH
07002-16 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 3"-PG-104-A (E-400A N4) | — | Red highlighter trace, no text — segment flagged; verify installation/routing. | Piping | MED
07002-17 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 3"-PG-104-B (E-400B N4) | — | Red highlighter trace — verify installation/routing. | Piping | MED
07003-01 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | PSV tailpipe | PSV-7101 | “Missing” + pink highlight — install PSV vent tailpipe TO ATM (SIZE HOLD — engineering to release). | Piping | CRITICAL
07003-02 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Relief | PSV-7101 | “Confirm” — verify set 275 PSIG (fire, 1D2). | Mechanical | CRITICAL
07003-03 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | 2" PSV inlet (N9/N10) | — | “Add support” — support 2" inlet line. | Piping | HIGH
07003-04 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | 4"-GH-7001-A2 | — | “Add Support (2)” — two supports upstream of N1. | Piping | HIGH
07003-05 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | DP installation | PDI-7101 | Cloud: “By Valley.” / “Missing” — install PDI-7101 assembly (manifold, ½" valves, tubing, 2"x½" taps); vendor “Valley” scope. | Vendor | HIGH
07003-06 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Gauge standpipe (N5) | — | Red-drawn vent valve at top — install. | Piping | HIGH
07003-07 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Stub below N6 | — | Red-drawn valve + plug — install drain valve + plug above 2"-LH-7002-A2-1.5"H-ET. | Piping | HIGH
07003-08 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Nozzle N8 stub | — | Red valve symbol (~¾", partially legible) at KMTD/MPLX boundary — install valve; verify size. | Piping | HIGH
07003-09 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Stub below N7 | — | Red-drawn valve + plug next to RO-7102 — install drain valve + plug. | Piping | HIGH
07003-10 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | 2"-LH-7002-A2-1.5"H-ET | RO-7101 | “XX” struck; red “0.1031"” — orifice bore 0.1031"; procure/verify plate. | I&E | HIGH
07003-11 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | N4 outlet | RO-7102 | Same — bore 0.1031"; procure/verify plate. | I&E | HIGH
07003-12 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Meter run | FE/FIT/MVT-7101, AE/AT-7101 | “wire” — wire meter-run instrumentation (heated enclosure). | Electrical | HIGH
07003-13 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | F-71001 base | — | “Install Platform” — access platform. | Structural | MED
07004-01 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71001 bottom outlet | 1" valve | “Remove” + X — remove 1" valve (into 2" drain manifold). | Piping | HIGH
07004-02 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71002 bottom outlet | 1" valve | “Remove” + X — remove 1" valve (to 2"-DR-7002-F2AS). | Piping | HIGH
07004-03 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 1"-G-0002-F2AS motive gas | — | “1" Add” + drawn valve at battery limit — install 1" valve. | Piping | HIGH
07004-04 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | IA at V-71002 regulators | PCV-71007/71008 | “Add 1" Valve” — install 1" IA isolation valve. | Piping | HIGH
07004-05 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 1" PRO GAS line | — | “1" Add” + drawn valve at PRO GAS ¦ MPLX boundary — install 1" valve. | Piping | HIGH
07004-06 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2" drain from V-102 (HAY-PID-02105) | — | “Add 2"” + drawn valve at A2AS¦F2AS spec break — install 2" valve. | Piping | HIGH
07004-07 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2"-DR-7002-F2AS | — | “2" / Add” + drawn valve + red routing to drain header — install 2" valve; complete routing. | Piping | HIGH
07004-08 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2"-DR-7001-F2AS | 2" check valve | “Installed Backwards” — check valve at F2¦F2AS break is reversed; reinstall in correct flow direction. | Piping | CRITICAL
07004-09 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2" drain nr. V-71003 inlet | — | “Add support” — install 2" pipe support at MPLX¦PRO GAS boundary. | Piping | HIGH
07004-10 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71003 sensing line | PC/PV-71003C | Red-drawn valve + “¼"” — install ¼" valve in sensing line. | I&E | HIGH
07004-11 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | LG-71003 gauge drain | — | Red tick + triangle at 1"x¾" tap — install ¾" bull plug / verify drain valve. | Piping | HIGH
07004-12 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | LG-71004 gauge drain | — | Red marks below lower gauge valve — install ¾" drain valve + plug. | Piping | HIGH
07004-13 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71003/71004 outfall | Open drain | Cloud + “← Connect Here” — tie open drain into header at marked point (near 2"-DR-7004-F2AS). | Piping | HIGH
07004-14 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | IA regulator station | PCV-71007/71008 | “support @ P.R.” — install support at pressure-reducing station. | Piping | HIGH
07004-15 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | ESD valve group | SV/ESD-71004, ZSO/ZSC-71004 | “Secure 1" IA pipe + Wire + Tubing” — secure IA pipe; complete wiring & tubing at ESD group. | I&E | CRITICAL
07004-16 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2"-DR-7003-F2AS | — | “U/G” + arc upstream of outlet-header flag — record underground routing (mate of 01001-38). | Engineering | LOW
07005-01 | HAY-PID-07005 | C | Methanol Tank TK-71001 | TK-71001 bottom | — | “Ground” — install tank grounding/bonding (flammable service). | Electrical | CRITICAL
07005-02 | HAY-PID-07005 | C | Methanol Tank TK-71001 | 1"-PL-7001-A2 | — | “support” — add pipe support(s) at mid-span of long 1" methanol run. | Piping | HIGH
07005-03 | HAY-PID-07005 | C | Methanol Tank TK-71001 | 1"-PL-7001-A2 flag | — | Cloud: “Connect to JT Skid” — tie methanol line in at JT skid (companion of 07002-07). | Piping | CRITICAL
07006-01 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7010-A2, d/s PCV-7003 | PSV-7006 | “Missing” + pink highlight — install PSV-7006 (PCV-failure case, SIZE HOLD) + vent to ATM. | Mechanical | CRITICAL
07006-02 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7602-A2 | Gen I branch | “U/G” — record underground takeoff (Note 3). | Engineering | LOW
07006-03 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7602-A2 | Gen I strainer | “Add Valve” — install 3" valve at Y-strainer assembly. | Piping | HIGH
07006-04 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7601-A2 | Main header | “U/G” — record underground segment. | Engineering | LOW
07006-05 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7603-A2 | Gen II branch | “U/G” — record underground takeoff. | Engineering | LOW
07006-06 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7603-A2 | Gen II strainer | “Add valve” — install 3" valve at Y-strainer. | Piping | HIGH
07006-07 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7604-A2 | Gen III branch | “U/G” — record underground takeoff. | Engineering | LOW
07006-08 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7604-A2 | Gen III strainer | “Add Valve” — install 3" valve at Y-strainer. | Piping | HIGH
08001-01 | HAY-PID-08001 | E | Amine Makeup Tank TK-81003 / P-81002 | 2"-LA-8018-A2-1.5"H-ET | P-81002 discharge | “support” — install pipe support on 2" heat-traced discharge line. | Piping | HIGH
08002-01 | HAY-PID-08002 | E | TEG Glycol Makeup Tank TK-81005 / P-81005 | 2"-LG-3003-A2 | P-81005 discharge | “support” — install 2" pipe support. | Piping | HIGH
08003-01 | HAY-PID-08003 | E | Chemetherm Makeup Tank TK-81007 / P-81007 | 2"-O-8207-A2 | P-81007 discharge | “support” — install 2" pipe support. | Piping | HIGH
08004-01 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | 2"-W-8303-A2AS | TK-81010 fill line | “Delete” + large hatched cloud — remove/do-not-install entire truck-unload fill line incl. 2" check, 2" ball valve, truck connection, 2"x3" roof fill. | Piping | HIGH
08004-02 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | TK-81010 shell | LG | “Missing” + red-drawn gauge column — install external level gauge with 1" top & bottom isolation valves. | I&E | HIGH
08004-03 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | TK-81010 bottom outlet | 3" assembly | “Delete” + cloud — remove existing 3" bottom outlet valve assembly. | Piping | HIGH
08004-04 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | TK-81010 new manifold | — | Red-drawn replacement: 2" header off bottom outlet w/ 2" break, 2" valve, hose/truck-fill stub, LG tie-in (1" valve), and new 1" suction run to P-81010 — install per sketch; verify fitting types in field. | Piping | HIGH
08004-05 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | 2"-W-8304-A2AS-1.5"H-ET | P-81010 suction | “Delete” + cloud — remove/do-not-install old heat-traced suction line (superseded by -04). | Piping | HIGH
08005-01 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | P-81011 air supply | — | “Tubing” — run air-supply tubing from 2" valve (PCV-8401 station) to pump air inlet. | I&E | HIGH
08005-02 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | 2"-AFO-8402-APG-1.5"H-ET | 2" check valve | “Missing” + red oval — install 2" check valve downstream of discharge flex. | Piping | HIGH
08005-03 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | 2"-AFO-8402-APG-1.5"H-ET | — | “support” — install pipe support mid-run (heat-traced). | Piping | HIGH
08005-04 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | End of discharge run | — | Red-drawn valve + “2"” (+ “inst…” partially legible) — install 2" isolation valve upstream of anti-foam distribution split. | Piping | HIGH
08005-05 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | Distribution split → P-1A/B | 2" ball valve | “Missing.” + cloud — install 2" ball valve on through-run to HAY-PID-02007. | Piping | HIGH
08005-06 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | Distribution area | — | “Need to Correct Iso To Match P&ID” — revise piping isometric to match P&ID. | Engineering | LOW

## Piping
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
01001-25 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0003-F2AS-1½"H-ET | LV-1001 bypass | “Missing” (×2, pink highlight) — 4" cone strainer and 4" FD (“SIZE HOLD”) on NC bypass not installed. Install; engineering to release size hold. | Piping | CRITICAL
01001-26 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0006-F2AS-1½"H-ET | LV-1002 bypass | “Missing” (×2) — same missing 4" cone strainer + FD (SIZE HOLD) at X-12001 letdown bypass. | Piping | CRITICAL
01003-16 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0009-F2AS area | Bridle drain | “Missing 3" blind + ½" valve” — install 3" blind flange (w/ gasket & bolting) and ½" valve at bridle drain below lower nozzle. | Piping | CRITICAL
02002-02 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | 2"-V-0033-A2 | PSV vent | “Missing” + pink highlight — install 2" PSV vent tailpipe to ATM. | Piping | CRITICAL
02003-07 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | 1"-C-0008-F2AS-SR | RO V-1 | “Missing” + pink highlight over printed “CHOKE NIPPLE / 3/8" BORE” — install 1" choke nipple, 3/8" bore, on condensate to flash tank. | Piping | CRITICAL
02005-10 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 1"-V-0071-A1 | PSV F-2 tail | “Doesn't Exist.” + X on printed 1" CSO valve — valve shown on drawing is not in field. | Piping | CRITICAL
02005-11 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 1"-V-0071-A1 | — | “Needs to Be Added Inside Skid limits.” — install the missing 1" CSO valve + tailpipe work inside skid. | Piping | CRITICAL
02012-07 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 24"-LA-0029-A2-1.5"H | — | “1"⌀ — Needs plug” — plug open 1" stub next to TE/TW E-2E. | Piping | CRITICAL
02013-09 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 14" vent header, NOTE 7 | — | “14" Add” + drawn valve + pink highlight — install 14" 150# valve d/s of XV-301. | Piping | CRITICAL
02013-11 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-401 overhead 3" line | — | “Add / 3"” + drawn valve d/s of XV-401 — install 3" 150# valve. | Piping | CRITICAL
02014-09 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | TK-1200A east head | — | “plug” — plug open 1½" connection. | Piping | CRITICAL
02015D-01 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | ¼"-GH-2001-A2 branch | — | “Missing (see 2015C)” + pink highlight — install fuel-gas blanket branch off 3"-GH-7008-A2 (pairs with 02015C-01/-02). | Piping | CRITICAL
02115-11 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 14"-VF-0023-A2, NOTE 7 | — | “14" Add” + drawn valve d/s of XV-302 — install 14" 150# valve. | Piping | CRITICAL
02115-13 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-402 overhead → 3"-VF-0003-A2 | — | “3" Add” + drawn valve d/s of XV-402 — install 3" 150# valve. | Piping | CRITICAL
03002-15 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 1"-V-0054-A2 | — | “1" Add valve (CSO)” — install 1" CSO valve on PSV-3001 vent to catch tank. | Piping | CRITICAL
03004-04 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1"A00-PSV-02 | PSV-1200 | “Add valve. (CSO)” “1"” — install 1" CSO valve on charcoal-filter PSV discharge (set 125 psig). | Piping | CRITICAL
03004-05 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1"A00-PSV-04 | PSV-1300 | “Add Valve (CSO)” “1"” — install 1" CSO valve on sock-filter PSV discharge. | Piping | CRITICAL
03004-07 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1"A00-PSV-06 | PSV-1400 | “Add valve (CSO)” “1"” — install 1" CSO valve on PSV-1400 discharge. | Piping | CRITICAL
07001-02 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 top, 6" nozzle | — | “VENT” + drawn gooseneck along 1½"-IA-7036-L2 — install atmospheric vent in lieu of removed PSV. | Piping | CRITICAL
07001-13 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 / VS-70002 | Spare nozzles | “Missing plugs” — install NPT plugs in open spare nozzles. | Piping | CRITICAL
07002-07 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Skid connection E | 1"-PL-7002-A2 | Cloud: “Connect, IA Currently Hooked up Here” — instrument air is wrongly connected to the methanol inlet port; remove IA, connect methanol supply. Cross-connection hazard. | Piping | CRITICAL
07002-08 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Skid conn. E → SG-7 | — | “Connect + support OVHD 1" IA” — run and support 1" overhead instrument-air line to the skid (correct IA landing). | Piping | CRITICAL
07003-01 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | PSV tailpipe | PSV-7101 | “Missing” + pink highlight — install PSV vent tailpipe TO ATM (SIZE HOLD — engineering to release). | Piping | CRITICAL
07004-08 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2"-DR-7001-F2AS | 2" check valve | “Installed Backwards” — check valve at F2¦F2AS break is reversed; reinstall in correct flow direction. | Piping | CRITICAL
07005-03 | HAY-PID-07005 | C | Methanol Tank TK-71001 | 1"-PL-7001-A2 flag | — | Cloud: “Connect to JT Skid” — tie methanol line in at JT skid (companion of 07002-07). | Piping | CRITICAL
01001-01 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 2"-IA-7001-L2 | PCV-1001/-1002 | “Install (Inlet/outlet)” — install the two 1" IA take-off valves/drops feeding PCV-1001 & PCV-1002. | Piping | HIGH
01001-07 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | — | Red-drawn 1" valve w/ plug teed off outlet header at the blind — install. | Piping | HIGH
01001-12 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Inlet PSV vent | — | Red-drawn ½" valve w/ cap labeled “½"” on vent tailpipe below inlet PSV — install. | Piping | HIGH
01001-13 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | — | Red-drawn small-bore valve + cap on stub near 16"x10" control valve cloud — install. | Piping | HIGH
01001-16 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0003-F2AS | — | Red-drawn valve + blind flange on stub at elbow — install. | Piping | HIGH
01001-17 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0006-F2AS | — | Red-drawn vertical valve + cap teed up off line — install. | Piping | HIGH
01001-23 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0002-F2AS-1½"H-ET | X-11001 | Red-drawn drain valve + plug on stub — install. | Piping | HIGH
01001-24 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0005-F2AS-1½"H-ET | X-12001 | Red-drawn drain valve + plug on stub — install. | Piping | HIGH
01001-30 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0004-F2AS-1½"H-ET | — | “Install pipe shoes (3)” — install three pipe shoes. | Piping | HIGH
01001-32 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | IA header drops | SC#1 / SC#2 | “Add valves (2) – SC#1 + SC#2” — add one IA isolation valve per slug catcher. | Piping | HIGH
01001-35 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | FV-1001 cloud | FV/FY-1001 | “Add” — red-drawn valves: 2" (×2) + ½" (×1) — install. | Piping | HIGH
01003-01 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 10"-GH-0021-F2AS | V-22001 inlet | “Missing U-bolt (2)” — install two 10" U-bolts at inlet ESD station. | Piping | HIGH
01003-02 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 10"-GH-0021-F2AS | — | “Secure 2 U-bolt / Missing 1 U-bolt” — secure two existing U-bolts, install one missing. | Piping | HIGH
01003-04 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-GH-0022-F2AS | — | “Add Gate Valve” — install 2" gate valve in bypass leg of inlet station. | Piping | HIGH
01003-07 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-GH-0027-F2AS / 10"-GH-0026-F2AS | — | Pink/red triangle on 1" vent valve at junction (to Coalescing Filter) — verify/install 1" valve. | Piping | HIGH
01003-15 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0010-F2AS boot drain | — | Red-drawn ½" valve + plug teed off 2" boot-drain stub — install. | Piping | HIGH
01003-17 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0009-F2AS | — | “Shim pipe shoe” — shim shoe downstream of V-22001 outlet valve. | Piping | HIGH
01003-18 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0009-F2AS | ESD-1004 | “Missing pipe shoe + shim” — install shoe + shim at FC letdown station. | Piping | HIGH
01003-19 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | Drain leg | — | “lift pipe & put shoe on beam” (1) — reset shoe onto beam. | Piping | HIGH
01003-20 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0010-F2AS | 2" FC (SIZE HOLD) | “lift pipe & put shoe on beam” (2) — reset shoe at letdown station. | Piping | HIGH
02001-07 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-C-0201-F2AS-1.5"H-ET | LCV-1100B | “Shoes” — install two pipe shoes on 2" condensate lines at station. | Piping | HIGH
02001-10 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | LCV-1100A station | — | “shoe” — install one pipe shoe. | Piping | HIGH
02001-13 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Inlet riser u/s N1 | — | Red “½"” + arrowhead at coupling — install ½" valve/plug at open coupling. | Piping | HIGH
02002-03 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | Same tailpipe | — | “Add Brace” — brace/support the vent tailpipe. | Piping | HIGH
02002-05 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | 6"-LA-0025-F2 | — | “Secure U-bolt” — secure U-bolt on lean amine line near N3. | Piping | HIGH
02002-08 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | Lower head, near N9 | — | “Remove” + X — remove 2" capped valve/stub. | Piping | HIGH
02003-02 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | PSV V-1 tailpipe | — | “Add Brace” — brace 2" atmospheric vent riser. | Piping | HIGH
02004-01 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | 8"-RA-0010-F2AS-SR | — | Red-drawn ½" valve + cap labeled “½"” on top of rich amine run — install high-point vent. | Piping | HIGH
02004-03 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | PCV V-2B station | u/s bleed | Red “1"” + cap mark — change upstream bleed valve to 1", cap outlet. | Piping | HIGH
02004-04 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | PCV V-2B station | d/s bleed | Printed ¾" struck, “1"” + cap — change downstream bleed to 1", cap outlet. | Piping | HIGH
02004-06 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LG V-2A bridle, N8 | 2" GVTONT CSO | Red “CB10” — change upper bridle valve spec GVTONT → CB10 (retain CSO). | Piping | HIGH
02004-07 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LG V-2A bridle, N9 | 2" GVTONT CSO | Red “CB10” — change lower bridle valve to CB10. | Piping | HIGH
02004-10 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | 1"-DR-0003-A2AS | — | “Remove By MPLX” + X — remove flanged drain valve adjacent saddle. | Piping | HIGH
02005-01 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-V-0060-A2AS | Skid edge | “Add 2" valve / (CSO)” — install 2" CSO valve at skid-edge vent to drain system. | Piping | HIGH
02005-04 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | Skid #1 limit (west) | — | Red-drawn 2" valve w/ X at skid boundary above rich-amine entry — pictorial for 02005-05; install with it. | Piping | HIGH
02005-05 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6"-RA-0012-A2-1.5"H-SR | — | “Add 2" check + Block” — install 2" check valve + 2" block valve at scope break (flush/aux connection). | Piping | HIGH
02005-07 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 meter run | — | Red-drawn ¾" valve + plug below FE F-1 — install vent/bleed. | Piping | HIGH
02005-08 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6"-RA-0013-A2-1.5"H-SR | — | Red-drawn ¾" valve + plug near F-1 outlet riser — install drain/vent. | Piping | HIGH
02005-12 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6" outlet header | — | Red-drawn valve + plug (size unmarked, ~¾") on header toward L/R exchanger — install low-point drain. | Piping | HIGH
02006-02 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 6" crossover branch | — | Red-drawn valve + plug (no size) upstream of 6" block valve — install vent/drain bleed. | Piping | HIGH
02007-01 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0018-A1-1.5"H | P-1A discharge | Red “½"” + drawn valve between check and block — install ½" valve (vent/gauge). | Piping | HIGH
02007-02 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0019-A1-1.5"H | P-1B discharge | Red “½"” + drawn valve — install ½" valve. | Piping | HIGH
02007-04 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 1"-V-0076-A1 branch | ½" CB203 | “plug” — install ½" plug on open connection below valve near PSV F-4. | Piping | HIGH
02007-07 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 2"-AFD-8402-APG-1.5"H-ET | — | “Remove 2x4 & Adjust support” — remove temporary lumber, install permanent support. | Piping | HIGH
02008-01 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-AFD-8406-APG-1.5"H-ET | — | “Add shoes (4)” — install four pipe shoes on antifoam line at skid-edge run. | Piping | HIGH
02008-04 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-RF-0035-A2-1.5"H-ET-SR | LV T-2 | Red “¾” + drawn valve below line — install ¾" drain/bleed between block and check. | Piping | HIGH
02008-05 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-RF-0035-A2-1.5"H-ET-SR | Skid limit | Red “2" / Add” + drawn gate valve — install 2" block valve at Skid #1 limit crossing. | Piping | HIGH
02009-02 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 10"-LA-0017-A2-1.5"H | — | Red “1"” ×3 + drawn valves — install two 1" high-point vents and one 1" drain on lean amine to reboiler. | Piping | HIGH
02011-01 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 3"-V-0073-A2 | — | Red “3" / Add” + drawn gate valve — install 3" block valve before the drain-system flag. | Piping | HIGH
02011-12 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-G2 | 6" CV90 | “Valve Handle” — install missing handwheel at P-3A discharge block. | Piping | HIGH
02011-13 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0024-G2 | 6" CV90 | “Valve Handle” — install missing handwheel at P-3B discharge block. | Piping | HIGH
02011-16 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A suction drop | 6" cone strainer | Red doodle at temporary strainer — verify installed; remove after flushing per commissioning plan. | Piping | HIGH
02011-17 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3B suction drop | 6" cone strainer | Same verification at P-3B. | Piping | HIGH
02012-01 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 level bridles | LG/LT E-2A, E-2B | Large cloud: “Change all of Them to Gate Valves” — replace all bridle isolation valves (½", ¾" CB203; 2" CB10 CSO) with gate valves; count in field before ordering. | Piping | HIGH
02012-06 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 1"-V-0094-A2 | — | “Secure” — support/secure 1" drain line. | Piping | HIGH
02012-09 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | TCV E-2 station | — | “Shim pipe shoes (3)” — shim three shoes at hot-oil control station. | Piping | HIGH
02012-10 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 shell (S4–S1) | — | Red-drawn 2" valve at shell connection — install (field addition). | Piping | HIGH
02013-01 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 2"-GH-7004-A2 | — | Red-drawn 2" valve u/s of PCV-100 — install 2" fuel gas isolation valve. | Piping | HIGH
02013-05 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 14"-AG-0033-A2AS-SR | — | Red-drawn high-point vent (valve + plug) before KOD-301 — install (likely 1"; verify size). | Piping | HIGH
02013-07 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 top | — | Red-drawn valve at PSV/inlet nozzle connection — install small-bore valve. | Piping | HIGH
02013-08 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 drain | — | Red-drawn 2" valve at drain termination d/s of flame arrestor — install. | Piping | HIGH
02014-03 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | D — system by-pass vent | — | Cloud: “Missing / Not on ISOs / SKID LIMITS” — fabricate/install 2" NPT bypass-vent piping; add to ISOs. (Eng. Question Q6) | Piping | HIGH
02014-04 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 2"-PV-2053-A2 | — | “Add 2" Valve (CSO)” — install at condenser vapor outlet near PSV-1100A. | Piping | HIGH
02014-06 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 1"-GI-7001-F2AS | — | “1" Add valve” — install 1" valve in flame-arrestor branch. | Piping | HIGH
02014-07 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 3"-PV-3001-A2 | — | “3" Add valve” — install 3" valve at skid edge. | Piping | HIGH
02014-10 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 2" NPT bypass-vent run | — | “Missing” + cloud/pink — fabricate/install segment from D vent past HZZ-1100A to BTEX outlet drop near SP-1100A. | Piping | HIGH
02014-14 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 2"-DA-2051-A2-1.5"H-ET | — | “2" Add Valve” — install 2" valve in drain to slop tank. | Piping | HIGH
02015A-04 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | 8"-HM-187-C2-1.5"H | — | “Missing PI, Requires Tap on 8"” — hot-tap/weld ½" threadolet on 8" outlet line for the PI. (with -03) | Piping | HIGH
02015B-02 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-106 → filter | SSI-30001A | Red “1"” + drawn field routing from 6" return header to filter — install 1" side-stream supply piping. | Piping | HIGH
02015B-03 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | Filter hookup | SSI-30001A | Red-drawn loop through filter inlet/outlet (1" 3000# SW nozzles) — re-route/complete filter piping per sketch. | Piping | HIGH
02015B-05 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-110 | — | Red “1"” + drawn drop — tie side-stream return into discharge header as 1" drop (branch fitting required). | Piping | HIGH
02015C-03 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzles C1, C3 | — | Red checks on both 150# RF flanges — complete/verify hookups (with -02). | Piping | HIGH
02015C-07 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 8"-HM-187-C2-1.5"H | — | Cloud + “Missing” — install 8" loop/seal (gooseneck) assembly with plug/blind at skid boundary. | Piping | HIGH
02016-02 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | ½"-C-7001-F2AS | — | “Add” + drawn valve before drop to N4 — install isolation valve. | Piping | HIGH
02016-03 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | Drop to N4 (½") | — | Red fitting stack “1x½” — install union/flange pair, valve, 1"x½" swage at N4. | Piping | HIGH
02016-05 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | 3" drop to N1 | — | “3" Add” + drawn valve — install 3" valve on vent header drop. | Piping | HIGH
02016-10 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 truck-out | — | Red-drawn 2" line: “Elevate, Keep within Containment, Add Truck Connection” — install elevated 2" truck-out w/ 2" valve + capped truck connection. | Piping | HIGH
02016-12 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2002 drain | — | Red-drawn pump-out w/ “½"x2"” swage: “Elevate & Keep within Containment” — install per sketch (2" pipe, valve, cap). | Piping | HIGH
02115-01 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 2"-GH-7005-A2 | — | Red-drawn 2" valve u/s of PCV-103 — install 2" fuel gas isolation valve. | Piping | HIGH
02115-05 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 14"-AG-0040-A2AS-SR | — | Red-drawn high-point vent (valve + plug) before KOD-302 — install (verify size). | Piping | HIGH
02115-07 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 14" inlet drop | — | Red-drawn valve at inlet connection — install (size per connection; verify). | Piping | HIGH
02115-09 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 2" drain | — | Red-drawn valve + termination at open end — install 2" valve (+ flame arrestor per KOD-301 pattern). | Piping | HIGH
02115-10 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 14"-VF-0023-A2 | — | “Install U-bolt” — install 14" U-bolt on vent header. | Piping | HIGH
02115-15 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | VCU-102 inlet area | — | “Install 1" IA Plug This Area” — locate open IA connection, install 1" plug. | Piping | HIGH
03001-01 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Upper gauge glass | LG-3201A | “Add Isolation Valves” — install ¾" isolation valve at top connection. | Piping | HIGH
03001-02 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Upper gauge glass | LG-3201A | Same note — install ¾" isolation valve at bottom connection. | Piping | HIGH
03001-05 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | RO-3201A flanges | — | “Bleed Rings” — install bleed ring(s) with bleed valves at orifice flanges. | Piping | HIGH
03001-06 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | PSV vent stack | SP-3200A | “Secure” — secure/support atmospheric vent stack (SIZE HOLD noted). | Piping | HIGH
03001-07 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Lower gauge glass | LG-3200A / TW-3200A | “Add Isolation Valves” — install ¾" isolation valve at upper tap. | Piping | HIGH
03001-08 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Lower gauge glass | LG-3200A | Same note — install ¾" isolation valve at lower tap (nozzle G). | Piping | HIGH
03001-10 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Nozzles E (1" liq outlet), D (1½"-RG-3001-F2) | — | Red hash ticks at vendor termination points (Note 3: piping beyond termination not provided) — complete downstream tie-ins. | Piping | HIGH
03001-11 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Nozzles C (lean glycol), H (1"-GH-3012-F2) | — | Red hash ticks at vendor termination points — complete downstream tie-ins. | Piping | HIGH
03001-12 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | 8"-GH-3004-F2 | — | Red-drawn 1" plugged valve assembly (stem, valve, flange bars, plug) — install 1" valved+plugged branch (vent/sample) on dry gas line. | Piping | HIGH
03001-15 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | IA line | — | “U-bolt” — install U-bolt supports on IA supply run. | Piping | HIGH
03002-02 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 8"-GH-3005-F2 | — | Red-drawn 1" valve on stub at elbow above nozzle B — install 1" high-point vent. | Piping | HIGH
03002-06 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Vessel connection | PI-1240A | “Add valve” — install ½" gauge isolation valve. | Piping | HIGH
03002-09 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Gauge glass | LG-1240A | “Add Isolation valves” — install ¾" valve, upper connection. | Piping | HIGH
03002-10 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Gauge glass | LG-1240A | Same — install ¾" valve, lower connection. | Piping | HIGH
03002-16 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Below PSV-3001 | — | “Add ½" bleed valve (CSO)” — install at 1" CSO isolation (SIZE HOLD noted). | Piping | HIGH
03003-02 | HAY-PID-03003 | F | Glycol Region (55 MMSCFD Dehy Train-I) | EBC-4001A stack, nozzle L | — | “plug” — install 1" plug in BTEX vapour glow plug connection. | Piping | HIGH
03003-03 | HAY-PID-03003 | F | Glycol Region (55 MMSCFD Dehy Train-I) | BBC-4000A reboiler | LG-4000 | “Add Isolation Valves” — install both 1"x½" gauge isolation valves. | Piping | HIGH
03004-01 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | Flash-gas line → 1"-V-0046-A2 | 1" H5S | “Missing” + cloud — install 1" H5S check valve. | Piping | HIGH
03004-02 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | MBD-2000A upper gauge | LG-2001A | “Add Isolation valves” — install both ½" tubing-gauge isolation valves. | Piping | HIGH
03004-03 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | MBD-2000A lower gauge | LG-2000 | “Add Isolation Valves” — install both isolation valves. | Piping | HIGH
03004-06 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1½" A00-GR-04 | 1½" W2ZU | “valve in wrong spot” / “Has to move” — relocate valve from MAJ-1200A outlet nozzle to marked position on vertical branch. | Piping | HIGH
03004-08 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1½"-RG-3001-F2 | — | “1½" Add Valve” — install 1½" isolation valve at Cimarron/MPLX scope break (rich glycol). | Piping | HIGH
03004-09 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1½"-LG-3001-F2 | — | “1½" Add Valve” — install 1½" isolation valve at scope break (lean glycol). | Piping | HIGH
04001-05 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | PVRV risers, C3 (×4) | Enardo ES-660-HF | “6X4” ×4 — install 6"x4" transition/reducer at each tank's PVRV riser. | Piping | HIGH
04001-06 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Tank bottoms (×4) | — | Red-drawn 1" valve at each tank near manway — install four 1" drain/water-draw valves. | Piping | HIGH
04001-07 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | C4 nozzles (×4) | — | Red triangle at each 4" side nozzle — verify blinded; install 4" blind flanges if open. | Piping | HIGH
04001-08 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 2"-DA-2101-A2-1.5"H-ET | — | Red-drawn new 2" HT drain line + 2" valve + capped riser at containment (P&ID ref blank) — install; engineering to assign tie-in/sheet ref. | Piping | HIGH
04001-09 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 2"-DA-2[6]81-A2-1.5"H-ET [digits unclear] | — | Second red-drawn 2" HT drain line + 2" valve, tie-in “HAY-P&ID 02013” — install; verify line number with engineering. | Piping | HIGH
07001-03 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | ½"-IA-7040-L2 | — | Red X-hatch — delete/remove line + ½" SS tube run below VS-70004. | Piping | HIGH
07001-04 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 bottom drain | Timer drain | Red “1"” + magenta — install/upsize drain train to 1". | Piping | HIGH
07001-06 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 top nozzle | — | “Vent” + “← PI” — install gooseneck vent + pressure gauge at top (1½"-IA-7032-L2). | Piping | HIGH
07001-08 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 bottom drain | Timer drain | Red “1"” — upsize drain train to 1". | Piping | HIGH
07001-10 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 top nozzle | — | “Vent” + “PI” — install vent + PI (1½"-IA-7035-L2). | Piping | HIGH
07001-12 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 bottom drain | Timer drain | Red “1"” — upsize drain train to 1". | Piping | HIGH
07001-15 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | 3"-IA-7006/7007-L2 | PCV-7001/-7002 | “Missing” — install four missing ½" valves at regulator manifold (set 110 psig). | Piping | HIGH
07001-16 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | 3"-IA-7006-L2 | — | “3" U-bolt” — install at air distribution flag. | Piping | HIGH
07001-19 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | TK-70001 | Hose connection | Red cloud + strikes over “HOSE CONNECTION”/2" valve/2"-IA-7042-L2 — remove hose connection; update drawing. | Piping | HIGH
07001-21 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | TK-70001 discharge | — | “Elevate & Keep Within Containment” “2"” — install elevated 2" line w/ valve, end hook inside containment. | Piping | HIGH
07001-22 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | TK-70001 outlet | — | Red “1X2” + drawn expander at containment boundary — install 1"x2" swage. | Piping | HIGH
07002-01 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 4"-GH-3007-F2 | — | “Add Support @ Double 90°” — install pipe support at vertical double-elbow drop (near PI/PCV-7101/7102). | Piping | HIGH
07002-11 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Above LCV-100 | — | Red “¼"” + drawn valve — install ¼" valve upstream of LCV-100 (size ¼" vs ¾" to be verified). | Piping | HIGH
07002-12 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Below LCV-100 | — | Red “¼"” + drawn valve above 1" DSS spec break — install ¼" bleed. | Piping | HIGH
07002-13 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | D/s LCV-200 | — | Red “¼"” + drawn valve at 2" DSS break — install ¼" valve. | Piping | HIGH
07002-14 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | D/s LCV-300 | — | Red “¾"” + drawn valve at 2" DSS break — install ¾" valve (size to be verified). | Piping | HIGH
07002-15 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | V-300 overhead 2"-PG-300-03 | Methanol inj. pt | Cloud: “not connected inside skid.” — complete ¼" methanol-injection tie-in from pump 4. | Piping | HIGH
07003-03 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | 2" PSV inlet (N9/N10) | — | “Add support” — support 2" inlet line. | Piping | HIGH
07003-04 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | 4"-GH-7001-A2 | — | “Add Support (2)” — two supports upstream of N1. | Piping | HIGH
07003-06 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Gauge standpipe (N5) | — | Red-drawn vent valve at top — install. | Piping | HIGH
07003-07 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Stub below N6 | — | Red-drawn valve + plug — install drain valve + plug above 2"-LH-7002-A2-1.5"H-ET. | Piping | HIGH
07003-08 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Nozzle N8 stub | — | Red valve symbol (~¾", partially legible) at KMTD/MPLX boundary — install valve; verify size. | Piping | HIGH
07003-09 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Stub below N7 | — | Red-drawn valve + plug next to RO-7102 — install drain valve + plug. | Piping | HIGH
07004-01 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71001 bottom outlet | 1" valve | “Remove” + X — remove 1" valve (into 2" drain manifold). | Piping | HIGH
07004-02 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71002 bottom outlet | 1" valve | “Remove” + X — remove 1" valve (to 2"-DR-7002-F2AS). | Piping | HIGH
07004-03 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 1"-G-0002-F2AS motive gas | — | “1" Add” + drawn valve at battery limit — install 1" valve. | Piping | HIGH
07004-04 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | IA at V-71002 regulators | PCV-71007/71008 | “Add 1" Valve” — install 1" IA isolation valve. | Piping | HIGH
07004-05 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 1" PRO GAS line | — | “1" Add” + drawn valve at PRO GAS ¦ MPLX boundary — install 1" valve. | Piping | HIGH
07004-06 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2" drain from V-102 (HAY-PID-02105) | — | “Add 2"” + drawn valve at A2AS¦F2AS spec break — install 2" valve. | Piping | HIGH
07004-07 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2"-DR-7002-F2AS | — | “2" / Add” + drawn valve + red routing to drain header — install 2" valve; complete routing. | Piping | HIGH
07004-09 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2" drain nr. V-71003 inlet | — | “Add support” — install 2" pipe support at MPLX¦PRO GAS boundary. | Piping | HIGH
07004-11 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | LG-71003 gauge drain | — | Red tick + triangle at 1"x¾" tap — install ¾" bull plug / verify drain valve. | Piping | HIGH
07004-12 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | LG-71004 gauge drain | — | Red marks below lower gauge valve — install ¾" drain valve + plug. | Piping | HIGH
07004-13 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71003/71004 outfall | Open drain | Cloud + “← Connect Here” — tie open drain into header at marked point (near 2"-DR-7004-F2AS). | Piping | HIGH
07004-14 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | IA regulator station | PCV-71007/71008 | “support @ P.R.” — install support at pressure-reducing station. | Piping | HIGH
07005-02 | HAY-PID-07005 | C | Methanol Tank TK-71001 | 1"-PL-7001-A2 | — | “support” — add pipe support(s) at mid-span of long 1" methanol run. | Piping | HIGH
07006-03 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7602-A2 | Gen I strainer | “Add Valve” — install 3" valve at Y-strainer assembly. | Piping | HIGH
07006-06 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7603-A2 | Gen II strainer | “Add valve” — install 3" valve at Y-strainer. | Piping | HIGH
07006-08 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7604-A2 | Gen III strainer | “Add Valve” — install 3" valve at Y-strainer. | Piping | HIGH
08001-01 | HAY-PID-08001 | E | Amine Makeup Tank TK-81003 / P-81002 | 2"-LA-8018-A2-1.5"H-ET | P-81002 discharge | “support” — install pipe support on 2" heat-traced discharge line. | Piping | HIGH
08002-01 | HAY-PID-08002 | E | TEG Glycol Makeup Tank TK-81005 / P-81005 | 2"-LG-3003-A2 | P-81005 discharge | “support” — install 2" pipe support. | Piping | HIGH
08003-01 | HAY-PID-08003 | E | Chemetherm Makeup Tank TK-81007 / P-81007 | 2"-O-8207-A2 | P-81007 discharge | “support” — install 2" pipe support. | Piping | HIGH
08004-01 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | 2"-W-8303-A2AS | TK-81010 fill line | “Delete” + large hatched cloud — remove/do-not-install entire truck-unload fill line incl. 2" check, 2" ball valve, truck connection, 2"x3" roof fill. | Piping | HIGH
08004-03 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | TK-81010 bottom outlet | 3" assembly | “Delete” + cloud — remove existing 3" bottom outlet valve assembly. | Piping | HIGH
08004-04 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | TK-81010 new manifold | — | Red-drawn replacement: 2" header off bottom outlet w/ 2" break, 2" valve, hose/truck-fill stub, LG tie-in (1" valve), and new 1" suction run to P-81010 — install per sketch; verify fitting types in field. | Piping | HIGH
08004-05 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | 2"-W-8304-A2AS-1.5"H-ET | P-81010 suction | “Delete” + cloud — remove/do-not-install old heat-traced suction line (superseded by -04). | Piping | HIGH
08005-02 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | 2"-AFO-8402-APG-1.5"H-ET | 2" check valve | “Missing” + red oval — install 2" check valve downstream of discharge flex. | Piping | HIGH
08005-03 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | 2"-AFO-8402-APG-1.5"H-ET | — | “support” — install pipe support mid-run (heat-traced). | Piping | HIGH
08005-04 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | End of discharge run | — | Red-drawn valve + “2"” (+ “inst…” partially legible) — install 2" isolation valve upstream of anti-foam distribution split. | Piping | HIGH
08005-05 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | Distribution split → P-1A/B | 2" ball valve | “Missing.” + cloud — install 2" ball valve on through-run to HAY-PID-02007. | Piping | HIGH
01001-04 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | 16" CSO valve | “Rotate Handle Due South” — reorient valve handle. | Piping | MED
01001-21 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-11001 bridle | LS-1001 | Red “2"” (twice) at bridle isolation valves — verify/upsize isolation valves to 2". | Piping | MED
01001-22 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-12001 bridle | LS-1002 | Red “2"” (twice) — same verification at X-12001 bridle. | Piping | MED
01003-10 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-21001 bridle | — | Red “3"” (twice) at bridle isolation valves — verify/upsize to 3". | Piping | MED
01003-12 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | — | Red “3"” (twice) — verify/upsize bridle isolation valves to 3". | Piping | MED
02002-07 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | 8"-G-0103-F2AS | 8" CV60N | “Rotate 90° so Valve is Horizontal” — reorient inlet valve. | Piping | MED
02005-14 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-DR-0100-A1 (east) | — | Red emphasis chevrons on printed drain flag — verify/connect continuation to HAY-PID-02006. | Piping | MED
02006-04 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 2"-DR-0100-A1 (east) | — | Red emphasis on printed flag to HAY-PID-02007 — verify continuation/tie-in. | Piping | MED
02015B-01 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-106 | — | Red tick at tee — marks tap point for 1" side-stream supply (see -02). | Piping | MED
03002-05 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | FV-1240A manifold | — | Red marks at two ½" bypass/vent valves — install ½" plugs/caps (or valves); confirm intent in field. | Piping | MED
04001-15 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 4"-DA-4010-A2-1"H-ET | — | “Install Enviro Box” — install environmental containment box at 4" valve/spec-blind station. | Piping | MED
07002-16 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 3"-PG-104-A (E-400A N4) | — | Red highlighter trace, no text — segment flagged; verify installation/routing. | Piping | MED
07002-17 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 3"-PG-104-B (E-400B N4) | — | Red highlighter trace — verify installation/routing. | Piping | MED

## Mechanical
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
01001-14 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 3"-GH-0015-A2AS | PSV-1001 | “Confirm” — verify relief set pressure 1430 PSIG (fire) against nameplate/certs. | Mechanical | CRITICAL
01001-15 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 3"-GH-0017-A2AS | PSV-1003 | “Confirm” — verify relief set pressure (X-12001) against nameplate/certs. | Mechanical | CRITICAL
01003-06 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 3"-GH-0031-A2AS vent | V-22001 PSV | “Missing” + pink highlight over ENTIRE PSV package (PSV, 3" vent to ATM, 1½"-GH-0030-F2AS inlet, ½" bleed) — supply & install complete relief assembly (set per V-22001, 1435 PSIG design). | Mechanical | CRITICAL
02001-03 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | S-1100 relief | PSV-1100 | “Missing” + pink highlight over full assembly (PSV set 1440 PSIG fire, 2" TO ATM tail, 2"x1" reducer, ½" bleed, 2" CSO block) — supply & install. | Mechanical | CRITICAL
02002-01 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | T-1 relief | PSV T-1 | “Confirm” — verify set pressure 1440 PSIG (fire) against nameplate. | Mechanical | CRITICAL
02003-01 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 relief | PSV V-1 | “Confirm” — verify set pressure 1440 PSIG (fire, 1D2 orifice) against nameplate. | Mechanical | CRITICAL
02004-02 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 relief | PSV V-2 | “Confirm” — verify set pressure 150 PSIG (6R8) against nameplate. | Mechanical | CRITICAL
02005-02 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 relief | PSV F-1 | “Confirm” — verify set 150 PSIG (fire, 1½F2). | Mechanical | CRITICAL
02009-01 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 12"-AG-0031-A2AS-1.5"H | PSV T-2 | “Confirm” — verify pilot-operated PSV set 100 PSIG. | Mechanical | CRITICAL
02010-01 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | 8"-LA-0022-A2 relief riser | PSV AC-1 | “Missing” + pink highlight — install PSV AC-1 (2"x1½", set 150 PSIG, check-valve-failure case) and relief route via 3"-V-0102-A2. | Mechanical | CRITICAL
02011-03 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | Relief | PSV P-3C | “Confirm” — verify pilot-operated PSV set 1440 PSIG (blocked flow). | Mechanical | CRITICAL
02012-03 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 shell relief | PSV E-2 | “Missing” + cloud — install 2"x1" thermal PSV, set 150 PSIG. | Mechanical | CRITICAL
02015C-04 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 1½"-PV-0003-A2 | PSV-45001A | “Confirm” — verify set 25 PSIG. | Mechanical | CRITICAL
03002-01 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Vessel relief | PSV-1240A | “Confirm” — verify set 1440 PSIG (E orifice). | Mechanical | CRITICAL
07001-14 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | 3"-IA-7006-L2 | PSV-7002 | “Missing” + large cloud — install COMPLETE relief station: PSV-7002 (1"x2", set 121 psig), 2" CSO block, 2"x1" reducer, ½" bleed, vent pipe. | Mechanical | CRITICAL
07003-02 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Relief | PSV-7101 | “Confirm” — verify set 275 PSIG (fire, 1D2). | Mechanical | CRITICAL
07006-01 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7010-A2, d/s PCV-7003 | PSV-7006 | “Missing” + pink highlight — install PSV-7006 (PCV-failure case, SIZE HOLD) + vent to ATM. | Mechanical | CRITICAL
01003-13 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 manway | MW | “Torque” — torque manway bolting to spec. | Mechanical | HIGH
02002-06 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | T-1 manway M1 (18") | — | “Torque after Inspection” — torque lower manway after internal inspection. | Mechanical | HIGH
02003-04 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 manway M1 (18") | — | “Torque” — torque manway cover. | Mechanical | HIGH
02008-02 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-W-8305-A2AS-1.5"H-ET | X-2 | “Missing” + pink highlight — install MPLX-supplied 2" static mixer X-2 (Note 1). | Mechanical | HIGH
02009-07 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | T-2 manway M2 (20") | — | “Torque After Inspection” — torque after internal inspection. | Mechanical | HIGH
02011-10 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A flanges | — | “Bolt up After Alignment” — final bolt-up of 4" 900# discharge spool and 6" 150# suction flange after alignment. | Mechanical | HIGH
02011-11 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3B flanges | — | “Bolt up After Alignment” — same at P-3B. | Mechanical | HIGH
02015A-07 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Combustion blower | — | “Shim Blow Motor & Remove straps” — shim motor, remove shipping straps. | Mechanical | HIGH
03002-07 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Manway M1 (18" 600#) | — | “Torque” — torque manway. | Mechanical | HIGH
02004-05 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 nozzle M4 (4") | — | Small red check at flange pair (KMTD/MPLX break) — field verification mark; confirm intent/torque status. | Mechanical | MED

## I&E
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
01001-10 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | SV-1001, ZSO/ZSC-1001 | “Wire + Tubing” — complete wiring and pneumatic tubing at inlet ESD valve station. | I&E | CRITICAL
01001-11 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | SV-1002, ZSO/ZSC-1002 | “Wire + Tubing” — complete wiring and tubing at outlet ESD valve station. | I&E | CRITICAL
01001-28 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Letdown loop | LY/LV-1002, LSH/LSLL-1002 | “Wire” — complete loop wiring incl. level safety switches. | I&E | CRITICAL
01001-42 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4" FC valve | ZSO/ZSC-1007 | “wire” — wire position switches on ESD blowdown valve. | I&E | CRITICAL
01003-03 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | Inlet ESD valve | SV-1004 | “Tubing” — complete pneumatic tubing at solenoid/quick-connect. | I&E | CRITICAL
01003-21 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | ESD-1004 | ZSO/ZSC-1004 | “Tubing + lower latching switch to grade (Tubing)” — run tubing; relocate latching switch to grade. | I&E | CRITICAL
02001-08 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Shutdown valve | SDV-1100, ZSO/ZSC-1100 | “Tubing” — complete pneumatic tubing. | I&E | CRITICAL
02011-14 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-F2 | FIT/FIC P-3 | “Missing” + pink highlight — install FIT P-3 dP transmitter, both impulse manifold valve sets, and tubing on common discharge meter. | I&E | CRITICAL
02013-02 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 2"-FG-2220-A2 | FE/FIT-100 | “Missing / Need RO + FIT / wire pulled” + pink highlight — install restriction orifice FE-100 and transmitter FIT-100; terminate pulled wire. | I&E | CRITICAL
02013-06 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 | PSV-301, PG-301, LSHH/LSH/LSL/LSLL-301 | “Missing wire pulled” + pink highlight — install PSV-301 (set 100 psig, vent SIZE HOLD), PG-301 + ½" MNV, full level-switch stack; terminate wiring. | I&E | CRITICAL
02013-10 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-401 | PSV-401, PG-401, LSHH…LSLL-401 | “Missing wire pulled” + pink highlight — install PSV-401 (set 15 psig), PG-401, level-switch stack; terminate wiring. | I&E | CRITICAL
02015C-01 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | ¼"-GH-2001-A2 | PCV-2001 | “Missing (¾" valve installed on Adjacent 3" FG pipe)” + pink highlight — blanket-gas regulator station (set 30 psig) not installed as drawn; field deviation exists. Install per design / reconcile. (Eng. Question Q5) | I&E | CRITICAL
02015C-02 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | To nozzle C3 | — | “¼" Tubing Missing” + pink highlight — install blanket-gas tubing across scope breaks to tank top. | I&E | CRITICAL
02015D-02 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | 1½"-80-NG-204 | XV-20003A | Pink highlight — burner main-gas vent valve assembly (1½" XV, FO orifice, vent gooseneck) missing; install (vent piping by MPLX, Note 2). | I&E | CRITICAL
02015D-03 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | ¾"-80-NG-205 | XV-20006A | “Missing” (two-headed arrow, also to -02) — pilot-gas vent valve assembly (¾" XV w/ solenoid, FO orifice, gooseneck) missing; install. | I&E | CRITICAL
02115-02 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 2"-FG-2222-A2 | FE/FIT-101 | “Missing / RO? / wire pulled” + pink highlight — install FE-101 orifice + FIT-101; terminate pulled wire. | I&E | CRITICAL
02115-06 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 | PSV-302, PG-302, LSHH…LSLL-302 | “Missing” + pink highlight — install PSV-302 (set 100 psig, vent SIZE HOLD), PG-302 + ½" MNV, level-switch stack. | I&E | CRITICAL
02115-12 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-402 | PSV-402, LSHH…LSLL-402 | “Missing” + pink highlight — install PSV-402 (set 15 psig) + level-switch stack. | I&E | CRITICAL
02115-14 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | Detonation arrestors | TE-402 / TE-403 | “wire (pulled)” — terminate TE-402/403 (TAHH @ 250°F). | I&E | CRITICAL
03002-03 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 8"-GH-3005-F2 meter run | FE/FIT/UIT-1240A | “Missing / Need RO + FIT / Wire pulled” + pink highlight — install orifice plate + FIT-1240A; terminate pulled wire. | I&E | CRITICAL
04001-12 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 4" transfer line | ESD-4001, ZSC/ZSO-4001, SV-4001 | “Wire” — wire ESD valve solenoid + position switches. | I&E | CRITICAL
07004-15 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | ESD valve group | SV/ESD-71004, ZSO/ZSC-71004 | “Secure 1" IA pipe + Wire + Tubing” — secure IA pipe; complete wiring & tubing at ESD group. | I&E | CRITICAL
01001-19 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-11001 level bridle | LIT-1001 | “4x2 / Remove” + strike on ½" valve between LIT-1001 and control override — remove valve; verify 4"x2" reducer requirement. | I&E | HIGH
01001-20 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-12001 level bridle | LIT-1002 | Same markup as 01001-19 at X-12001 — remove ½" valve; verify 4"x2" reducer. | I&E | HIGH
01001-27 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Letdown loop | LY/LV-1001 | “Wire” — complete loop wiring. | I&E | HIGH
01001-33 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 12"-GH-0010-F2AS | PT-1001A | Red cloud + “Wire” + leader re-tapping PT-1001A onto the 12" line — relocate tap, wire transmitter. | I&E | HIGH
01001-39 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Adjacent riser | PT-1001B | Red cloud + curved arrow — relocate PT-1001B tap to adjacent riser. | I&E | HIGH
01001-41 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Blowdown drain, X-12001 | — | “Wire + Tubing” — complete wiring/tubing in blowdown drain area. | I&E | HIGH
01003-08 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | LIT-1004 | Red “LT” circle + “3X2” capped-stub sketch — mount LIT-1004 on 3"x2" reducer with cap. | I&E | HIGH
01003-09 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-21001 bridle | LIT-1003 / LSH-1003 | “Remove” + strike — remove ½" valve/plug between instruments. | I&E | HIGH
01003-11 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | LIT-1004 | “Remove” + strike — remove ½" valve at V-22001 bridle. | I&E | HIGH
02001-09 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Below LC-1100A | — | “Tubing” — complete tubing on vertical 2" run/header connections. | I&E | HIGH
02002-04 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | T-1 column | PDT T-1 | “Missing” + pink highlight along full ½" SS tubing run (top to bottom tap) — install dP impulse tubing (~55 ft + fittings). | I&E | HIGH
02002-10 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | 6"-RA-0009-F2AS-SR | RO T-1 | “Confirm” — verify restriction orifice bore 1.5" per datasheet. | I&E | HIGH
02003-03 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 nozzle N3 (2") | PI V-1 | “Remove” + X — remove small gauge/bleed valve at N3 between PI isolation and vessel. | I&E | HIGH
02003A-01 | HAY-PID-02003A | E | Gas Cooler AC-4 (400 GPM Amine Plant) | Louver actuator run | TY AC-4 | “Tubing” — install pneumatic tubing from TY AC-4 to automated louver actuator. | I&E | HIGH
02005-03 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 degasser | — | “Missing ½" Tubing” + pink highlight — install ½" SS tubing run (check valve to ½"-V-0060-A1 tie-in). | I&E | HIGH
02005-06 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 inlet meter | FE F-1 | “Confirm” — verify orifice bore 2.0". | I&E | HIGH
02005-09 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-2 degasser | — | “Tighten ½" Tubing Ferrule” — tighten compression fitting. | I&E | HIGH
02006-01 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 6"-LA-0022-A1 | TI/TW E-1D | Red cloud + tag “E-1D” on unlabeled TI/TW bubble — install & tag temperature indicator with thermowell on E-1 lean amine outlet. | I&E | HIGH
02009-03 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | LG T-2A MAG bridle | — | “Missing” — install ½" CB203 vent (top) and ½" CB203 drain (bottom) on gauge bridle. | I&E | HIGH
02009-11 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Acid gas PV loop | PY T-2 / PV T-2 | “Tubing” — install instrument air tubing (I/P to valve). | I&E | HIGH
02010-03 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | AC-1 louver run | TY AC-1C | “Tubing” — install I/P-to-louver-actuator tubing. | I&E | HIGH
02010-04 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | AC-2 louver run | TY AC-2C | “Tubing” — install tubing to AC-2 louver actuator. | I&E | HIGH
02011-04 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | PSV P-3C station | — | “Missing” + pink highlight — install ½"x⅜" SS tubing run to P-3A discharge valve string. | I&E | HIGH
02011-05 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-G2 | PIT P-3A2 | Red bubble + two drawn root valves at new tap between CV90 and check — relocate PIT P-3A2 tap here; install two small-bore root valves. | I&E | HIGH
02011-08 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0024-G2 | PI/PIT P-3D | “Wire” + cloud + tap arcs — wire P-3B discharge instruments; relocate tap (mirror of 02011-05). | I&E | HIGH
02011-15 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-F2 | FE P-3 | “Confirm” — verify orifice bore 3.5" per datasheet. | I&E | HIGH
02014-01 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | Fuel gas supply (L) | — | “Tubing” — install ¼" fuel-gas supply tubing run. | I&E | HIGH
02014-02 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | Diffuser feed | DIF-001A | “Missing Tubing” + pink highlight — install tubing PY-1001A → diffuser at condenser inlet. | I&E | HIGH
02014-05 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | ½" tubing from 2"-GH-7006-A2 | PCV-2002A | Red X + pink highlight — install PCV-2002A regulator (set 100 psig) with tubing (see -11). | I&E | HIGH
02014-08 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | TK-1200A | LG-1200A | “Missing” + pink highlight — install gauge glass + 2×¾" isolation, ½" vent, ½" drain valves. | I&E | HIGH
02014-11 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | Motive gas (P) circuit | — | “Missing Tubing” — install ½" tubing riser + header to ABV-1000A and ½"-PV-2054-A2. | I&E | HIGH
02014-13 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | V-7000A vent/condensate | LS-1000A / CV-001 | “Tubing” — install tubing for reset/vent circuit to B outlet. | I&E | HIGH
02015A-03 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater outlet detail | PI-27002A | Cloud + pink: “Missing / Not on ISO's” — outlet pressure-gauge assembly (0-160 psig, ½" NPT valve, siphon) missing; shipped-loose per Note 8, MPLX installs. | I&E | HIGH
02016-04 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 N3 | PI-2001 | “Install” — install pressure indicator. | I&E | HIGH
02016-06 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 right head | LG bridle | “Add” — install external level-gauge bridle: standpipe, gauge, ½" top + ½" bottom isolation valves. | I&E | HIGH
02016-11 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2002 right head | LG-2002 | “Missing” + pink highlight — install level gauge (½"×½"). | I&E | HIGH
02115-08 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 bridle | LG-302 | “Missing” — install gauge glass + 2×1" BAV isolation valves + ½" vents. | I&E | HIGH
03001-04 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Glycol drain (F) | RO-3201A | Printed bore struck; red “0.1505"” — orifice bore 0.1505"; procure/verify plate. | I&E | HIGH
03001-13 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Liquid outlet (E) | RO-3202A | Bore struck; red “0.1505"” — orifice bore 0.1505"; procure/verify plate. | I&E | HIGH
03001-14 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | IA to LCV-3200A | — | Red-drawn IA detail: 1" plugged tee valve + “plug”, 1" end valve — install per sketch. | I&E | HIGH
03002-08 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Level bridle | LSH-1240A | “Hookup (Wire or Tubing?)” — complete hookup; engineering to confirm electric vs pneumatic. (Eng. Question Q14) | I&E | HIGH
03002-13 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 2"-DA-3004-F2 | RO-1240A | “XX” bore struck; red “0.7394"” — orifice bore 0.7394"; procure/verify plate. | I&E | HIGH
03002-14 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 2"-DA-3019-F2 | RO-1241A | Same — bore 0.7394"; procure/verify plate. | I&E | HIGH
03002-17 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Outlet gas GC | AE/AT/AI-1240A | Red cloud over analyzer package + arc to 16" corner — complete GC package hookup (with -18). | I&E | HIGH
03002-18 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 16"-GH-3006-F2AS | ¾" Note-6 tap | “Missing Tap + Tubing” — install analyzer probe tap (GENIE probe) + sample tubing to GC. | I&E | HIGH
03003-01 | HAY-PID-03003 | F | Glycol Region (55 MMSCFD Dehy Train-I) | FA-4000A ¾" conn. | TW/TI-4002 | “Missing” + pink highlight — install thermowell + temperature indicator. | I&E | HIGH
07001-07 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 shell | PI-7001 | Red cloud — relocate PI-7001 to top nozzle (with -06). | I&E | HIGH
07001-11 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 shell | PI-7002 | Red cloud — relocate to top (with -10). | I&E | HIGH
07001-18 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | ½" SS tube runs | — | “Missing ½" Tubing” + magenta — install tubing: skid boundary to timer drains, below VS-70004, and to TK-70001 hookup. | I&E | HIGH
07001-20 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | TK-70001 | LG-7001 | “Missing” + magenta — install level gauge + two 1" isolation valves. | I&E | HIGH
07002-10 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | V-100 overhead | PCV-100A, PI-101A | Cloud + “Missing” — install instrument-gas regulator set: PCV-100A, PI-101A (0-150#), ¼" valve, tubing, TO SG-7 takeoff. | I&E | HIGH
07003-10 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | 2"-LH-7002-A2-1.5"H-ET | RO-7101 | “XX” struck; red “0.1031"” — orifice bore 0.1031"; procure/verify plate. | I&E | HIGH
07003-11 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | N4 outlet | RO-7102 | Same — bore 0.1031"; procure/verify plate. | I&E | HIGH
07004-10 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71003 sensing line | PC/PV-71003C | Red-drawn valve + “¼"” — install ¼" valve in sensing line. | I&E | HIGH
08004-02 | HAY-PID-08004 | E | Water Makeup Tank TK-81009 / TK-81010 | TK-81010 shell | LG | “Missing” + red-drawn gauge column — install external level gauge with 1" top & bottom isolation valves. | I&E | HIGH
08005-01 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | P-81011 air supply | — | “Tubing” — run air-supply tubing from 2" valve (PCV-8401 station) to pump air inlet. | I&E | HIGH
02001-05 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Level controller | LC S-1100B | “Rotate Due West” — reorient controller. | I&E | MED
02001-06 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Level controller | LC S-1100A | “Rotate Due East” — reorient controller. | I&E | MED
02007-08 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | Spare-filter bridges | PDI F-4B / F-4C | Red tick marks on both PDI balloons — verify gauges installed/functional. | I&E | MED
02009-05 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Nozzle C2 gauges | PI T-2B, TI T-2B | Red range edits “0-100#” / “50-200F” — verify/replace gauges to marked ranges. | I&E | MED

## Electrical
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
02015A-02 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater outlet | TE-27002A | “Wire” — wire control thermocouple (TIC-27002A loop). | Electrical | CRITICAL
02015C-05 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzle C6 | LSL-45001A | “Wire” — wire low-level interlock (wiring by MPLX, Note 6). | Electrical | CRITICAL
04001-13 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | All four tanks | — | “Ground All Tanks” — ground/bond TK-41001–41004. | Electrical | CRITICAL
04001-14 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Grounding station | — | “Missing” — supply & install grounding station assembly. | Electrical | CRITICAL
07005-01 | HAY-PID-07005 | C | Methanol Tank TK-71001 | TK-71001 bottom | — | “Ground” — install tank grounding/bonding (flammable service). | Electrical | CRITICAL
01001-03 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Inlet gas | PIT-1001 | “Wire” — pull/terminate instrument wiring. | Electrical | HIGH
01001-18 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Outlet gas | PIT-1002 | “Wire” — pull/terminate instrument wiring. | Electrical | HIGH
01001-29 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Signal runs, X-11001 | — | Red slashes across dashed signal lines + “Wire” — pull signal wiring. | Electrical | HIGH
01003-14 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 skirt | — | “Ground” — install vessel grounding. | Electrical | HIGH
02001-04 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Meter Skid #1 | Mustang SCS panel | “Conduit Installed, Need to pull wire” — pull & terminate wire to heated enclosure/stream splitter. | Electrical | HIGH
02001-11 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | S-1100 | — | “Ground vessel + skid” — install grounding. | Electrical | HIGH
02004-08 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LIT V-2 standpipe | LIT V-2 | “Secure Wire” (two arrows) — secure wire/heat-trace along bridle standpipe. | Electrical | HIGH
02004-09 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LIT V-2 bridle | LIT V-2 | “Wire” — complete/terminate wiring at transmitter. | Electrical | HIGH
02009-10 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Still-bottoms bridle | LIT T-2B | “Electrical Cover” — install missing transmitter housing cover. | Electrical | HIGH
02011-06 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A discharge cluster | PI/PIT P-3A2 | “Wire” + cloud — pull/terminate wiring. | Electrical | HIGH
02011-07 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A suction | PI/PIT P-3A1 | “Wire” — wire loop. | Electrical | HIGH
02011-09 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3B suction | PI/PIT P-3C | “Wire” — wire loop. | Electrical | HIGH
02012-04 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 bridles | LT E-2A / E-2B | “Wire” — wire both level transmitters. | Electrical | HIGH
02012-05 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 1"-V-0094-A2 area | TIT E-2E | “Wire” — wire temperature transmitter. | Electrical | HIGH
02012-12 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 3"-GH-7008-A2 meter | FQI H-1 | “Wire” — wire fuel-gas metering cluster. | Electrical | HIGH
02013-14 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | Blower | BL-101 | “wire + ground” — power wiring and grounding. | Electrical | HIGH
02014-12 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | Condenser liquid outlet | ABV-1200A | “Wire” — wire actuated 3-way valve. | Electrical | HIGH
02015A-01 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | 8"-HM-108A-C2-1.5"H | TE/TI/TY-27001A | “Wire” — wire inlet temperature loop. | Electrical | HIGH
02015A-08 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater electrical | — | “Missing 2" seal off cover” — install. | Electrical | HIGH
02015A-10 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater electrical | — | “Missing 2-1" & 2-2" electrical Covers” — install two 1" and two 2" covers. | Electrical | HIGH
02115-18 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | Blower | BL-102 | “Wire + Ground” — power wiring and grounding. | Electrical | HIGH
03002-04 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Meter run | TE-1240A | “Wire” — wire temperature element. | Electrical | HIGH
04001-01 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | TK-41001 | LIT/LSH-4001 | “Wire” — wire level transmitter + switch. | Electrical | HIGH
04001-02 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | TK-41002 | LIT/LSH-4002 | “Wire” — wire. | Electrical | HIGH
04001-03 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | TK-41003 | LIT/LSH-4003 | “Wire” — wire. | Electrical | HIGH
04001-04 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | TK-41004 | LIT/LSH-4004 | “Wire” — wire. | Electrical | HIGH
07001-17 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | Vessels + building | — | “Ground 3 Vessels + Building” — install grounding. | Electrical | HIGH
07003-12 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Meter run | FE/FIT/MVT-7101, AE/AT-7101 | “wire” — wire meter-run instrumentation (heated enclosure). | Electrical | HIGH

## Civil
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
01001-31 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Vessel saddles | X-11001/X-12001 | “Grout + Ground” — grout saddles and install grounding. | Civil / Elec | HIGH
02001-12 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | S-1100 skirt | — | “Grout” — grout vessel base. | Civil | HIGH
02002-09 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | T-1 skirt | — | “Grout” — grout baseplate. | Civil | HIGH
02003-05 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 skirt | — | “Grout” — grout vessel base. | Civil | HIGH
02004-11 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 saddles | — | “Grout (2)” — grout both saddles. | Civil | HIGH
02009-08 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | T-2 skirt | — | “Grout” — grout base ring. | Civil | HIGH
02012-08 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 supports | — | “Grout supports” — grout at containment. | Civil | HIGH
02013-12 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-401 skid | — | “Grout (2)” — grout two base points. | Civil | HIGH
02013-13 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | VCU-101 / BL-101 base | — | “Grout” — grout base. | Civil | HIGH
02015A-06 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater/stack skid | — | “Grout + ground” — grout base, install grounding. | Civil / Elec | HIGH
02115-16 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-402 skid | — | “Grout (2)” — grout two base points. | Civil | HIGH
02115-17 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | VCU-102 / BL-102 base | — | “Grout” — grout base. | Civil | HIGH
03001-09 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | MAF-3200A skirt | — | “Grout” — grout base. | Civil | HIGH
03002-12 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Base ring | — | “Grout” — grout base. | Civil | HIGH

## Structural
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
02012-02 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 platform | — | “Platform Grating” — install missing grating at reboiler platform. | Structural | HIGH
01001-02 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Slug catcher area | X-11001/X-12001 | “Install Platforms (2)” — install two access platforms. | Structural | MED
01003-05 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 top | — | “Add platform (AR)” — access platform as required. | Structural | MED
02003-06 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | LV V-1 area | — | “Install platform” — access platform for level valve/instrument area. | Structural | MED
02004-12 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 level end | — | “Install Platform” — access platform at level-instrument end. | Structural | MED
02009-09 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Lower T-2, N9 area | — | “Install platform” — access platform at reflux line/valve area. | Structural | MED
02009-12 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 14"-AG-0033-A2AS-SR PCV station | — | “Install platform” — access platform at 8" acid gas control station. | Structural | MED
07003-13 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | F-71001 base | — | “Install Platform” — access platform. | Structural | MED

## Engineering
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
02011-02 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 3"-V-0073-A2 | PSV P-3C path | “Discharge Pressure? Goes to 165# MAWP Vessel” — engineering must verify 1440 PSIG relief routing to low-pressure drain vessel. (Eng. Question Q3) | Engineering | CRITICAL
02015C-08 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 8"-HM-180 / 8"-HM-187 | FCV-45001A | Cloud + pink: “Doesn't Exist – Not on ISO's” / “Missing” — 8" control-valve station absent entirely; engineering to confirm requirement, then procure/install. (Eng. Question Q4) | Engineering | CRITICAL
07001-01 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 wet receiver | PSV-7005 | “Remove” + cloud + X — remove PSV-7005 manifold (set 155 psig) and adjoining PI-7004/½" valve. Engineering to confirm relief philosophy change. (Eng. Question Q16) | Engineering | CRITICAL
07001-05 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 dry receiver | PSV-7003 | “Remove” + cloud + X — remove PSV assembly (set 155 psig). (Eng. Question Q16) | Engineering | CRITICAL
07001-09 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 dry receiver | PSV-7001 | “Remove” + cloud + X — remove PSV assembly. (Eng. Question Q16) | Engineering | CRITICAL
01001-34 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 12"-GH-0010-F2AS | FE/FT-1001, TW/TE-1001 | Large hatched cloud over meter-run instruments + sketch of orifice run: “Installing Orifice Meter or RO + FIT ?” — engineering to confirm metering design; install per answer. (Eng. Question Q1) | Engineering | HIGH
02001-01 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 10"-GH-0028-F2AS | — | Red sketch: two tap valves w/ bleeds flanking orifice-flange pair + “RO + FIT ?” — engineering to confirm whether RO + flow transmitter go here; install per answer. (Eng. Question Q2) | Engineering | HIGH
02007-03 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 1"-V-0076-A1 | 1" C1203F LSD | “Dosn't Exist.” [sic] + cloud — printed 1" shutdown valve not in field; reconcile install vs drawing revision. (Eng. Question Q13) | Engineering | HIGH
02007-05 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0021-A1-1.5"H | 6" CV10 | “Dosn't Exist.” + cloud — printed 6" valve on lean amine outlet not in field; reconcile. (Eng. Question Q13) | Engineering | HIGH
02015C-06 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzle C7 | TP-E6 | Cloud: “Where to?” / “Don't Exist – Not on ISO's” — test point connection absent and unrouted; engineering to clarify. (Eng. Question Q4) | Engineering | HIGH
02016-01 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | ½"-C-7001-F2AS | — | “upsize to 1" and/or support” — upsize condensate line to 1" and/or add supports; engineering to confirm. (Eng. Question Q11) | Engineering | HIGH
03001-03 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | PSV mount | PSV-3200A | Red “1½"” + drawn nozzle at vessel wall — verify PSV connection nozzle size 1½" vs printed 1"x1". (Eng. Question Q12) | Engineering | HIGH
01001-37 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 3"-LH-0011-F2AS-1½"H-ET | — | Red “2"-LH-0009-F2AS-1H-ET” added above unlabeled line; flag corrected to “Coalescing Filter / HAY-PID-02101”; “Δ 3x2” at branch — correct line tags on drawing; verify 3"x2" reducer at branch. | Engineering | MED
01001-38 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 2"-DR-7003-F2AS | — | Red-drawn new line + off-page flag to Liquid Blowcase (HAY-PID-07004) — add line to drawing; verify field tie-in (matches 07004 sheet markup). | Engineering | MED
02001-14 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-LH-0009-F2AS | — | Red “2"-LH-0009-F2AS / P&ID-01003” + tie of 2"-C-0201 drop into gas outlet header — update drawing; verify field tie-in (mate of 01003-22). | Engineering | MED
02005-13 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-DR-0100-A1/A2 | — | Red continuation flag “2-DR-0100-A2 / HAY-PID-02016” at west end of drain header — correct drawing continuity; verify field tie-in. | Engineering | MED
02007-06 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 2"-DR-0100-A1 (east) | — | “Removed” + cloud + cut marks — drain header terminus piping removed in field; update drawing / confirm extent. | Engineering | MED
02012-11 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | TCV E-2 station | — | Red “6"” at four station valves — verify actual valve sizes vs drawing; revise drawing or valves. (Eng. Question Q9) | Engineering | MED
02016-07 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 | TI/TW-2001 | “Delete” + hatched cloud — remove from scope (with ¾" nozzle). | Engineering | MED
02016-08 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 | LG-2001 | Hatched cloud — delete (replaced by external bridle -06). | Engineering | MED
02016-09 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2001 left head | — | Hatched cloud over small capped fitting — delete. | Engineering | MED
02016-13 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2002 header drops | — | Red routing clarifications (break squiggles at 1½"-PV-0002/0003-A2 × 1"-DA-0001-A2 / 1"-V-0094-A2 crossings) — verify as-built tie-in locations; update drawing. | Engineering | MED
03002-11 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | Vessel skirt | — | “Do we Need this platform?” — RFI to engineering on service platform. (Eng. Question Q15) | Engineering | MED
03002-19 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 16" riser / 2"-DA-3003-F2-1.5"H-ET | — | “U/G” breaks + red trace to PCV-3001 — record underground transition; verify slop-header tie-in. | Engineering | MED
04001-10 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Drain headers | — | Red tie-in routing arrows into 2"-DA-3003-A2 / 4"-DA-3023-A2 / 2"-DA-2051-A2 junctions — verify as-built tie-in points; update drawing. | Engineering | MED
07002-02 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Methanol pumps title block | P-500A–D | Red cloud + “✱✱” — all four methanol pumps flagged; see Q7 (meaning of asterisks to be confirmed). | Engineering | MED
07002-03 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Pump discharge | P-500A | Red “✱” at discharge assembly — pump flagged for attention (Q7). | Engineering | MED
07002-04 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Pump discharge | P-500B | Red “✱” — flagged (Q7). | Engineering | MED
07002-05 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Pump discharge | P-500C | Red “✱” — flagged (Q7). | Engineering | MED
07002-06 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Pump discharge | P-500D | Red “✱” — flagged (Q7). | Engineering | MED
07002-09 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Supply gas to instrumentation | PCV-501, SG-1…SG-6 | Red “✱✱” at header — cross-reference flag (with -02/-08); confirm intent. | Engineering | MED
01001-08 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | — | “U/G” at OUTLET GAS HEADER TO 16" LAUNCHER flag — record underground transition (as-built). | Engineering | LOW
01001-09 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | — | “U/G” break-arc right of ESD station — record underground segment (as-built). | Engineering | LOW
01001-36 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Left of FV cloud | — | “U/G” break-arcs — record underground segments (as-built). | Engineering | LOW
01001-40 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 1"-GH-3006-F2AS | — | Red/pink highlight along line to Dehy Train I & II + “U/G” — record underground routing (as-built). | Engineering | LOW
01001-43 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Near 4" FC station | — | “U/G” + break-arc — record underground transition (as-built). | Engineering | LOW
01003-22 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0009-F2AS | — | Red note “2"-LH-0009-F2AS / P&ID-02001” + circled 1 — line continues to HAY-PID-02001; update drawing continuity (mate of 02001-14). | Engineering | LOW
01003-23 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 3"-LH-0011-F2AS-1"H-ET | — | Red “3” size prefix added; flag sheet number struck, “02101” written — correct line size & continuation sheet on drawing. | Engineering | LOW
02001-15 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-LH-0009-F2AS-1"H-ET | — | “U/G” + break — record underground segment of gas outlet header (as-built). | Engineering | LOW
02001-16 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Outlet header flag | — | Sheet number struck, “01001” written — correct continuation flag. | Engineering | LOW
02006-03 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 2"-DR-0100-A2 (west) | — | Red “2-DR-0100-A2” filled into blank continuation flag over HAY-PID-02005 — correct drawing (mate of 02005-13). | Engineering | LOW
02015B-04 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | SSI-300017 riser | — | Red trace at header crossing — crossing only (no connection); as-built clarification. | Engineering | LOW
07004-16 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2"-DR-7003-F2AS | — | “U/G” + arc upstream of outlet-header flag — record underground routing (mate of 01001-38). | Engineering | LOW
07006-02 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7602-A2 | Gen I branch | “U/G” — record underground takeoff (Note 3). | Engineering | LOW
07006-04 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7601-A2 | Main header | “U/G” — record underground segment. | Engineering | LOW
07006-05 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7603-A2 | Gen II branch | “U/G” — record underground takeoff. | Engineering | LOW
07006-07 | HAY-PID-07006 | D | Generator Fuel Gas (Generators I / II / III) | 3"-GH-7604-A2 | Gen III branch | “U/G” — record underground takeoff. | Engineering | LOW
08005-06 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | Distribution area | — | “Need to Correct Iso To Match P&ID” — revise piping isometric to match P&ID. | Engineering | LOW

## Operations
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
01001-05 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | Inlet spec blind | “Roll after PSSR” — red-drawn spectacle blind at inlet 16" CSO valve; roll to open position after PSSR. | Operations | CRITICAL
01001-06 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0002-F2AS | Outlet spec blind | “Roll after PSSR” — second red-drawn spectacle blind on outlet gas header to 16" launcher; roll after PSSR. | Operations | CRITICAL
02001-02 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Filter inlet | FV S-1100 | “Remove Wood block” — remove shipping block from 10" FC valve. | Operations | CRITICAL
02009-04 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 2"-DA-2001-A2-1.5"H-ET, N11 | 2" CB10 | Red “CSC” beside printed CSO — car-seal-closed per field; reconcile CSO vs CSC with engineering. (Eng. Question Q10) | Operations | CRITICAL
02009-06 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 2"-DA-2002-A2-1.5"H-ET, N14 | 2" CB10 | Red “CSC” — same car-seal reconciliation at bottom drain. | Operations | CRITICAL
02010-02 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | PSV AC-1 inlet riser | 2" CV10 | Red “CSO” — car-seal-open the isolation valve. | Operations | CRITICAL
02013-03 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | VCU-101 stack | Bird screen | “Remove plastic/wood” — remove shipping covers from stack outlet. | Operations | CRITICAL
02115-03 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | VCU-102 stack | Bird screen | “Remove Wood/Plastic” — remove shipping covers. | Operations | CRITICAL
02015A-12 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Notes block | Note 8 | Pink highlight on “SHIPPED LOOSE BY SIGMA THERMAL AND INSTALLED IN PIPING BY MPLX” — locate all shipped-loose items and install. | Operations | HIGH
02008-03 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | Notes block | — | Pink highlight on note “1) SUPPLIED BY MPLX.” — cross-reference to 02008-02 (locate MPLX-supplied material). | Operations | MED
02010-05 | HAY-PID-02010 | E | Amine Solution Cooler / Reflux Condenser (AC-1, AC-2) | AC-2A/B area | — | “Cleanup Area” — housekeeping. | Operations | MED
02015A-09 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater instruments | — | “Remove instrumentation plastic” — remove shipping wrap. | Operations | MED
04001-11 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Containment, south of TK-41002 | — | “Remove wood” — remove dunnage from containment. | Operations | MED

## Vendor
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
02013-04 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | VCU-101 burner | BS-101/102/103, FR-101/103 | “Wire (By Zeeco)” — flame scanner/rod wiring to JB-101, vendor scope. | Vendor | CRITICAL
02015A-05 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Coil feed runs | FE-27003A/-04A/-05A | “Torque (By Sigma Thermal ?)” — torque three 4" 300# orifice-flange sets; confirm responsibility. (Eng. Question Q8) | Vendor | CRITICAL
02015A-11 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Blower 8" flange | — | “Bolt up Blower 8" (by Sigma Thermal ? Need Garlock gasket)” — bolt up; procure 8" Garlock gasket; confirm responsibility. (Eng. Question Q8) | Vendor | CRITICAL
02115-04 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | VCU-102 burner | BS-104/105/106, FR-106 | “wire (By Zeeco)” — flame scanner wiring to JB-101, vendor scope. | Vendor | CRITICAL
07003-05 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | DP installation | PDI-7101 | Cloud: “By Valley.” / “Missing” — install PDI-7101 assembly (manifold, ½" valves, tubing, 2"x½" taps); vendor “Valley” scope. | Vendor | HIGH

## BOM - Missing Material
Qty | Description | Size | Rating | Material | Spec | Tag | Line Number | Notes / Punch Ref | PO No. | Status
1 | PSV, complete w/ inlet block & vent tailpipe | V-PMS | Set per V-22001 (1435 PSIG design) | V-PMS | A2AS vent | PSV V-22001 | 3"-GH-0031-A2AS | 01003-06 — whole package highlighted missing
1 | PSV assembly: PSV + 2" CSO block + 2"x1" reducer + ½" bleed + 2" ATM tail | 2"x1" | Set 1440 PSIG (fire) | V-PMS | V-PMS | PSV-1100 | S-1100 relief | 02001-03
1 | PSV, thermal relief | 2"x1" | Set 150 PSIG | V-PMS | V-PMS | PSV E-2 | E-2 shell | 02012-03
1 | PSV (check-valve-failure case) | 2"x1½" | Set 150 PSIG | V-PMS | A2 | PSV AC-1 | 8"-LA-0022-A2 riser | 02010-01
2 | PSV, KO drum (fire) w/ vent to safe location | SIZE HOLD | Set 100 PSIG | V-PMS | V-PMS | PSV-301 / PSV-302 | KOD-301 / KOD-302 | 02013-06 / 02115-06 — engineering to release size
2 | PSV, KO drum (fire) w/ vent to safe location | SIZE HOLD | Set 15 PSIG | V-PMS | V-PMS | PSV-401 / PSV-402 | KOD-401 / KOD-402 | 02013-10 / 02115-12
1 | PSV relief station complete (PSV + 2" CSO block + 2"x1" reducer + ½" bleed + vent) | 1"x2" | Set 121 PSIG | V-PMS | L2 | PSV-7002 | 3"-IA-7006-L2 | 07001-14
1 | PSV (PCV failure) + ATM vent | SIZE HOLD | Set 5 PSIG system | V-PMS | A2 | PSV-7006 | 3"-GH-7010-A2 | 07006-01
1 | PSV vent tailpipe to ATM | 2" | V-PMS | V-PMS | A2 | PSV T-1 | 2"-V-0033-A2 | 02002-02
1 | PSV vent tailpipe to ATM | SIZE HOLD | V-PMS | V-PMS | V-PMS | PSV-7101 | F-71001 | 07003-01
1 | Choke nipple (restriction orifice) | 1", ⅜" bore | V-PMS | V-PMS | F2AS | RO V-1 | 1"-C-0008-F2AS-SR | 02003-07
2 | Orifice plate, bore 0.1031" | 2" line | V-PMS | V-PMS | A2 | RO-7101 / RO-7102 | 2"-LH-7002-A2-1.5"H-ET / N4 | 07003-10/-11
2 | Orifice plate, bore 0.7394" | 2" line | V-PMS | V-PMS | F2 | RO-1240A / RO-1241A | 2"-DA-3004-F2 / 2"-DA-3019-F2 | 03002-13/-14
2 | Orifice plate, bore 0.1505" + bleed ring set w/ bleed valves | per line | 6000# taps | V-PMS | F2 | RO-3201A / RO-3202A | MAF-3200A drains | 03001-04/-05/-13
2 | Flow element (RO) + FIT transmitter | 2" line | V-PMS | V-PMS | A2 | FE/FIT-100, FE/FIT-101 | 2"-FG-2220-A2 / 2"-FG-2222-A2 | 02013-02 / 02115-02 — wire already pulled
1 | Orifice plate + FIT (meter run exists) | 8" line | V-PMS | V-PMS | F2 | FE/FIT-1240A | 8"-GH-3005-F2 | 03002-03
1 | dP flow transmitter + 2 impulse manifold valve sets + tubing | — | V-PMS | — | F2 | FIT P-3 | 6"-LA-0025-F2 | 02011-14
2 | Cone strainer, temporary | 4" | V-PMS | V-PMS | F2AS | — | 4"-LH-0003 / 4"-LH-0006 | 01001-25/-26 (with FD below)
2 | Flow device “4" FD” | 4" — SIZE HOLD | V-PMS | V-PMS | F2AS | — | same | 01001-25/-26 — engineering to release
1 | Static mixer (MPLX-supplied — locate) | 2" | V-PMS | V-PMS | A2AS | X-2 | 2"-W-8305-A2AS-1.5"H-ET | 02008-02
1 | Control valve station w/ actuator (existence to be confirmed by engineering first) | 8" | V-PMS | V-PMS | C2 | FCV-45001A | 8"-HM-180 / -187 | 02015C-08 — “not on ISOs”
1 | Blanket-gas regulator + ¼" fittings | ¼" | Set 30 PSIG | V-PMS | A2 | PCV-2001 | ¼"-GH-2001-A2 | 02015C-01
1 | Regulator, motive/fuel gas | ½" tubing | Set 100 PSIG | V-PMS | — | PCV-2002A | from 2"-GH-7006-A2 | 02014-05
1 | Regulator set: PCV + PI 0-150# + ¼" valve + tubing | ¼" | V-PMS | V-PMS | — | PCV-100A / PI-101A | V-100 overhead | 07002-10
1 | Burner main-gas vent valve assembly: XV + FO orifice + vent gooseneck | 1½" | V-PMS | V-PMS | NG | XV-20003A | 1½"-80-NG-204 | 02015D-02 — vent piping by MPLX
1 | Burner pilot-gas vent valve assembly: XV w/ solenoid + FO orifice + gooseneck | ¾" | V-PMS | V-PMS | NG | XV-20006A | ¾"-80-NG-205 | 02015D-03
2 | Valve, vent header (type per spec) | 14" | 150# | V-PMS | A2 | — | 14" VF headers @ NOTE 7 | 02013-09 / 02115-11 — long lead
2 | Valve, KO drum overhead | 3" | 150# | V-PMS | A2 | — | 3"-VF-0002 / 3"-VF-0003 | 02013-11 / 02115-13
4 | Level switch stack (LSHH/LSH/LSL/LSLL, 2" conns) per KO drum | 2" | V-PMS | V-PMS | — | LS*-301/-302/-401/-402 | KOD drums | 02013-06/-10, 02115-06/-12 (16 switches total)
2 | Pressure gauge + ½" MNV | ½" | V-PMS | V-PMS | — | PG-301 / PG-302 | KOD-301/302 | 02013-06 / 02115-06
6 | Level gauge (sight glass) assemblies w/ isolation valves | various | V-PMS | V-PMS | — | LG-1200A, LG-302, LG-2002, LG-7001, TK-2001 bridle, TK-81010 LG | — | 02014-08, 02115-08, 02016-06/-11, 07001-20, 08004-02
1 | Pressure gauge assembly 0-160 PSIG w/ ½" NPT valve + siphon (shipped loose — locate) | ½" | V-PMS | V-PMS | C2 | PI-27002A | 8"-HM-187-C2-1.5"H | 02015A-03; new tap req'd (-04)
2 | Pressure gauge (receiver top mount) | ½" | V-PMS | V-PMS | L2 | VS-70001 / VS-70002 | — | 07001-06/-10
1 | Pressure indicator | ½" | V-PMS | V-PMS | — | PI-2001 | TK-2001 N3 | 02016-04
2 | TI + thermowell | ¾" | V-PMS | V-PMS | — | TI/TW E-1D, TW/TI-4002 | 6"-LA-0022-A1 / FA-4000A | 02006-01, 03003-01
1 | PDI dP assembly: manifold, ½" valves, tubing, 2"x½" taps (“By Valley”) | ½" | V-PMS | V-PMS | — | PDI-7101 | F-71001 | 07003-05
±10 | Valve, small-bore (vents/bleeds/gauge) w/ caps or plugs | ½" | V-PMS | V-PMS | per line class | — | various | 01001-12/-35, 02004-01, 02007-01/-02, 03002-06/-16, 02016 bridle, etc.
±12 | Valve, small-bore (drains/vents) w/ plugs | ¾" | V-PMS | V-PMS | per line class | — | various | 02005-07/-08/-12, 02008-04, 03001-01/-02/-07/-08, 03002-09/-10, 07003, 07004-11/-12, 07002-14
±16 | Valve (incl. 5× CSO on PSV discharges) | 1" | V-PMS | V-PMS | per line class | — | various | 01001-01/-07/-32, 02005-10/-11, 02009-02, 02013-05, 02014-06, 03002-15, 03004-04/-05/-07, 04001-06, 07004-03/-04/-05
±4 | Valve, ¼" (LCV stations, sensing lines) | ¼" | V-PMS | V-PMS | DSS/per class | — | JT skid, blowcase | 07002-11/-12/-13, 07004-10
3 | Valve, isolation | 1½" | V-PMS | V-PMS | F2 | — | 1½"-RG-3001-F2, 1½"-LG-3001-F2 + KOD-402 area | 03004-08/-09; plug 02014-09 separately
±15 | Valve (block/gate/ball/check) incl. CSO where marked | 2" | V-PMS | V-PMS | per line class | — | various | 01001-35, 01003-04, 02005-01/-05, 02008-05, 02012-10, 02013-01/-08, 02014-04/-14, 02016-10/-12, 02115-01/-09, 07004-06/-07, 08005-02/-04/-05
±6 | Valve, block | 3" | V-PMS | V-PMS | A2 / V-PMS | — | 3"-V-0073-A2, TK-2001 N1, 3"-PV-3001-A2, Gen I/II/III strainers | 02011-01, 02016-05, 02014-07, 07006-03/-06/-08
1 | Check valve | 1" (H5S) | V-PMS | V-PMS | A00 | — | flash gas → 1"-V-0046-A2 | 03004-01
Field count | Gate valves to replace E-2 bridle valves (½", ¾" CB203; 2" CB10 CSO) | ½"–2" | V-PMS | V-PMS | CB203/CB10 dims | LG/LT E-2A/B | E-2 bridles | 02012-01 — count before ordering
2 | Valve spec change GVTONT → CB10 (CSO) | 2" | V-PMS | V-PMS | CB10 | LG V-2A bridle | V-2 N8/N9 | 02004-06/-07
2 | Handwheel/valve handle | 6" CV90 | — | — | — | P-3A/B discharge | 6"-LA-0025/0024-G2 | 02011-12/-13
1 | Blind flange + gasket + stud bolts/nuts | 3" | V-PMS | V-PMS | F2AS | V-22001 bridle drain | 2"-LH-0009-F2AS area | 01003-16 (+½" valve)
±4 | Blind flange (verify open) + gaskets/bolting | 4" | V-PMS | V-PMS | — | Slop tank C4 nozzles | TK-41001…41004 | 04001-07
4 | Reducer/transition, PVRV riser | 6"x4" | V-PMS | V-PMS | — | Enardo risers | TK-41001…41004 C3 | 04001-05
1 | Reducer | 3"x2" | V-PMS | V-PMS | F2AS | — | 3"-LH-0011 branch | 01001-37 (verify)
1 | Reducer + cap (LIT mount) | 3"x2" | V-PMS | V-PMS | — | LIT-1004 | V-22001 bridle | 01003-08
1 | Expander/swage | 1"x2" | V-PMS | V-PMS | L2 | TK-70001 outlet | — | 07001-22
1 | Swage + union/flange pair + valve | 1"x½" | V-PMS | V-PMS | F2AS | TK-2001 N4 drop | ½"-C-7001-F2AS | 02016-03
lot | SS instrument tubing + compression fittings (PDT T-1 column run ~55 ft; degassers; P-3C ½"x⅜"; analyzer sample; louver actuators ×3; blanket gas; motive gas circuit; timer drains) | ¼"–½" | — | 316 SS | — | — | various | 02002-04, 02005-03, 02011-04, 03002-18, 02003A-01, 02010-03/-04, 02015C-02, 02014-01/-02/-11/-13, 07001-18
lot | Pipe, fittings & valves for red-drawn field routings: TK-81010 suction/fill manifold (2"/1"); TK-2001/2002 truck-outs (2"); slop-tank new drains 2"×2 (1.5"H-ET); side-stream filter 1" loop; VS-70004/70001/70002 vents; KOD drain terminations; bypass-vent 2" NPT (BTEX) | 1"–2" | V-PMS | V-PMS | per line class | — | see punch refs | 08004-04, 02016-10/-12, 04001-08/-09, 02015B-02/-03/-05, 07001-02/-06/-10, 02013-08, 02115-09, 02014-03/-10
1 | Pipe loop/seal (gooseneck) assembly w/ plug/blind | 8" | V-PMS | V-PMS | C2 | — | 8"-HM-187-C2-1.5"H | 02015C-07
1 | Threadolet/tap on 8" line (hot work) for PI | ½" | V-PMS | V-PMS | C2 | PI-27002A | 8"-HM-187-C2-1.5"H | 02015A-04
±14 | Pipe shoes (incl. shim stock at 6 locations) | 2"–4" | — | CS | — | — | various | 01001-30, 01003-17…20, 02001-07/-10, 02008-01, 02012-09
±8 | U-bolts w/ nuts | 3"–14" | — | CS/galv | — | — | 10"-GH-0021, 14"-VF-0023, 3"-IA-7006, IA runs | 01003-01/-02, 02115-10, 07001-16, 03001-15
±12 | Pipe supports / braces / stands (incl. PSV tailpipe braces ×2, double-90 support, makeup-pump discharges ×4) | 1"–4" | — | CS | — | — | various | 02002-03/-05, 02003-02, 02007-07, 02012-06, 03001-06, 07002-01, 07003-03/-04, 07005-02, 08001…08003, 08005-03, 07004-09/-14
±7 | Access platforms + grating (structural steel) | — | — | Steel | — | — | — | 01001-02, 01003-05, 02003-06, 02004-12, 02009-09/-12, 02012-02, 07003-13 (03002-11 pending RFI)
lot | Non-shrink grout (vessels, skids: ~14 locations) | — | — | — | — | — | — | grout items across sheets
lot | Grounding: cable, lugs, rods; grounding station assembly (slop tanks); tank/vessel/building bonding | — | — | Cu | — | — | — | 04001-13/-14, 07001-17, 07005-01, 01003-14, 02001-11, + grout/ground combos
lot | Instrument cable + terminations (≈35 “Wire” items across sheets) | — | — | — | — | — | — | see Electrical/I&E punch items
1+4 | Electrical seal-off cover 2" (1); electrical covers 1" (2) & 2" (2) | 1"/2" | — | — | — | H-27001A pkg | — | 02015A-08/-10
1 | Gasket, blower flange (“Garlock”) | 8" | V-PMS | Garlock | — | H-27001A blower | — | 02015A-11
lot | Plugs: 1" (3+), 1½" (1), ½" (2+), ¾" bull plugs (2), NPT assortment for spare nozzles | ½"–1½" | V-PMS | V-PMS | per class | — | 02012-07, 02014-09, 02115-15, 02007-04, 03003-02, 07001-13, 07004-11/-12 | —
2 | Truck/hose connection w/ cap (+1 hose/quick-connect stub, TK-81010) | 2" | V-PMS | V-PMS | — | TK-2001, TK-2002, TK-81010 | — | 02016-10/-12, 08004-04
1 | Environmental containment (drip) box | — | — | — | — | — | 4"-DA-4010-A2-1"H-ET station | 04001-15
1 | Analyzer probe tap (GENIE) + sample tubing | ¾" | V-PMS | 316 SS tubing | F2AS | AT-1240A | 16"-GH-3006-F2AS | 03002-18
1 | Transmitter electrical housing cover | — | — | — | — | LIT T-2B | — | 02009-10

## Engineering Questions
Q# | Topic | Question / Detail | Answer / Disposition | Answered By | Date
Q1 | Slug catcher metering (HAY-PID-01001) | field asks “Installing Orifice Meter or RO + FIT?” on 12"-GH-0010-F2AS. Confirm metering design so the meter run can be completed. (01001-34)
Q2 | Coalescing filter inlet (HAY-PID-02001) | same question — “RO + FIT ?” sketched on 10"-GH-0028-F2AS. (02001-01)
Q3 | HP pump relief routing (HAY-PID-02011) | “Discharge Pressure? Goes to 165# MAWP Vessel” — PSV P-3C (set 1440 PSIG) relieves via 3"-V-0073-A2 to the drain system. Verify overpressure protection of the receiving vessel. Process-safety critical. (02011-02)
Q4 | Hot Oil expansion tank (HAY-PID-02015C) | FCV-45001A station and test point TP-E6 “don’t exist / not on ISO’s”. Confirm whether FCV-45001A is required (procure if so — 8" control valve, long lead) and where TP-E6 routes. (02015C-06/-08)
Q5 | Blanket gas deviation (HAY-PID-02015C) | PCV-2001 station missing; field notes “¾" valve installed on Adjacent 3" FG pipe” instead. Accept deviation or install per design? (02015C-01)
Q6 | BTEX bypass vent (HAY-PID-02014) | 2" NPT system-bypass-vent piping missing and “Not on ISOs”, crosses skid limits — issue ISO/routing. (02014-03/-10)
Q7 | JT skid asterisks (HAY-PID-07002) | red ✱ on P-500A–D and ✱✱ on the pump title block / supply-gas header — clarify field intent (deadhead check? alignment? vendor issue?). (07002-02…06, -09)
Q8 | Sigma Thermal scope (HAY-PID-02015A) | orifice-flange torquing (“By Sigma Thermal ?”) and 8" blower bolt-up responsibility — confirm vendor vs MPLX scope. (02015A-05/-11)
Q9 | TCV E-2 station sizes (HAY-PID-02012) | red “6"” marked at four station valves vs printed sizes — verify installed sizes; revise drawing or hardware. (02012-11)
Q10 | Car seals on T-2 drains (HAY-PID-02009) | field marks CSC where drawing shows CSO at N11/N14 drains — confirm car-seal philosophy. (02009-04/-06)
Q11 | Condensate line size (HAY-PID-02016) | “upsize to 1" and/or support” for ½"-C-7001-F2AS — confirm resolution. (02016-01)
Q12 | PSV-3200A nozzle (HAY-PID-03001) | red 1½" vs printed 1"x1" NPT — confirm PSV connection size. (03001-03)
Q13 | “Doesn’t exist” valves (HAY-PID-02007, 02005) | printed 1" C1203F LSD valve and 6" CV10 lean-amine valve absent in field; PSV F-2 tailpipe 1" CSO absent. Install per drawing or revise drawing? (02007-03/-05, 02005-10/-11)
Q14 | LSH-1240A hookup (HAY-PID-03002) | “Wire or Tubing?” — confirm electric vs pneumatic. (03002-08)
Q15 | Platform need (HAY-PID-03002) | “Do we Need this platform?” at MBF-1240A. (03002-11)
Q16 | Air-system relief philosophy (HAY-PID-07001) | field removes PSV-7001/-7003/-7005 and adds open vents + PIs at receiver tops, and installs missing PSV-7002 on the header. Confirm the relief redesign is engineered & code-compliant before executing removals. Do not remove reliefs without engineering sign-off. (07001-01/-05/-09, -14)
Q17 | SIZE HOLD releases | engineering to release held sizes blocking procurement: PSV-301/-302/-401/-402 vents, PSV-7006, PSV-7101 tailpipe, SP-3200A vent stack, 4" FD devices (01001-25/-26), 2" FC (01003-20), 3x2 LT reducer verification.
Q18 | New slop-tank drain lines (HAY-PID-04001) | two red-drawn 2" HT lines; one tie-in P&ID ref left blank, second line number partially legible (“2"-DA-2[6]81-A2”) — assign line numbers/sheet refs and confirm tie-in points. (04001-08/-09/-10)

## Procurement
Priority | Order | Qty | Notes | PO No. | Status
CRITICAL | PSVs: V-22001, PSV-1100, PSV E-2, PSV AC-1, PSV-301/-302/-401/-402, PSV-7002 station, PSV-7006 | 10 | LL — sets/orifices per data sheets; 4 vents HOLD (Q17)
CRITICAL | 14" 150# valves (VF headers); 3" 150# valves (VF) | 2 + 2 | LL
CRITICAL | KO-drum level-switch stacks; PG-301/302 w/ MNV | 4 stacks + 2 | —
CRITICAL | Burner vent assemblies XV-20003A / XV-20006A; PCV-2001; blanket ¼" tubing | 2 + 1 + lot | Sigma Thermal parts — confirm scope (Q8)
CRITICAL | FCV-45001A 8" control valve station | 1 | LL + HOLD (Q4)
HIGH | Orifice plates: 0.1031" ×2, 0.7394" ×2, 0.1505" ×2 (+bleed rings); RO V-1 choke nipple ⅜" bore; FE/FIT-100/-101/-1240A; FIT P-3 + manifolds | — | bores are field-specified — verify against datasheets
HIGH | Valve package: ¼" ×4, ½" ×10±, ¾" ×12±, 1" ×16±, 1½" ×3, 2" ×15±, 3" ×6±, gate-valve swap for E-2 bridles (field count), 2" CB10 ×2, 1" H5S check, 2" check (anti-foam) | ~70 | order to line-class specs — Verify in PMS
HIGH | Level gauges ×6; PI/PG ×5; TI/TW ×2; PDI-7101 assembly; PCV-2002A; PCV-100A set | — | —
HIGH | 4" cone strainers ×2 + 4" FD ×2 | 4 | FD HOLD (Q17)
HIGH | SS tubing ¼"–½" + fittings (bulk); instrument cable (bulk) | lot | —
HIGH | Supports: shoes ×14±, U-bolts ×8±, misc supports/braces ×12±, shim stock | lot | —
HIGH | Pipe & fittings for field-routed lines (1"–2", incl. 1.5"H-ET heat trace on two slop drains); 8" loop/seal; ½" threadolet (8" C2); reducers 6"x4" ×4, 3"x2" ×2, 1"x2", 1"x½"; blind flanges 3" ×1, 4" ×4; gaskets & stud bolts | lot | heat trace + insulation to match -ET lines
HIGH | Grounding: station assembly, cable, lugs, rods; electrical covers (1" ×2, 2" ×2), 2" seal-off cover; 8" Garlock gasket | lot | —
MED | Platform steel + grating (7± locations); enviro box; truck connections ×2 + caps; plugs assortment | lot | one platform HOLD (Q15)