TITAN 2 PROJECT · DAILY REPORT

Construction Coordinator Daily Report — Thursday, August 13, 2026

Site:  MPLX Titan Gas Plant, Jal, NM

Owner:  Azota Gas Processing, Ltd.

Report No.:  DR-2026-08-13

Prepared By:  Construction Coordinator — Titan 2

Weather:  Not recorded

Crews On Site:  Field crews (control panels), Eagle Compression (forms / grout pump), civil crews (heater columns, backfill); counts not recorded

## SUMMARY OF THE DAY

Three Bidell control panels were set but with the umbilical cords exiting the front instead of the back toward the cable tray — the plan is to pull and reset all three on 08-14, rerouting the cords under the legs, and set the remaining fourth panel the same day. Eagle Compression completed forms on the first Bidell unit and the pump crew arrived to pump the first grout on 08-14, with the remaining three units to form and grout behind it. The stabilizer compressors need precision leveling; a crew with machinist levels comes 08-14 to level all three to spec, and two units’ interconnect piping to the cooler and engine skid is complete to the pipe-rack stubs, to be verified with Mock in the morning. The tower night-work agenda and scope went to the CM, with a Teams meeting set for 08-18 at 14:00 and an onsite kickoff to follow. Civil crews are breaking heater column forms (four of eight complete) and started backfill on the adjacent foundation, paused by congestion. The slug catcher end cap was flown up for fit-up and returned to the ground for an unknown reason. The daily action-item review closed six register items, including the WICK manway question and the acid gas awning clearance (six inches above the exhaust port).

## WORK PERFORMED / PROGRESS TODAY

- Bidell control panels: three panels set; umbilical cords found exiting the front instead of toward the rear cable tray — pull-and-reset planned for 08-14 along with setting the fourth panel.

- Bidell compressors / grout: forms complete on the first unit; Eagle’s pump crew arrived, first grout pump scheduled 08-14; three units remain to form and grout.

- Stabilizer compressors: machinist level indicated out-of-level — precision leveling crew scheduled 08-14; interconnect piping on two units complete to the pipe-rack stubs, verification with Mock set for the morning of 08-14.

- Towers / night work: agenda and scope prepared and sent to the CM; Teams meeting scheduled 08-18 at 14:00; onsite kickoff meeting to follow for contractors and supervision.

- Civil / heaters: form breaking on the H-49200 heater columns — four of eight columns complete; site cleanup to follow. Backfill started on the adjacent foundation but paused due to congestion and equipment access.

- Slug catcher: end cap flown up for fit-up and returned to the ground; reason unknown — watching for clashes.

- Acid gas compressors: awning build coordinated with the AR foreman; required clearance above the control panel exhaust port set at six inches to avoid interference and allow future removal/replacement.

- Action-item review: daily register walked down — WICK manway feedback, platform decisions, safety package approval, ground-grid backfill coordination, awning clearance, and the heater column pour all closed; details in the register notes below.

## INSPECTIONS & TESTS

- None performed today.

- Scheduled: stabilizer precision leveling and Mock piping verification 08-14; WICK manway/vessel work the weekend of 08-15–08-16; Kodiak pre-commissioning starting 08-17; WICK UT team beginning about 09-01.

## ISSUES / DELAYS (4 OPEN)

- Bidell umbilical cords — three set panels have cords exiting the front instead of the rear cable tray; panels must be pulled and reset (rework, planned 08-14).

- Foundation backfill paused — congestion and equipment access stopped the adjacent-foundation backfill before completion.

- Slug catcher end cap — flown up for fit-up and returned to ground with no reason recorded; potential clash risk until confirmed.

- Heater shell bolting procedure — still outstanding from OPF (P.O. 24250-133); shell assembly remains held.

Coordinator note: The stabilizer machinist-level finding means the earlier levelness reports on C-51150 and C-51175 are to be re-confirmed after the 08-14 precision leveling and the documentation re-issued before any alignment sign-offs — tracked as action item 52.

## OPEN ACTION ITEMS

| # | Action | Area | Responsible / With | Status |
| --- | --- | --- | --- | --- |
| 1 | Gallup vessel inspection — coordination meeting scheduled to align the agenda with the other trades; Teams meeting 08-18 at 14:00, with an onsite kickoff (meet-and-greet, site safety, discipline alignment) to follow; night work starts 08-24. | Inspections | Coordinator / Gallup / CM | In Progress |
| 3 | Obtain the correct bolting procedure for the new heater shells — request current-rev GA and erection manual from OPF (P.O. 24250-133); not in Procore. | Heaters | Coordinator / OPF | Open |
| 4 | Support WICK's on-site inspection of the heaters and concrete foundations. | Heaters | Coordinator / WICK | Open |
| 6 | Coordinate with M4 for final pump alignment and inspection ahead of tie-in sign-off — paused until ready for final alignment. | Pumps | Coordinator / M4 | On Hold |
| 9 | Cover the suction inlets on the Kodiak units to prevent debris entry. | Kodiak | Field team | Open |
| 10 | Build shade covers over the Kodiak control panels; awning build for the acid gas panels being coordinated with the AR foreman (six-inch clearance above the exhaust port confirmed). | Kodiak | AR foreman | In Progress |
| 14 | Interconnect piping for the stabilizer compressors — two units' piping to the cooler and engine skid is complete to the pipe-rack stubs; verify completion status with Mock the morning of 08-14 and continue the remaining runs. | Piping | Coordinator / Mock / MACH | In Progress |
| 15 | Check whether catalysts are still in the exhaust systems and whether they must be removed for the 24-hour burn-in. | Kodiak | TBD | Open |
| 16 | Haul the labeled Kodiak aerial toolboxes to the conex, protected from weather and loss. | Kodiak | Coordinator | Open |
| 18 | Secure the shim packages and filters to prevent loss. | Kodiak | Field team | Open |
| 20 | CNG trailered fuel gas for turbine pre-commissioning — on hold as a contingency in case fuel gas is unavailable; Solar mechanics confirmed the trailer suction does not require a black-start generator on site. | Turbines | Coordinator / CNG | On Hold |
| 21 | Follow up with the AR foreman on the piping estimation and clarify who procures the materials. | Piping | Coordinator / AR | Open |
| 22 | SEC compressor deficiencies — repair bent catwalk and damaged grating, remove tripping-hazard mounting brackets from the control panels, fix platforms, and add platforms on the east side. | SEC | AR foreman | In Progress |
| 24 | Equipment/measurement list — email Morgan's measurement-skid list as requested; Azota to cross-reference the received-equipment list against what is on site; identify which meter skids serve the pipeline connections. | Equipment | Coordinator / Azota | Open |
| 30 | Tower scaffolding — about two weeks covering all towers, larger towers first, OSHA-compliant manway access; due date moved to 08-14. | Towers | Scaffold contractor | In Progress |
| 31 | Precision-level the stabilizer compressors — machinist level showed out-of-level; crew with machinist levels to level all three units to spec. | Equipment | Leveling crew | Sched. 08-14 |
| 35 | Bidell compressor grout — first unit formed, pump crew on site to pump grout 08-14; form and grout the remaining three units, then move to the stabilizer area. | Compressors | Eagle / grout crew | In Progress |
| 36 | Instrument tracking Excel (on-site / missing / long-lead / out-of-scope) — construction managers reviewing the list; forward red-line decisions through Manny. | I&E | CMs / Manny | In Progress |
| 38 | Bring the skid steer on site to clean up excess dirt around the acid gas panel foundations (backhoe on site is too large). | Acid Gas | AR foreman | Sched. 08-14 |
| 41 | Compile the tank and pump account for the SEC, acid gas, and stabilizer compressors; determine oil types and quantities; submit the BOM to the oil supplier. | Compressors | Coordinator | Open |
| 42 | Ground and bond the newly set day tanks, staircases, and platforms — scope sits with Azota or Epic. | Kodiak | Azota / Epic | Open |
| 43 | Confirm whether the 4-inch ESD valve is sufficiently sized for the upsized 6-inch fuel gas line (possible choke point); get confirmation on the bridle level switches and add two 4-inch 600-rated strainers to the list — construction manager following up. | Fuel Gas | CM / Engineering | In Progress |
| 44 | Ensure the pipeline connection points (flanges, meter skids) are installed before the pipeline construction team arrives. | Pipeline | Coordinator | Open |
| 45 | Confirm the Legacy rescue team booking for seven consecutive nights starting 08-24 to support the tower night work. | Towers | Coordinator / Legacy | Open |
| 46 | Kodiak pre-commissioning begins — support startup activities. | Kodiak | Kodiak | Sched. 08-17 |
| 47 | Pick up the bridge and shell beam cutoffs. | Site | Coordinator | Open |
| 48 | Bidell control panels — pull and reset the three panels whose umbilical cords exit the front, rerouting the cords under the legs toward the rear cable tray, and set the remaining fourth panel. | Compressors | Field crew | Due 08-14 |
| 49 | Finish breaking forms on the remaining four heater columns (four of eight complete) and perform site cleanup after form breaking. | Civil | Civil crew | Open |
| 50 | Finish backfilling the adjacent foundation once the congestion/equipment access issue is resolved. | Civil | Civil crew | Open |
| 51 | Investigate the slug catcher end-cap fit-up — the end cap was flown up and returned to the ground for an unknown reason; confirm there are no clashes. | Mechanical | Mechanical lead | Open |
| 52 | Re-confirm the formal levelness of stabilizer compressors C-51150 and C-51175 after the 08-14 precision leveling — earlier levelness reports are superseded by the out-of-level machinist finding; re-issue the levelness documentation for all three units before any alignment sign-offs. | Equipment | Coordinator / Leveling crew | Open |

## PLAN FOR NEXT WORK DAY — FRI 08-14

- Pull and reset the three Bidell control panels (umbilicals under the legs) and set the fourth panel.

- Pump the first Bidell grout; form and grout the remaining three units.

- Precision-level the three stabilizer compressors with machinist levels; verify interconnect piping status with Mock in the morning.

- Skid steer on site to clean up around the acid gas panel foundations.

- Finish breaking the remaining heater column forms; continue umbilical cord rework.

- Tower scaffolding due; confirm readiness for the 08-18 Teams meeting with Gallup and the CM.

Compiled from the last two 08-13 Plaud notes: the Titan Two project update and the action-item status meeting. Weather and crew counts were not recorded in the source notes. Register housekeeping per coordinator's direction — completed items removed: 2 (WICK manway feedback), 26 (platform decision), 28 (safety package approval), 34 (ground-grid backfill coordination), 39 (awning clearance — six inches above exhaust confirmed), 40 (heater column pour — forms now being broken). Item 48 now tracks the Bidell panel umbilical rework per the action-item review. Numbering of surviving items is unchanged; new items start at 49. Item 52 reinstates stabilizer levelness verification: the reports closed under former item 19 are superseded by the out-of-level finding and must be re-issued after the 08-14 precision leveling.