## Summary
Hayfield Ridge Amine Facility — P&ID Redline Punch List & BOM Review — REV 1 (Corrected)
Rev 1 issued 2026-08-12, corrected against the current authoritative redline set. Rev 0 (2026-08-09) had 430 items; item keys carry over.
P&IDs re-reviewed | 40
Open punch items | 137
Critical | 15
High | 97
Medium | 21
Low | 4
Closed/merged from Rev 0 | 295
BOM line items | 38
Engineering questions open | 10
Items signed off | 0
Items remaining | 137
Items by discipline | Items | Closed
Piping | 89 | 0
Mechanical | 1 | 0
I&E | 23 | 0
Engineering | 23 | 0
Vendor | 1 | 0
How to use
• REV 1 supersedes the 2026-08-09 workbook: 292 Rev 0 items closed (marks no longer on the current redline set), 3 duplicates merged, 2 new items added (02003-08, 02004-13). Full trace on the Disposition sheet.
• SAFETY-flagged dispositions (backwards check valve, relief-routing question, all missing-PSV marks, spectacle blinds) need field confirmation at PSSR before being treated as complete — filter the Disposition sheet on "SAFETY".
• Sign off on the discipline tabs (yellow columns; example format: Closed / J. Smith / 2026-08-15); Summary counts update automatically.
• Priority: CRITICAL = before pressure test/commissioning/startup/safety · HIGH = before mechanical completion · MED = before turnover · LOW = documentation.
• BOM: "Verify in Piping Material Specification" (V-PMS) = drawing does not state rating/material; order to the governing line class. Qty "±" requires field count.
QC verification record (2026-08-12)
• Battery 1 — verdict reconciliation: independent per-page verdict files re-parsed; 430/430 covered (138 KEEP / 292 DROP / 0 UNSURE), zero conflicts, zero discrepancies vs this workbook; 138 − 3 merged + 2 new = 137.
• Battery 2 — internals: master tab matches the issued report field-for-field (137 rows); discipline tabs union to 137, no duplicates, critical-first; Disposition = 295 rows (16 SAFETY, 3 MERGED), no overlap with open items; BOM/question refs all resolve to open items; repo copies SHA-256 identical.
• Battery 3 — physical evidence: red/pink cluster scan of all 40 current-set sheets reconciles with the open list on every page (explained variances: 04001 multi-instance rows, 01001-33 pencil mark, 08005 adjacent-mark merge).
• Closure basis: mark absence only — physical completion of closed items is not certified; the 16 SAFETY-tagged dispositions require PSSR walkdown confirmation.

## Punch List (All)
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority
01001-12 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Inlet PSV vent | — | Red-drawn ½" valve w/ cap labeled “½"” on vent tailpipe below inlet PSV — install. | Piping | HIGH
01001-13 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | — | Red-drawn small-bore valve + cap on stub near 16"x10" control valve cloud — install. | Piping | HIGH
01001-16 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0003-F2AS | — | Red-drawn valve + blind flange on stub at elbow — install. | Piping | HIGH
01001-17 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0006-F2AS | — | Red-drawn vertical valve + cap teed up off line — install. | Piping | HIGH
01001-19 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-11001 level bridle | LIT-1001 | “4x2 / Remove” + strike on ½" valve between LIT-1001 and control override — remove valve; verify 4"x2" reducer requirement. | I&E | HIGH
01001-20 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-12001 level bridle | LIT-1002 | Same markup as 01001-19 at X-12001 — remove ½" valve; verify 4"x2" reducer. | I&E | HIGH
01001-21 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-11001 bridle | LS-1001 | Red “2"” (twice) at bridle isolation valves — verify/upsize isolation valves to 2". | Piping | MED
01001-22 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-12001 bridle | LS-1002 | Red “2"” (twice) — same verification at X-12001 bridle. | Piping | MED
01001-23 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0002-F2AS-1½"H-ET | X-11001 | Red-drawn drain valve + plug on stub — install. | Piping | HIGH
01001-24 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0005-F2AS-1½"H-ET | X-12001 | Red-drawn drain valve + plug on stub — install. | Piping | HIGH
01001-33 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 12"-GH-0010-F2AS | PT-1001A | Pencil note “P-T 1001A” with curved leader re-tapping PT-1001A onto the 12" line — relocate tap. (Red cloud/“Wire” from earlier markup removed; graphite mark remains on current set.) | I&E | HIGH
01001-37 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 3"-LH-0011-F2AS-1½"H-ET | — | Red “2"-LH-0009-F2AS-1H-ET” added above unlabeled line; flag corrected to “Coalescing Filter / HAY-PID-02101”; “Δ 3x2” at branch — correct line tags on drawing; verify 3"x2" reducer at branch. | Engineering | MED
01001-38 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 2"-DR-7003-F2AS | — | Red-drawn new line + off-page flag to Liquid Blowcase (HAY-PID-07004) — add line to drawing; verify field tie-in (matches 07004 sheet markup). | Engineering | MED
01003-07 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-GH-0027-F2AS / 10"-GH-0026-F2AS | — | Pink/red triangle on 1" vent valve at junction (to Coalescing Filter) — verify/install 1" valve. | Piping | HIGH
01003-09 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-21001 bridle | LIT-1003 / LSH-1003 | “Remove” + strike — remove ½" valve/plug between instruments. | I&E | HIGH
01003-10 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-21001 bridle | — | Red “3"” (twice) at bridle isolation valves — verify/upsize to 3". | Piping | MED
01003-11 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | LIT-1004 | “Remove” + strike — remove ½" valve at V-22001 bridle. | I&E | HIGH
01003-12 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | — | Red “3"” (twice) — verify/upsize bridle isolation valves to 3". | Piping | MED
01003-15 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0010-F2AS boot drain | — | Red-drawn ½" valve + plug teed off 2" boot-drain stub — install. | Piping | HIGH
01003-23 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 3"-LH-0011-F2AS-1"H-ET | — | Red “3” size prefix added; flag sheet number struck, “02101” written — correct line size & continuation sheet on drawing. | Engineering | LOW
02001-01 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 10"-GH-0028-F2AS | — | Red sketch retained: two tap valves w/ bleeds flanking an orifice-flange pair on the 10" inlet — install per sketch. (Earlier “RO + FIT ?” question text removed on current set — confirm final metering disposition, Q2.) | Engineering | HIGH
02001-07 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-C-0201-F2AS-1.5"H-ET | LCV-1100B | “Shoes” — install two pipe shoes on 2" condensate lines at station. | Piping | HIGH
02001-13 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Inlet riser u/s N1 | — | Red “½"” + arrowhead at coupling — install ½" valve/plug at open coupling. | Piping | HIGH
02001-14 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-LH-0009-F2AS | — | Red “2"-LH-0009-F2AS / P&ID-01003” + tie of 2"-C-0201 drop into gas outlet header — update drawing; verify field tie-in. Merged: covers former 01003-22 (same continuation marked on HAY-PID-01003). | Engineering | MED
02001-16 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Outlet header flag | — | Sheet number struck, “01001” written — correct continuation flag. | Engineering | LOW
02002-08 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | Lower head, near N9 | — | “Remove” + X — remove 2" capped valve/stub. | Piping | HIGH
02003-03 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 nozzle N3 (2") | PI V-1 | “Remove” + X — remove small gauge/bleed valve at N3 between PI isolation and vessel. | I&E | HIGH
02003-08 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | LV V-1 bypass loop | — | Red-drawn small valve + solid plug immediately d/s of the control valve (before the downstream 1" CB203) — install bleed/drain valve + plug. NEW mark on current set. | Piping | HIGH
02004-01 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | 8"-RA-0010-F2AS-SR | — | Red-drawn ½" valve + cap labeled “½"” on top of rich amine run — install high-point vent. | Piping | HIGH
02004-05 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 nozzle M4 (4") | — | Small red check at flange pair (KMTD/MPLX break) — field verification mark; confirm intent/torque status. | Mechanical | MED
02004-06 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LG V-2A bridle, N8 | 2" GVTONT CSO | Red “CB10” — change upper bridle valve spec GVTONT → CB10 (retain CSO). | Piping | HIGH
02004-07 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LG V-2A bridle, N9 | 2" GVTONT CSO | Red “CB10” — change lower bridle valve to CB10. | Piping | HIGH
02004-10 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | 1"-DR-0003-A2AS | — | “Remove By MPLX” + X — remove flanged drain valve adjacent saddle. | Piping | HIGH
02004-13 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | PCV V-2B bypass drop leg | — | Red-drawn valve + solid plug at the low-point corner of the bypass leg — install low-point drain valve + plug. NEW mark on current set. | Piping | HIGH
02005-07 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 meter run | — | Red-drawn ¾" valve + plug below FE F-1 — install vent/bleed. | Piping | HIGH
02005-08 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6"-RA-0013-A2-1.5"H-SR | — | Red-drawn ¾" valve + plug near F-1 outlet riser — install drain/vent. | Piping | HIGH
02005-10 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 1"-V-0071-A1 | PSV F-2 tail | “Doesn't Exist.” + X on printed 1" CSO valve — valve shown on drawing is not in field. | Piping | CRITICAL
02005-11 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 1"-V-0071-A1 | — | “Needs to Be Added Inside Skid limits.” — install the missing 1" CSO valve + tailpipe work inside skid. | Piping | CRITICAL
02005-12 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6" outlet header | — | Red-drawn valve + plug (size unmarked, ~¾") on header toward L/R exchanger — install low-point drain. | Piping | HIGH
02005-13 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-DR-0100-A1/A2 | — | Red continuation flag “2-DR-0100-A2 / HAY-PID-02016” at west end of drain header — correct drawing continuity on this sheet and HAY-PID-02006; verify field tie-in. Merged: covers former 02006-03 (same flag correction on the mate sheet). | Engineering | MED
02005-14 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-DR-0100-A1 (east) | — | Red emphasis chevrons on printed drain flag — verify/connect continuation to HAY-PID-02006. | Piping | MED
02006-01 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 6"-LA-0022-A1 | TI/TW E-1D | Red cloud + tag “E-1D” on unlabeled TI/TW bubble — install & tag temperature indicator with thermowell on E-1 lean amine outlet. | I&E | HIGH
02006-02 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 6" crossover branch | — | Red-drawn valve + plug (no size) upstream of 6" block valve — install vent/drain bleed. | Piping | HIGH
02006-04 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 2"-DR-0100-A1 (east) | — | Red emphasis on printed flag to HAY-PID-02007 — verify continuation/tie-in. | Piping | MED
02007-01 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0018-A1-1.5"H | P-1A discharge | Red “½"” + drawn valve between check and block — install ½" valve (vent/gauge). | Piping | HIGH
02007-02 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0019-A1-1.5"H | P-1B discharge | Red “½"” + drawn valve — install ½" valve. | Piping | HIGH
02007-03 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 1"-V-0076-A1 | 1" C1203F LSD | “Dosn't Exist.” [sic] + cloud — printed 1" shutdown valve not in field; reconcile install vs drawing revision. (Eng. Question Q13) | Engineering | HIGH
02007-05 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0021-A1-1.5"H | 6" CV10 | “Dosn't Exist.” + cloud — printed 6" valve on lean amine outlet not in field; reconcile. (Eng. Question Q13) | Engineering | HIGH
02007-06 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 2"-DR-0100-A1 (east) | — | “Removed” + cloud + cut marks — drain header terminus piping removed in field; update drawing / confirm extent. | Engineering | MED
02007-08 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | Spare-filter bridges | PDI F-4B / F-4C | Red tick marks on both PDI balloons — verify gauges installed/functional. | I&E | MED
02008-04 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-RF-0035-A2-1.5"H-ET-SR | LV T-2 | Red “¾” + drawn valve below line — install ¾" drain/bleed between block and check. | Piping | HIGH
02009-02 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 10"-LA-0017-A2-1.5"H | — | Red “1"” ×3 + drawn valves — install two 1" high-point vents and one 1" drain on lean amine to reboiler. | Piping | HIGH
02009-05 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Nozzle C2 gauges | PI T-2B, TI T-2B | Red instrument range edits at nozzle C2: “0-100#” over PI T-2B and “50-300F” over TI T-2B — verify/replace gauges to marked ranges (current set reads 50-300F). | I&E | MED
02011-05 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-G2 | PIT P-3A2 | Red bubble + two drawn root valves at new tap between CV90 and check — relocate PIT P-3A2 tap here; install two small-bore root valves. | I&E | HIGH
02011-08 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0024-G2 | PI/PIT P-3D | Red cloud around PI/PIT P-3D + arc arrows to the new tap on 6"-LA-0024-G2 — relocate tap (mirror of 02011-05). (“Wire” call-out removed on current set — wiring scope cleared.) | I&E | HIGH
02011-14 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-F2 | FIT/FIC P-3 | “Missing” + pink highlight — install FIT P-3 dP transmitter, both impulse manifold valve sets, and tubing on common discharge meter. | I&E | CRITICAL
02011-16 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A suction drop | 6" cone strainer | Red doodle at temporary strainer — verify installed; remove after flushing per commissioning plan. | Piping | HIGH
02011-17 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3B suction drop | 6" cone strainer | Same verification at P-3B. | Piping | HIGH
02012-01 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 level bridles | LG/LT E-2A, E-2B | Large cloud: “Change all of Them to Gate Valves” — replace all bridle isolation valves (½", ¾" CB203; 2" CB10 CSO) with gate valves; count in field before ordering. | Piping | HIGH
02012-07 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 24"-LA-0029-A2-1.5"H | — | Red-drawn 1" stub/⌀ glyph on 24"-LA-0029-A2-1.5"H adjacent TE/TW E-2E — plug open 1" connection. (“Needs plug” text removed; drawn mark remains.) | Piping | CRITICAL
02012-10 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 shell (S4–S1) | — | Red-drawn 2" valve at shell connection — install (field addition). | Piping | HIGH
02012-11 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | TCV E-2 station | — | Red “6"” at four station valves — verify actual valve sizes vs drawing; revise drawing or valves. (Eng. Question Q9) | Engineering | MED
02013-01 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 2"-GH-7004-A2 | — | Red-drawn 2" valve u/s of PCV-100 — install 2" fuel gas isolation valve. | Piping | HIGH
02013-02 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 2"-FG-2220-A2 | FE/FIT-100 | Red-drawn orifice marks + “2"” flanking the FIT-100 tap on 2"-FG-2220-A2 — install FE-100 restriction orifice + FIT-100; terminate previously pulled wire. (Pink/“Missing… wire pulled” text removed; drawn marks remain.) | I&E | CRITICAL
02013-05 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 14"-AG-0033-A2AS-SR | — | Red-drawn high-point vent (valve + plug) before KOD-301 — install (likely 1"; verify size). | Piping | HIGH
02013-07 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 top | — | Red-drawn valve at PSV/inlet nozzle connection — install small-bore valve. | Piping | HIGH
02013-08 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 drain | — | Red-drawn 2" valve at drain termination d/s of flame arrestor — install. | Piping | HIGH
02014-03 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | D — system by-pass vent | — | Cloud: “Missing / Not on ISOs / SKID LIMITS” — fabricate/install 2" NPT bypass-vent piping; add to ISOs. (Eng. Question Q6) | Piping | HIGH
02014-10 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 2" NPT bypass-vent run | — | “Missing” + cloud/pink — fabricate/install segment from D vent past HZZ-1100A to BTEX outlet drop near SP-1100A. | Piping | HIGH
02115-01 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 2"-GH-7005-A2 | — | Red-drawn 2" valve u/s of PCV-103 — install 2" fuel gas isolation valve. | Piping | HIGH
02115-02 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 2"-FG-2222-A2 | FE/FIT-101 | Red-drawn orifice marks flanking FE/FIT-101 tap on 2"-FG-2222-A2 — install FE-101 orifice + FIT-101; terminate pulled wire. (Text removed; drawn marks remain.) | I&E | CRITICAL
02115-05 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 14"-AG-0040-A2AS-SR | — | Red-drawn high-point vent (valve + plug) before KOD-302 — install (verify size). | Piping | HIGH
02115-07 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 14" inlet drop | — | Red-drawn valve at inlet connection — install (size per connection; verify). | Piping | HIGH
02115-09 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 2" drain | — | Red-drawn valve + termination at open end — install 2" valve (+ flame arrestor per KOD-301 pattern). | Piping | HIGH
02015A-03 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater outlet detail | PI-27002A | Cloud: “Missing / Not on ISO’s” — outlet pressure-gauge assembly (0-160 psig, ½" NPT valve, siphon; shipped loose per Note 8, MPLX installs) missing. Merged: includes the ½" tap required on 8"-HM-187-C2-1.5"H (former 02015A-04). | I&E | HIGH
02015B-02 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-106 → filter | SSI-30001A | Red-drawn routing from the 1" branch (GL4SW3) to the SSI-30001A filter inlet — install side-stream supply per markup. (Size labels removed on current set — verify 1" in field.) | Piping | HIGH
02015B-03 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | Filter hookup | SSI-30001A | Red-drawn loop through filter inlet/outlet (1" 3000# SW nozzles) — re-route/complete filter piping per sketch. | Piping | HIGH
02015B-04 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | SSI-300017 riser | — | Red trace at header crossing — crossing only (no connection); as-built clarification. | Engineering | LOW
02015B-05 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-110 | — | Red-drawn vertical drop tying into 6"-40-TF-110 — install side-stream return tie-in per markup. (Size label removed — verify 1" in field.) | Piping | HIGH
02015C-01 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | ¼"-GH-2001-A2 | PCV-2001 | Red hatch marks on ¼"-GH-2001-A2 at the PCV-2001 station inlet — blanket-gas regulator station (set 30 psig) still flagged not installed. (Earlier “¾" valve installed on adjacent 3" FG pipe” deviation note removed — reconcile with engineering, Q5.) | I&E | CRITICAL
02015C-02 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | To nozzle C3 | — | Red hatch marks along the ¼" blanket-gas run to nozzle C3 — install ¼" tubing/branch, full run across HAY-PID-02015C and 02015D. Merged: covers former 02015D-01 (matching hatch on the blower sheet). | I&E | CRITICAL
02015C-03 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzles C1, C3 | — | Red checks on both 150# RF flanges — complete/verify hookups (with -02). | Piping | HIGH
02015C-06 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzle C7 | TP-E6 | Cloud: “Where to?” / “Don't Exist – Not on ISO's” — test point connection absent and unrouted; engineering to clarify. (Eng. Question Q4) | Engineering | HIGH
02015C-07 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 8"-HM-187-C2-1.5"H | — | Cloud at the 8" gooseneck on 8"-HM-187-C2-1.5"H, text now “Doesn’t Exist – not on ISO’s” — install loop/seal assembly; add to ISOs (Q4). | Piping | HIGH
02015C-08 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 8"-HM-180 / 8"-HM-187 | FCV-45001A | Cloud + pink: “Doesn't Exist – Not on ISO's” / “Missing” — 8" control-valve station absent entirely; engineering to confirm requirement, then procure/install. (Eng. Question Q4) | Engineering | CRITICAL
02015D-02 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | 1½"-80-NG-204 | XV-20003A | Pink highlight — burner main-gas vent valve assembly (1½" XV, FO orifice, vent gooseneck) missing; install (vent piping by MPLX, Note 2). | I&E | CRITICAL
02015D-03 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | ¾"-80-NG-205 | XV-20006A | “Missing” (two-headed arrow, also to -02) — pilot-gas vent valve assembly (¾" XV w/ solenoid, FO orifice, gooseneck) missing; install. | I&E | CRITICAL
02016-03 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | Drop to N4 (½") | — | Red fitting stack “1x½” — install union/flange pair, valve, 1"x½" swage at N4. | Piping | HIGH
02016-13 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2002 header drops | — | Red routing clarifications (break squiggles at 1½"-PV-0002/0003-A2 × 1"-DA-0001-A2 / 1"-V-0094-A2 crossings) — verify as-built tie-in locations; update drawing. | Engineering | MED
03001-03 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | PSV mount | PSV-3200A | Red “1½"” + drawn nozzle at vessel wall — verify PSV connection nozzle size 1½" vs printed 1"x1". (Eng. Question Q12) | Engineering | HIGH
03001-05 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | RO-3201A flanges | — | “Bleed Rings” — install bleed ring(s) with bleed valves at orifice flanges. | Piping | HIGH
03001-10 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Nozzles E (1" liq outlet), D (1½"-RG-3001-F2) | — | Red hash ticks at vendor termination points (Note 3: piping beyond termination not provided) — complete downstream tie-ins. | Piping | HIGH
03001-11 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Nozzles C (lean glycol), H (1"-GH-3012-F2) | — | Red hash ticks at vendor termination points — complete downstream tie-ins. | Piping | HIGH
03001-12 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | 8"-GH-3004-F2 | — | Red-drawn 1" plugged valve assembly (stem, valve, flange bars, plug) — install 1" valved+plugged branch (vent/sample) on dry gas line. | Piping | HIGH
03002-02 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 8"-GH-3005-F2 | — | Red-drawn 1" valve on stub at elbow above nozzle B — install 1" high-point vent. | Piping | HIGH
03002-05 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | FV-1240A manifold | — | Red marks at two ½" bypass/vent valves — install ½" plugs/caps (or valves); confirm intent in field. | Piping | MED
03002-19 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 16" riser / 2"-DA-3003-F2-1.5"H-ET | — | “U/G” breaks + red trace to PCV-3001 — record underground transition; verify slop-header tie-in. | Engineering | MED
03004-01 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | Flash-gas line → 1"-V-0046-A2 | 1" H5S | Cloud + “Missing Checkvalve” — install 1" H5S check valve on the flash-gas line to 1"-V-0046-A2. | Piping | HIGH
03004-06 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1½" A00-GR-04 | 1½" W2ZU | “valve in wrong spot” / “Has to move” — relocate valve from MAJ-1200A outlet nozzle to marked position on vertical branch. | Piping | HIGH
04001-05 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | PVRV risers, C3 (×4) | Enardo ES-660-HF | “6X4” ×4 — install 6"x4" transition/reducer at each tank's PVRV riser. | Piping | HIGH
04001-06 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Tank bottoms (×4) | — | Red-drawn 1" valve at each tank near manway — install four 1" drain/water-draw valves. | Piping | HIGH
04001-07 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | C4 nozzles (×4) | — | Red triangle at each 4" side nozzle — verify blinded; install 4" blind flanges if open. | Piping | HIGH
04001-08 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 2"-DA-2101-A2-1.5"H-ET | — | Red-drawn new 2" HT drain line + 2" valve + capped riser at containment (P&ID ref blank) — install; engineering to assign tie-in/sheet ref. | Piping | HIGH
04001-09 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 2"-DA-2[6]81-A2-1.5"H-ET [digits unclear] | — | Second red-drawn 2" HT drain line + 2" valve, tie-in “HAY-P&ID 02013” — install; verify line number with engineering. | Piping | HIGH
04001-10 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Drain headers | — | Red tie-in routing arrows into 2"-DA-3003-A2 / 4"-DA-3023-A2 / 2"-DA-2051-A2 junctions — verify as-built tie-in points; update drawing. | Engineering | MED
07001-01 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 wet receiver | PSV-7005 | “Remove” + cloud + X — remove PSV-7005 manifold (set 155 psig) and adjoining PI-7004/½" valve. Engineering to confirm relief philosophy change. (Eng. Question Q16) | Engineering | CRITICAL
07001-02 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 top, 6" nozzle | — | “VENT” + drawn gooseneck along 1½"-IA-7036-L2 — install atmospheric vent in lieu of removed PSV. | Piping | CRITICAL
07001-03 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | ½"-IA-7040-L2 | — | Red X-hatch — delete/remove line + ½" SS tube run below VS-70004. | Piping | HIGH
07001-05 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 dry receiver | PSV-7003 | “Remove” + cloud + X — remove PSV assembly (set 155 psig). (Eng. Question Q16) | Engineering | CRITICAL
07001-06 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 top nozzle | — | “Vent” + “← PI” — install gooseneck vent + pressure gauge at top (1½"-IA-7032-L2). | Piping | HIGH
07001-07 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 shell | PI-7001 | Red cloud — relocate PI-7001 to top nozzle (with -06). | I&E | HIGH
07001-09 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 dry receiver | PSV-7001 | “Remove” + cloud + X — remove PSV assembly. (Eng. Question Q16) | Engineering | CRITICAL
07001-10 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 top nozzle | — | “Vent” + “PI” — install vent + PI (1½"-IA-7035-L2). | Piping | HIGH
07001-11 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 shell | PI-7002 | Red cloud — relocate to top (with -10). | I&E | HIGH
07002-10 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | V-100 overhead | PCV-100A, PI-101A | Cloud + “Missing” — install instrument-gas regulator set: PCV-100A, PI-101A (0-150#), ¼" valve, tubing, TO SG-7 takeoff. | I&E | HIGH
07002-11 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Above LCV-100 | — | Red “¼"” + drawn valve — install ¼" valve upstream of LCV-100 (size ¼" vs ¾" to be verified). | Piping | HIGH
07002-12 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Below LCV-100 | — | Red “¼"” + drawn valve above 1" DSS spec break — install ¼" bleed. | Piping | HIGH
07002-13 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | D/s LCV-200 | — | Red “¼"” + drawn valve at 2" DSS break — install ¼" valve. | Piping | HIGH
07002-14 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | D/s LCV-300 | — | Red “¾"” + drawn valve at 2" DSS break — install ¾" valve (size to be verified). | Piping | HIGH
07002-15 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | V-300 overhead 2"-PG-300-03 | Methanol inj. pt | Cloud: “not connected inside skid.” — complete ¼" methanol-injection tie-in from pump 4. | Piping | HIGH
07002-16 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 3"-PG-104-A (E-400A N4) | — | Red highlighter trace, no text — segment flagged; verify installation/routing. | Piping | MED
07002-17 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 3"-PG-104-B (E-400B N4) | — | Red highlighter trace — verify installation/routing. | Piping | MED
07003-05 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | DP installation | PDI-7101 | Cloud: “By Valley.” / “Missing” — install PDI-7101 assembly (manifold, ½" valves, tubing, 2"x½" taps); vendor “Valley” scope. | Vendor | HIGH
07003-06 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Gauge standpipe (N5) | — | Red-drawn vent valve at top — install. | Piping | HIGH
07003-07 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Stub below N6 | — | Red-drawn valve + plug — install drain valve + plug above 2"-LH-7002-A2-1.5"H-ET. | Piping | HIGH
07003-08 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Nozzle N8 stub | — | Red valve symbol (~¾", partially legible) at KMTD/MPLX boundary — install valve; verify size. | Piping | HIGH
07003-09 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Stub below N7 | — | Red-drawn valve + plug next to RO-7102 — install drain valve + plug. | Piping | HIGH
07004-01 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71001 bottom outlet | 1" valve | “Remove” + X — remove 1" valve (into 2" drain manifold). | Piping | HIGH
07004-02 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71002 bottom outlet | 1" valve | “Remove” + X — remove 1" valve (to 2"-DR-7002-F2AS). | Piping | HIGH
07004-07 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2"-DR-7002-F2AS | — | Red routing trace from 2"-DR-7002-F2AS into the bottom drain header — complete routing per markup. (Earlier “2"/Add” valve portion removed on current set — valve add cleared.) | Piping | HIGH
07004-10 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71003 sensing line | PC/PV-71003C | Red-drawn valve + “¼"” — install ¼" valve in sensing line. | I&E | HIGH
07004-11 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | LG-71003 gauge drain | — | Red tick + triangle at 1"x¾" tap — install ¾" bull plug / verify drain valve. | Piping | HIGH
07004-12 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | LG-71004 gauge drain | — | Red marks below lower gauge valve — install ¾" drain valve + plug. | Piping | HIGH
07004-13 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71003/71004 outfall | Open drain | Cloud around OPEN DRAIN at the V-71003/V-71004 outfall, text now “Where to / No ISO” — drain destination undefined and no isometric exists; engineering to route (Q19), then tie in. | Engineering | HIGH
08005-04 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | End of discharge run | — | Red-drawn valve + “2"” (+ “inst…” partially legible) — install 2" isolation valve upstream of anti-foam distribution split. | Piping | HIGH
08005-05 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | Distribution split → P-1A/B | 2" ball valve | “Missing.” + cloud — install 2" ball valve on through-run to HAY-PID-02007. | Piping | HIGH
08005-06 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | Distribution area | — | “Need to Correct Iso To Match P&ID” — revise piping isometric to match P&ID. | Engineering | LOW

## Piping
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
02005-10 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 1"-V-0071-A1 | PSV F-2 tail | “Doesn't Exist.” + X on printed 1" CSO valve — valve shown on drawing is not in field. | Piping | CRITICAL
02005-11 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 1"-V-0071-A1 | — | “Needs to Be Added Inside Skid limits.” — install the missing 1" CSO valve + tailpipe work inside skid. | Piping | CRITICAL
02012-07 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | 24"-LA-0029-A2-1.5"H | — | Red-drawn 1" stub/⌀ glyph on 24"-LA-0029-A2-1.5"H adjacent TE/TW E-2E — plug open 1" connection. (“Needs plug” text removed; drawn mark remains.) | Piping | CRITICAL
07001-02 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 top, 6" nozzle | — | “VENT” + drawn gooseneck along 1½"-IA-7036-L2 — install atmospheric vent in lieu of removed PSV. | Piping | CRITICAL
01001-12 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | Inlet PSV vent | — | Red-drawn ½" valve w/ cap labeled “½"” on vent tailpipe below inlet PSV — install. | Piping | HIGH
01001-13 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0001-F2AS | — | Red-drawn small-bore valve + cap on stub near 16"x10" control valve cloud — install. | Piping | HIGH
01001-16 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0003-F2AS | — | Red-drawn valve + blind flange on stub at elbow — install. | Piping | HIGH
01001-17 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 16"-GH-0006-F2AS | — | Red-drawn vertical valve + cap teed up off line — install. | Piping | HIGH
01001-23 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0002-F2AS-1½"H-ET | X-11001 | Red-drawn drain valve + plug on stub — install. | Piping | HIGH
01001-24 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 4"-LH-0005-F2AS-1½"H-ET | X-12001 | Red-drawn drain valve + plug on stub — install. | Piping | HIGH
01003-07 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-GH-0027-F2AS / 10"-GH-0026-F2AS | — | Pink/red triangle on 1" vent valve at junction (to Coalescing Filter) — verify/install 1" valve. | Piping | HIGH
01003-15 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 2"-LH-0010-F2AS boot drain | — | Red-drawn ½" valve + plug teed off 2" boot-drain stub — install. | Piping | HIGH
02001-07 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-C-0201-F2AS-1.5"H-ET | LCV-1100B | “Shoes” — install two pipe shoes on 2" condensate lines at station. | Piping | HIGH
02001-13 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Inlet riser u/s N1 | — | Red “½"” + arrowhead at coupling — install ½" valve/plug at open coupling. | Piping | HIGH
02002-08 | HAY-PID-02002 | E | Amine Contactor T-1 (400 GPM Amine Plant) | Lower head, near N9 | — | “Remove” + X — remove 2" capped valve/stub. | Piping | HIGH
02003-08 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | LV V-1 bypass loop | — | Red-drawn small valve + solid plug immediately d/s of the control valve (before the downstream 1" CB203) — install bleed/drain valve + plug. NEW mark on current set. | Piping | HIGH
02004-01 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | 8"-RA-0010-F2AS-SR | — | Red-drawn ½" valve + cap labeled “½"” on top of rich amine run — install high-point vent. | Piping | HIGH
02004-06 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LG V-2A bridle, N8 | 2" GVTONT CSO | Red “CB10” — change upper bridle valve spec GVTONT → CB10 (retain CSO). | Piping | HIGH
02004-07 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | LG V-2A bridle, N9 | 2" GVTONT CSO | Red “CB10” — change lower bridle valve to CB10. | Piping | HIGH
02004-10 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | 1"-DR-0003-A2AS | — | “Remove By MPLX” + X — remove flanged drain valve adjacent saddle. | Piping | HIGH
02004-13 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | PCV V-2B bypass drop leg | — | Red-drawn valve + solid plug at the low-point corner of the bypass leg — install low-point drain valve + plug. NEW mark on current set. | Piping | HIGH
02005-07 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | F-1 meter run | — | Red-drawn ¾" valve + plug below FE F-1 — install vent/bleed. | Piping | HIGH
02005-08 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6"-RA-0013-A2-1.5"H-SR | — | Red-drawn ¾" valve + plug near F-1 outlet riser — install drain/vent. | Piping | HIGH
02005-12 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 6" outlet header | — | Red-drawn valve + plug (size unmarked, ~¾") on header toward L/R exchanger — install low-point drain. | Piping | HIGH
02006-02 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 6" crossover branch | — | Red-drawn valve + plug (no size) upstream of 6" block valve — install vent/drain bleed. | Piping | HIGH
02007-01 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0018-A1-1.5"H | P-1A discharge | Red “½"” + drawn valve between check and block — install ½" valve (vent/gauge). | Piping | HIGH
02007-02 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0019-A1-1.5"H | P-1B discharge | Red “½"” + drawn valve — install ½" valve. | Piping | HIGH
02008-04 | HAY-PID-02008 | E | Reflux Pumps P-2A/B (400 GPM Amine Plant) | 2"-RF-0035-A2-1.5"H-ET-SR | LV T-2 | Red “¾” + drawn valve below line — install ¾" drain/bleed between block and check. | Piping | HIGH
02009-02 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | 10"-LA-0017-A2-1.5"H | — | Red “1"” ×3 + drawn valves — install two 1" high-point vents and one 1" drain on lean amine to reboiler. | Piping | HIGH
02011-16 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3A suction drop | 6" cone strainer | Red doodle at temporary strainer — verify installed; remove after flushing per commissioning plan. | Piping | HIGH
02011-17 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | P-3B suction drop | 6" cone strainer | Same verification at P-3B. | Piping | HIGH
02012-01 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 level bridles | LG/LT E-2A, E-2B | Large cloud: “Change all of Them to Gate Valves” — replace all bridle isolation valves (½", ¾" CB203; 2" CB10 CSO) with gate valves; count in field before ordering. | Piping | HIGH
02012-10 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | E-2 shell (S4–S1) | — | Red-drawn 2" valve at shell connection — install (field addition). | Piping | HIGH
02013-01 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 2"-GH-7004-A2 | — | Red-drawn 2" valve u/s of PCV-100 — install 2" fuel gas isolation valve. | Piping | HIGH
02013-05 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 14"-AG-0033-A2AS-SR | — | Red-drawn high-point vent (valve + plug) before KOD-301 — install (likely 1"; verify size). | Piping | HIGH
02013-07 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 top | — | Red-drawn valve at PSV/inlet nozzle connection — install small-bore valve. | Piping | HIGH
02013-08 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | KOD-301 drain | — | Red-drawn 2" valve at drain termination d/s of flame arrestor — install. | Piping | HIGH
02014-03 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | D — system by-pass vent | — | Cloud: “Missing / Not on ISOs / SKID LIMITS” — fabricate/install 2" NPT bypass-vent piping; add to ISOs. (Eng. Question Q6) | Piping | HIGH
02014-10 | HAY-PID-02014 | F | BTEX for 55 MMSCFD Dehy Unit-I (V-7000A, HZZ-1100A, TK-1200A) | 2" NPT bypass-vent run | — | “Missing” + cloud/pink — fabricate/install segment from D vent past HZZ-1100A to BTEX outlet drop near SP-1100A. | Piping | HIGH
02015B-02 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-106 → filter | SSI-30001A | Red-drawn routing from the 1" branch (GL4SW3) to the SSI-30001A filter inlet — install side-stream supply per markup. (Size labels removed on current set — verify 1" in field.) | Piping | HIGH
02015B-03 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | Filter hookup | SSI-30001A | Red-drawn loop through filter inlet/outlet (1" 3000# SW nozzles) — re-route/complete filter piping per sketch. | Piping | HIGH
02015B-05 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | 6"-40-TF-110 | — | Red-drawn vertical drop tying into 6"-40-TF-110 — install side-stream return tie-in per markup. (Size label removed — verify 1" in field.) | Piping | HIGH
02015C-03 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzles C1, C3 | — | Red checks on both 150# RF flanges — complete/verify hookups (with -02). | Piping | HIGH
02015C-07 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 8"-HM-187-C2-1.5"H | — | Cloud at the 8" gooseneck on 8"-HM-187-C2-1.5"H, text now “Doesn’t Exist – not on ISO’s” — install loop/seal assembly; add to ISOs (Q4). | Piping | HIGH
02016-03 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | Drop to N4 (½") | — | Red fitting stack “1x½” — install union/flange pair, valve, 1"x½" swage at N4. | Piping | HIGH
02115-01 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 2"-GH-7005-A2 | — | Red-drawn 2" valve u/s of PCV-103 — install 2" fuel gas isolation valve. | Piping | HIGH
02115-05 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 14"-AG-0040-A2AS-SR | — | Red-drawn high-point vent (valve + plug) before KOD-302 — install (verify size). | Piping | HIGH
02115-07 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 14" inlet drop | — | Red-drawn valve at inlet connection — install (size per connection; verify). | Piping | HIGH
02115-09 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | KOD-302 2" drain | — | Red-drawn valve + termination at open end — install 2" valve (+ flame arrestor per KOD-301 pattern). | Piping | HIGH
03001-05 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | RO-3201A flanges | — | “Bleed Rings” — install bleed ring(s) with bleed valves at orifice flanges. | Piping | HIGH
03001-10 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Nozzles E (1" liq outlet), D (1½"-RG-3001-F2) | — | Red hash ticks at vendor termination points (Note 3: piping beyond termination not provided) — complete downstream tie-ins. | Piping | HIGH
03001-11 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | Nozzles C (lean glycol), H (1"-GH-3012-F2) | — | Red hash ticks at vendor termination points — complete downstream tie-ins. | Piping | HIGH
03001-12 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | 8"-GH-3004-F2 | — | Red-drawn 1" plugged valve assembly (stem, valve, flange bars, plug) — install 1" valved+plugged branch (vent/sample) on dry gas line. | Piping | HIGH
03002-02 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 8"-GH-3005-F2 | — | Red-drawn 1" valve on stub at elbow above nozzle B — install 1" high-point vent. | Piping | HIGH
03004-01 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | Flash-gas line → 1"-V-0046-A2 | 1" H5S | Cloud + “Missing Checkvalve” — install 1" H5S check valve on the flash-gas line to 1"-V-0046-A2. | Piping | HIGH
03004-06 | HAY-PID-03004 | D | Glycol Region — Filters & Pumps (55 MMSCFD Dehy Train-I) | 1½" A00-GR-04 | 1½" W2ZU | “valve in wrong spot” / “Has to move” — relocate valve from MAJ-1200A outlet nozzle to marked position on vertical branch. | Piping | HIGH
04001-05 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | PVRV risers, C3 (×4) | Enardo ES-660-HF | “6X4” ×4 — install 6"x4" transition/reducer at each tank's PVRV riser. | Piping | HIGH
04001-06 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Tank bottoms (×4) | — | Red-drawn 1" valve at each tank near manway — install four 1" drain/water-draw valves. | Piping | HIGH
04001-07 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | C4 nozzles (×4) | — | Red triangle at each 4" side nozzle — verify blinded; install 4" blind flanges if open. | Piping | HIGH
04001-08 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 2"-DA-2101-A2-1.5"H-ET | — | Red-drawn new 2" HT drain line + 2" valve + capped riser at containment (P&ID ref blank) — install; engineering to assign tie-in/sheet ref. | Piping | HIGH
04001-09 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | 2"-DA-2[6]81-A2-1.5"H-ET [digits unclear] | — | Second red-drawn 2" HT drain line + 2" valve, tie-in “HAY-P&ID 02013” — install; verify line number with engineering. | Piping | HIGH
07001-03 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | ½"-IA-7040-L2 | — | Red X-hatch — delete/remove line + ½" SS tube run below VS-70004. | Piping | HIGH
07001-06 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 top nozzle | — | “Vent” + “← PI” — install gooseneck vent + pressure gauge at top (1½"-IA-7032-L2). | Piping | HIGH
07001-10 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 top nozzle | — | “Vent” + “PI” — install vent + PI (1½"-IA-7035-L2). | Piping | HIGH
07002-11 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Above LCV-100 | — | Red “¼"” + drawn valve — install ¼" valve upstream of LCV-100 (size ¼" vs ¾" to be verified). | Piping | HIGH
07002-12 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | Below LCV-100 | — | Red “¼"” + drawn valve above 1" DSS spec break — install ¼" bleed. | Piping | HIGH
07002-13 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | D/s LCV-200 | — | Red “¼"” + drawn valve at 2" DSS break — install ¼" valve. | Piping | HIGH
07002-14 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | D/s LCV-300 | — | Red “¾"” + drawn valve at 2" DSS break — install ¾" valve (size to be verified). | Piping | HIGH
07002-15 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | V-300 overhead 2"-PG-300-03 | Methanol inj. pt | Cloud: “not connected inside skid.” — complete ¼" methanol-injection tie-in from pump 4. | Piping | HIGH
07003-06 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Gauge standpipe (N5) | — | Red-drawn vent valve at top — install. | Piping | HIGH
07003-07 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Stub below N6 | — | Red-drawn valve + plug — install drain valve + plug above 2"-LH-7002-A2-1.5"H-ET. | Piping | HIGH
07003-08 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Nozzle N8 stub | — | Red valve symbol (~¾", partially legible) at KMTD/MPLX boundary — install valve; verify size. | Piping | HIGH
07003-09 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | Stub below N7 | — | Red-drawn valve + plug next to RO-7102 — install drain valve + plug. | Piping | HIGH
07004-01 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71001 bottom outlet | 1" valve | “Remove” + X — remove 1" valve (into 2" drain manifold). | Piping | HIGH
07004-02 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71002 bottom outlet | 1" valve | “Remove” + X — remove 1" valve (to 2"-DR-7002-F2AS). | Piping | HIGH
07004-07 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | 2"-DR-7002-F2AS | — | Red routing trace from 2"-DR-7002-F2AS into the bottom drain header — complete routing per markup. (Earlier “2"/Add” valve portion removed on current set — valve add cleared.) | Piping | HIGH
07004-11 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | LG-71003 gauge drain | — | Red tick + triangle at 1"x¾" tap — install ¾" bull plug / verify drain valve. | Piping | HIGH
07004-12 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | LG-71004 gauge drain | — | Red marks below lower gauge valve — install ¾" drain valve + plug. | Piping | HIGH
08005-04 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | End of discharge run | — | Red-drawn valve + “2"” (+ “inst…” partially legible) — install 2" isolation valve upstream of anti-foam distribution split. | Piping | HIGH
08005-05 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | Distribution split → P-1A/B | 2" ball valve | “Missing.” + cloud — install 2" ball valve on through-run to HAY-PID-02007. | Piping | HIGH
01001-21 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-11001 bridle | LS-1001 | Red “2"” (twice) at bridle isolation valves — verify/upsize isolation valves to 2". | Piping | MED
01001-22 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-12001 bridle | LS-1002 | Red “2"” (twice) — same verification at X-12001 bridle. | Piping | MED
01003-10 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-21001 bridle | — | Red “3"” (twice) at bridle isolation valves — verify/upsize to 3". | Piping | MED
01003-12 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | — | Red “3"” (twice) — verify/upsize bridle isolation valves to 3". | Piping | MED
02005-14 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-DR-0100-A1 (east) | — | Red emphasis chevrons on printed drain flag — verify/connect continuation to HAY-PID-02006. | Piping | MED
02006-04 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 2"-DR-0100-A1 (east) | — | Red emphasis on printed flag to HAY-PID-02007 — verify continuation/tie-in. | Piping | MED
03002-05 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | FV-1240A manifold | — | Red marks at two ½" bypass/vent valves — install ½" plugs/caps (or valves); confirm intent in field. | Piping | MED
07002-16 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 3"-PG-104-A (E-400A N4) | — | Red highlighter trace, no text — segment flagged; verify installation/routing. | Piping | MED
07002-17 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | 3"-PG-104-B (E-400B N4) | — | Red highlighter trace — verify installation/routing. | Piping | MED

## Mechanical
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
02004-05 | HAY-PID-02004 | E | Amine Flash Tank V-2 (400 GPM Amine Plant) | V-2 nozzle M4 (4") | — | Small red check at flange pair (KMTD/MPLX break) — field verification mark; confirm intent/torque status. | Mechanical | MED

## I&E
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
02011-14 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-F2 | FIT/FIC P-3 | “Missing” + pink highlight — install FIT P-3 dP transmitter, both impulse manifold valve sets, and tubing on common discharge meter. | I&E | CRITICAL
02013-02 | HAY-PID-02013 | F | T.O. for 400 GPM Amine Train & Dehy Train I (VCU-101) | 2"-FG-2220-A2 | FE/FIT-100 | Red-drawn orifice marks + “2"” flanking the FIT-100 tap on 2"-FG-2220-A2 — install FE-100 restriction orifice + FIT-100; terminate previously pulled wire. (Pink/“Missing… wire pulled” text removed; drawn marks remain.) | I&E | CRITICAL
02015C-01 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | ¼"-GH-2001-A2 | PCV-2001 | Red hatch marks on ¼"-GH-2001-A2 at the PCV-2001 station inlet — blanket-gas regulator station (set 30 psig) still flagged not installed. (Earlier “¾" valve installed on adjacent 3" FG pipe” deviation note removed — reconcile with engineering, Q5.) | I&E | CRITICAL
02015C-02 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | To nozzle C3 | — | Red hatch marks along the ¼" blanket-gas run to nozzle C3 — install ¼" tubing/branch, full run across HAY-PID-02015C and 02015D. Merged: covers former 02015D-01 (matching hatch on the blower sheet). | I&E | CRITICAL
02015D-02 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | 1½"-80-NG-204 | XV-20003A | Pink highlight — burner main-gas vent valve assembly (1½" XV, FO orifice, vent gooseneck) missing; install (vent piping by MPLX, Note 2). | I&E | CRITICAL
02015D-03 | HAY-PID-02015D | E | Combustion Air Blower / Burner BRN-20001A (Hot Oil Unit-I) | ¾"-80-NG-205 | XV-20006A | “Missing” (two-headed arrow, also to -02) — pilot-gas vent valve assembly (¾" XV w/ solenoid, FO orifice, gooseneck) missing; install. | I&E | CRITICAL
02115-02 | HAY-PID-02115 | F | T.O. for 640 GPM Amine Train & Dehy Train II (VCU-102) | 2"-FG-2222-A2 | FE/FIT-101 | Red-drawn orifice marks flanking FE/FIT-101 tap on 2"-FG-2222-A2 — install FE-101 orifice + FIT-101; terminate pulled wire. (Text removed; drawn marks remain.) | I&E | CRITICAL
01001-19 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-11001 level bridle | LIT-1001 | “4x2 / Remove” + strike on ½" valve between LIT-1001 and control override — remove valve; verify 4"x2" reducer requirement. | I&E | HIGH
01001-20 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | X-12001 level bridle | LIT-1002 | Same markup as 01001-19 at X-12001 — remove ½" valve; verify 4"x2" reducer. | I&E | HIGH
01001-33 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 12"-GH-0010-F2AS | PT-1001A | Pencil note “P-T 1001A” with curved leader re-tapping PT-1001A onto the 12" line — relocate tap. (Red cloud/“Wire” from earlier markup removed; graphite mark remains on current set.) | I&E | HIGH
01003-09 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-21001 bridle | LIT-1003 / LSH-1003 | “Remove” + strike — remove ½" valve/plug between instruments. | I&E | HIGH
01003-11 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | V-22001 bridle | LIT-1004 | “Remove” + strike — remove ½" valve at V-22001 bridle. | I&E | HIGH
02003-03 | HAY-PID-02003 | E | Outlet Scrubber V-1 (400 GPM Amine Plant) | V-1 nozzle N3 (2") | PI V-1 | “Remove” + X — remove small gauge/bleed valve at N3 between PI isolation and vessel. | I&E | HIGH
02006-01 | HAY-PID-02006 | E | L/R Exchanger E-1 (400 GPM Amine Plant) | 6"-LA-0022-A1 | TI/TW E-1D | Red cloud + tag “E-1D” on unlabeled TI/TW bubble — install & tag temperature indicator with thermowell on E-1 lean amine outlet. | I&E | HIGH
02011-05 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0025-G2 | PIT P-3A2 | Red bubble + two drawn root valves at new tap between CV90 and check — relocate PIT P-3A2 tap here; install two small-bore root valves. | I&E | HIGH
02011-08 | HAY-PID-02011 | G | HP Amine Pumps P-3A/B (400 GPM Amine Plant) | 6"-LA-0024-G2 | PI/PIT P-3D | Red cloud around PI/PIT P-3D + arc arrows to the new tap on 6"-LA-0024-G2 — relocate tap (mirror of 02011-05). (“Wire” call-out removed on current set — wiring scope cleared.) | I&E | HIGH
02015A-03 | HAY-PID-02015A | E | Exhaust Stack / Hot Oil Heater H-27001A (Hot Oil Unit-I) | Heater outlet detail | PI-27002A | Cloud: “Missing / Not on ISO’s” — outlet pressure-gauge assembly (0-160 psig, ½" NPT valve, siphon; shipped loose per Note 8, MPLX installs) missing. Merged: includes the ½" tap required on 8"-HM-187-C2-1.5"H (former 02015A-04). | I&E | HIGH
07001-07 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 shell | PI-7001 | Red cloud — relocate PI-7001 to top nozzle (with -06). | I&E | HIGH
07001-11 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 shell | PI-7002 | Red cloud — relocate to top (with -10). | I&E | HIGH
07002-10 | HAY-PID-07002 | F | JT Fuel Skid (V-100/200/300, E-400A/B, P-500A-D) | V-100 overhead | PCV-100A, PI-101A | Cloud + “Missing” — install instrument-gas regulator set: PCV-100A, PI-101A (0-150#), ¼" valve, tubing, TO SG-7 takeoff. | I&E | HIGH
07004-10 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71003 sensing line | PC/PV-71003C | Red-drawn valve + “¼"” — install ¼" valve in sensing line. | I&E | HIGH
02007-08 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | Spare-filter bridges | PDI F-4B / F-4C | Red tick marks on both PDI balloons — verify gauges installed/functional. | I&E | MED
02009-05 | HAY-PID-02009 | F | Amine Still / Reflux Accumulator T-2 | Nozzle C2 gauges | PI T-2B, TI T-2B | Red instrument range edits at nozzle C2: “0-100#” over PI T-2B and “50-300F” over TI T-2B — verify/replace gauges to marked ranges (current set reads 50-300F). | I&E | MED

## Engineering
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
02015C-08 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | 8"-HM-180 / 8"-HM-187 | FCV-45001A | Cloud + pink: “Doesn't Exist – Not on ISO's” / “Missing” — 8" control-valve station absent entirely; engineering to confirm requirement, then procure/install. (Eng. Question Q4) | Engineering | CRITICAL
07001-01 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70004 wet receiver | PSV-7005 | “Remove” + cloud + X — remove PSV-7005 manifold (set 155 psig) and adjoining PI-7004/½" valve. Engineering to confirm relief philosophy change. (Eng. Question Q16) | Engineering | CRITICAL
07001-05 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70001 dry receiver | PSV-7003 | “Remove” + cloud + X — remove PSV assembly (set 155 psig). (Eng. Question Q16) | Engineering | CRITICAL
07001-09 | HAY-PID-07001 | G | Air Compressor / Receivers (SK-70001, VS-70001/2/4, TK-70001) | VS-70002 dry receiver | PSV-7001 | “Remove” + cloud + X — remove PSV assembly. (Eng. Question Q16) | Engineering | CRITICAL
02001-01 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 10"-GH-0028-F2AS | — | Red sketch retained: two tap valves w/ bleeds flanking an orifice-flange pair on the 10" inlet — install per sketch. (Earlier “RO + FIT ?” question text removed on current set — confirm final metering disposition, Q2.) | Engineering | HIGH
02007-03 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 1"-V-0076-A1 | 1" C1203F LSD | “Dosn't Exist.” [sic] + cloud — printed 1" shutdown valve not in field; reconcile install vs drawing revision. (Eng. Question Q13) | Engineering | HIGH
02007-05 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 6"-LA-0021-A1-1.5"H | 6" CV10 | “Dosn't Exist.” + cloud — printed 6" valve on lean amine outlet not in field; reconcile. (Eng. Question Q13) | Engineering | HIGH
02015C-06 | HAY-PID-02015C | E | Expansion Tank TK-45001A (Hot Oil Unit-I) | Nozzle C7 | TP-E6 | Cloud: “Where to?” / “Don't Exist – Not on ISO's” — test point connection absent and unrouted; engineering to clarify. (Eng. Question Q4) | Engineering | HIGH
03001-03 | HAY-PID-03001 | D | Gas Absorber MAF-3200A (55 MMSCFD Dehy Train-I) | PSV mount | PSV-3200A | Red “1½"” + drawn nozzle at vessel wall — verify PSV connection nozzle size 1½" vs printed 1"x1". (Eng. Question Q12) | Engineering | HIGH
07004-13 | HAY-PID-07004 | E | Blowcase System V-71001…V-71004 | V-71003/71004 outfall | Open drain | Cloud around OPEN DRAIN at the V-71003/V-71004 outfall, text now “Where to / No ISO” — drain destination undefined and no isometric exists; engineering to route (Q19), then tie in. | Engineering | HIGH
01001-37 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 3"-LH-0011-F2AS-1½"H-ET | — | Red “2"-LH-0009-F2AS-1H-ET” added above unlabeled line; flag corrected to “Coalescing Filter / HAY-PID-02101”; “Δ 3x2” at branch — correct line tags on drawing; verify 3"x2" reducer at branch. | Engineering | MED
01001-38 | HAY-PID-01001 | G | Slug Catcher (X-11001 / X-12001) | 2"-DR-7003-F2AS | — | Red-drawn new line + off-page flag to Liquid Blowcase (HAY-PID-07004) — add line to drawing; verify field tie-in (matches 07004 sheet markup). | Engineering | MED
02001-14 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | 2"-LH-0009-F2AS | — | Red “2"-LH-0009-F2AS / P&ID-01003” + tie of 2"-C-0201 drop into gas outlet header — update drawing; verify field tie-in. Merged: covers former 01003-22 (same continuation marked on HAY-PID-01003). | Engineering | MED
02005-13 | HAY-PID-02005 | E | Amine Filters F-1 / F-2 (400 GPM Amine Plant) | 2"-DR-0100-A1/A2 | — | Red continuation flag “2-DR-0100-A2 / HAY-PID-02016” at west end of drain header — correct drawing continuity on this sheet and HAY-PID-02006; verify field tie-in. Merged: covers former 02006-03 (same flag correction on the mate sheet). | Engineering | MED
02007-06 | HAY-PID-02007 | E | Amine Booster Pumps / Lean Solids Filter (P-1A/B, F-4) | 2"-DR-0100-A1 (east) | — | “Removed” + cloud + cut marks — drain header terminus piping removed in field; update drawing / confirm extent. | Engineering | MED
02012-11 | HAY-PID-02012 | F | Reboiler Skid H-1 / E-2 (400 GPM Amine Plant) | TCV E-2 station | — | Red “6"” at four station valves — verify actual valve sizes vs drawing; revise drawing or valves. (Eng. Question Q9) | Engineering | MED
02016-13 | HAY-PID-02016 | D | Catch Tank TK-2001 / TK-2002 (400 GPM Amine Plant) | TK-2002 header drops | — | Red routing clarifications (break squiggles at 1½"-PV-0002/0003-A2 × 1"-DA-0001-A2 / 1"-V-0094-A2 crossings) — verify as-built tie-in locations; update drawing. | Engineering | MED
03002-19 | HAY-PID-03002 | E | Vertical Scrubber MBF-1240A (55 MMSCFD Dehy Train-I) | 16" riser / 2"-DA-3003-F2-1.5"H-ET | — | “U/G” breaks + red trace to PCV-3001 — record underground transition; verify slop-header tie-in. | Engineering | MED
04001-10 | HAY-PID-04001 | E | Slop Tanks TK-41001…41004 | Drain headers | — | Red tie-in routing arrows into 2"-DA-3003-A2 / 4"-DA-3023-A2 / 2"-DA-2051-A2 junctions — verify as-built tie-in points; update drawing. | Engineering | MED
01003-23 | HAY-PID-01003 | E | Gas Scrubber (V-21001 / V-22001) | 3"-LH-0011-F2AS-1"H-ET | — | Red “3” size prefix added; flag sheet number struck, “02101” written — correct line size & continuation sheet on drawing. | Engineering | LOW
02001-16 | HAY-PID-02001 | F | Inlet Coalescing Filter S-1100 (400 GPM Amine Plant) | Outlet header flag | — | Sheet number struck, “01001” written — correct continuation flag. | Engineering | LOW
02015B-04 | HAY-PID-02015B | E | Side Stream Filter & Circulation Pumps (Hot Oil Unit-I) | SSI-300017 riser | — | Red trace at header crossing — crossing only (no connection); as-built clarification. | Engineering | LOW
08005-06 | HAY-PID-08005 | B | Anti Foam Tank TK-81011 / P-81011 | Distribution area | — | “Need to Correct Iso To Match P&ID” — revise piping isometric to match P&ID. | Engineering | LOW

## Vendor
Item No | P&ID | Rev | Sheet Title | Line / Equipment | Tag | Description & Action Required | Discipline | Priority | Status | Closed By | Date Closed
07003-05 | HAY-PID-07003 | E | FG Coalescing Filter F-71001 | DP installation | PDI-7101 | Cloud: “By Valley.” / “Missing” — install PDI-7101 assembly (manifold, ½" valves, tubing, 2"x½" taps); vendor “Valley” scope. | Vendor | HIGH

## BOM - Open Items
Qty | Description | Size | Rating | Material | Spec | Tag | Line Number | Notes / Punch Ref | PO No. | Status
2 | Flow element (restriction orifice) + FIT transmitter; terminate pulled wire | 2" line | V-PMS | V-PMS | A2 | FE/FIT-100, FE/FIT-101 | 2"-FG-2220-A2 / 2"-FG-2222-A2 | 02013-02 / 02115-02
1 | dP flow transmitter + 2 impulse manifold valve sets + tubing | — | V-PMS | — | F2 | FIT P-3 | 6"-LA-0025-F2 | 02011-14
1 | PDI dP assembly: manifold, ½" valves, tubing, 2"x½" taps (“By Valley” cloud) | ½" | V-PMS | V-PMS | — | PDI-7101 | F-71001 | 07003-05
1 | Regulator set: PCV + PI 0-150# + ¼" valve + tubing | ¼" | V-PMS | V-PMS | — | PCV-100A / PI-101A | V-100 overhead | 07002-10
1 | Blanket-gas regulator + ¼" fittings | ¼" | Set 30 PSIG | V-PMS | A2 | PCV-2001 | ¼"-GH-2001-A2 | 02015C-01 (Q5)
lot | ¼" blanket-gas tubing/branch, full run across 02015C + 02015D | ¼" | — | SS | — | — | ¼"-GH-2001-A2 | 02015C-02 (merged)
1 | Burner main-gas vent valve assembly: XV + FO orifice + vent gooseneck | 1½" | V-PMS | V-PMS | NG | XV-20003A | 1½"-80-NG-204 | 02015D-02
1 | Burner pilot-gas vent valve assembly: XV w/ solenoid + FO orifice + gooseneck | ¾" | V-PMS | V-PMS | NG | XV-20006A | ¾"-80-NG-205 | 02015D-03
1 | Control valve station w/ actuator — HOLD pending Q4 confirmation | 8" | V-PMS | V-PMS | C2 | FCV-45001A | 8"-HM-180 / -187 | 02015C-08 (long lead)
1 | Pipe loop/seal (gooseneck) assembly w/ plug/blind — HOLD pending Q4 | 8" | V-PMS | V-PMS | C2 | — | 8"-HM-187-C2-1.5"H | 02015C-07
1 | Pressure gauge assembly 0-160 PSIG w/ ½" NPT valve + siphon (shipped loose — locate) + ½" threadolet tap on 8" line | ½" | V-PMS | V-PMS | C2 | PI-27002A | 8"-HM-187-C2-1.5"H | 02015A-03 (merged)
1 | TI + thermowell | ¾" | V-PMS | V-PMS | A1 | TI/TW E-1D | 6"-LA-0022-A1 | 02006-01
2 | Pressure gauge (receiver top mount, with vent goosenecks ×3) | ½" | V-PMS | V-PMS | L2 | VS-70001 / VS-70002 / VS-70004 | — | 07001-02/-06/-10 (Q16)
1 | Check valve | 1" (H5S) | V-PMS | V-PMS | A00 | — | flash gas → 1"-V-0046-A2 | 03004-01
1 | Valve, CSO + tailpipe completion inside skid limits | 1" | V-PMS | V-PMS | A1 | — | 1"-V-0071-A1 | 02005-10/-11
1+ | Bleed ring set w/ bleed valves at orifice flanges | 1" 6000# | V-PMS | V-PMS | F2 | RO-3201A | MAF-3200A glycol drain | 03001-05
1 | Valved + plugged branch assembly (o-let, valve, plug) | 1" | 6000# taps | V-PMS | F2 | — | 8"-GH-3004-F2 | 03001-12
1 | Orifice-flange pair + 2 tap valves w/ bleeds (per field sketch) | 10" line | V-PMS | V-PMS | F2AS | — | 10"-GH-0026-F2AS | 02001-01 (Q2)
±9 | Valves, small-bore w/ caps or plugs (vents/bleeds/drains) | ½" | V-PMS | V-PMS | per line class | — | various | 01001-12, 01003-15, 02001-13, 02004-01, 02007-01/-02, 03002-05 (plugs), 02003-08*, 02004-13*
±7 | Valves w/ plugs (drains/vents) | ¾" | V-PMS | V-PMS | per line class | — | various | 02005-07/-08, 02008-04, 07003-07/-09, 07004-11 (plug)/-12
±10 | Valves (incl. 3 on 10"-LA-0017, 4 slop-tank drains, high-point vent on 8"-GH-3005) | 1" | V-PMS | V-PMS | per line class | — | various | 02009-02, 03002-02, 04001-06, 02012-07 (plug only)
±4 | Valves, ¼" (LCV stations, sensing line) | ¼" | V-PMS | V-PMS | DSS / per class | — | JT skid, blowcase | 07002-11/-12/-13, 07004-10 (07002-14 is ¾")
±7 | Valves (fuel-gas isolations ×2, KOD drains ×2, E-2 shell, anti-foam ×2) | 2" | V-PMS | V-PMS | per line class | — | various | 02012-10, 02013-01/-08, 02115-01/-09, 08005-04/-05
2 | Valve spec change GVTONT → CB10 (CSO) | 2" | V-PMS | V-PMS | CB10 | LG V-2A bridle | V-2 N8/N9 | 02004-06/-07
Field count | Gate valves to replace E-2 bridle valves (½", ¾" CB203; 2" CB10 CSO) | ½"–2" | V-PMS | V-PMS | — | LG/LT E-2A/B | E-2 bridles | 02012-01
2 | High-point vent assemblies (valve + plug; size unmarked, likely 1") | TBD | V-PMS | V-PMS | A2AS | — | 14"-AG-0033 / 14"-AG-0040 | 02013-05 / 02115-05
2 | Valves at KOD-301/302 top connections (size per connection) | TBD | V-PMS | V-PMS | — | KOD-301 / KOD-302 | — | 02013-07 / 02115-07
2 | Root valves + fittings for relocated PIT taps | ½" | V-PMS | V-PMS | G2 | PIT P-3A2 / PIT P-3D | 6"-LA-0025/0024-G2 | 02011-05/-08
1 | Valve + blind flange on stub | SB | V-PMS | V-PMS | F2AS | — | 16"-GH-0003-F2AS | 01001-16 (+ caps: -13/-17)
±2 | Reducers 4"x2" (bridle LIT mounts — verify) | 4"x2" | V-PMS | V-PMS | — | LIT-1001/-1002 | X-11001/X-12001 bridles | 01001-19/-20; 3"x2" verify 01001-37
4 | Reducer/transition, PVRV riser | 6"x4" | V-PMS | V-PMS | — | Enardo risers | TK-41001…41004 C3 | 04001-05
±4 | Blind flange (verify nozzles open) + gaskets/bolting | 4" | V-PMS | V-PMS | — | Slop tank C4 nozzles | TK-41001…41004 | 04001-07
1 | Swage + union/flange pair + valve | 1"x½" | V-PMS | V-PMS | F2AS | TK-2001 N4 drop | ½"-C-7001-F2AS | 02016-03
2 | New heat-traced drain lines: 2" pipe + fittings + 2" valves + heat trace/insulation | 2" | V-PMS | V-PMS | A2, 1.5"H-ET | — | 2"-DA-2101 + second line (Q18) | 04001-08/-09/-10
lot | Side-stream filter loop piping + branch fittings (size labels removed — verify 1") | 1" | V-PMS | V-PMS | — | SSI-30001A | 6"-40-TF-106 / -110 | 02015B-02…-05
lot | 2" NPT bypass-vent piping (BTEX), per markup — add to ISOs | 2" NPT | V-PMS | V-PMS | — | — | D vent → C outlet | 02014-03/-10 (Q6)
1 | Pipe shoe | 2" | — | CS | — | — | 2"-C-0201-F2AS-1.5"H-ET | 02001-07
2 | Replacement gauges if ranges wrong: PI 0-100#, TI 50-300F | — | — | — | — | PI T-2B / TI T-2B | T-2 nozzle C2 | 02009-05

## Engineering Questions
Q# | Topic | Question / Detail | Answer / Disposition | Answered By | Date
Q2 | Coalescing filter inlet (HAY-PID-02001) | the orifice/tap sketch remains but the “RO + FIT ?” question text was removed — confirm final metering disposition so 02001-01 can be executed. (Companion Q1 on the slug catcher was fully removed — see Section 7.)
Q4 | Hot Oil expansion tank (HAY-PID-02015C) | FCV-45001A station, the 8" gooseneck, and test point TP-E6 are all clouded “Doesn’t Exist – not on ISO’s”. Confirm scope, issue ISOs, and release the 8" control valve for procurement if required (long lead). (02015C-06/-07/-08)
Q5 | Blanket gas (HAY-PID-02015C) | PCV-2001 station still hatched as not installed; the earlier field-deviation note (“¾" valve on adjacent 3" FG pipe”) was removed. Install per design or formalize the deviation. (02015C-01)
Q6 | BTEX bypass vent (HAY-PID-02014) | 2" NPT vent piping still clouded “Missing / Not on ISOs / Skid limits” — issue ISO/routing. (02014-03/-10)
Q9 | TCV E-2 station sizes (HAY-PID-02012) | red “6"” marks remain at four station valves — verify installed sizes vs drawing. (02012-11)
Q12 | PSV-3200A nozzle (HAY-PID-03001) | red 1½" vs printed 1"x1" NPT still marked — confirm connection size. (03001-03)
Q13 | “Doesn’t exist” valves (HAY-PID-02007 / 02005) | printed 1" C1203F LSD valve, 6" CV10 lean-amine valve, and the PSV F-2 tailpipe 1" CSO remain marked absent — install per drawing or revise drawings. (02007-03/-05, 02005-10/-11)
Q16 | Air-system relief redesign (HAY-PID-07001) | the PSV-7001/-7003/-7005 removals with replacement vents + relocated PIs remain fully marked. Confirm the redesign is engineered and code-compliant BEFORE removing relief devices. (07001-01…-11)
Q18 | Slop-tank drain lines (HAY-PID-04001) | both red-drawn 2" lines remain; one tie-in reference still blank, the other line number partially legible — assign line numbers/sheet refs. (04001-08/-09/-10)
Q19 (new) | Blowcase open drain (HAY-PID-07004) | cloud now reads “Where to / No ISO” — define the drain destination and issue the ISO, then tie in. (07004-13)

## Procurement
Priority | Order | Qty | Notes | PO No. | Status
CRITICAL | FE/FIT-100 & -101 orifices + transmitters; FIT P-3 + manifolds | 3 sets | wire already pulled at VCU meters
CRITICAL | Blanket-gas: PCV-2001 + ¼" tubing/fittings; burner vent assemblies XV-20003A / XV-20006A | 1+lot+2 | hot-oil startup blockers
CRITICAL | FCV-45001A 8" CV station; 8" gooseneck assembly | 1+1 | HOLD Q4 — release scope first; long lead
HIGH | Valve package: ¼"×4, ½"×9±, ¾"×7±, 1"×10±, 2"×7±, 2" CB10 ×2, 1" H5S check, 1" CSO, KOD-top valves ×2, HP-vent assemblies ×2, gate-valve swap (field count) | ~48 | order to line-class specs — V-PMS
HIGH | PDI-7101 assembly; PCV-100A/PI-101A set; PI-27002A gauge assy + ½" threadolet; TI/TW E-1D; receiver PIs ×2; bleed rings; orifice-flange pair + tap valves (Q2) | — | PI-27002A is shipped-loose — locate first
HIGH | Piping lots: 2" HT slop drains ×2 (+heat trace), 1" side-stream loop, 2" NPT BTEX vent, reducers (6"x4" ×4, 4"x2" ±2, 1"x½"), 4" blinds ±4, 1 shoe | lot | Q18/Q6 refs to be assigned
MED | Replacement gauges PI 0-100# / TI 50-300F (if range verification fails) | 2 | 02009-05

## Disposition (Rev 0 closed)
Item No | P&ID | Description (Rev 0) | Disposition | Rev 0 Priority
01001-01 | HAY-PID-01001 | “Install (Inlet/outlet)” — install the two 1" IA take-off valves/drops feeding PCV-1001 & PCV-1002. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-02 | HAY-PID-01001 | “Install Platforms (2)” — install two access platforms. | CLOSED — mark not on current redline set (2026-08-12) | MED
01001-03 | HAY-PID-01001 | “Wire” — pull/terminate instrument wiring. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-04 | HAY-PID-01001 | “Rotate Handle Due South” — reorient valve handle. | CLOSED — mark not on current redline set (2026-08-12) | MED
01001-05 | HAY-PID-01001 | “Roll after PSSR” — red-drawn spectacle blind at inlet 16" CSO valve; roll to open position after PSSR. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
01001-06 | HAY-PID-01001 | “Roll after PSSR” — second red-drawn spectacle blind on outlet gas header to 16" launcher; roll after PSSR. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
01001-07 | HAY-PID-01001 | Red-drawn 1" valve w/ plug teed off outlet header at the blind — install. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-08 | HAY-PID-01001 | “U/G” at OUTLET GAS HEADER TO 16" LAUNCHER flag — record underground transition (as-built). | CLOSED — mark not on current redline set (2026-08-12) | LOW
01001-09 | HAY-PID-01001 | “U/G” break-arc right of ESD station — record underground segment (as-built). | CLOSED — mark not on current redline set (2026-08-12) | LOW
01001-10 | HAY-PID-01001 | “Wire + Tubing” — complete wiring and pneumatic tubing at inlet ESD valve station. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01001-11 | HAY-PID-01001 | “Wire + Tubing” — complete wiring and tubing at outlet ESD valve station. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01001-14 | HAY-PID-01001 | “Confirm” — verify relief set pressure 1430 PSIG (fire) against nameplate/certs. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01001-15 | HAY-PID-01001 | “Confirm” — verify relief set pressure (X-12001) against nameplate/certs. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01001-18 | HAY-PID-01001 | “Wire” — pull/terminate instrument wiring. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-25 | HAY-PID-01001 | “Missing” (×2, pink highlight) — 4" cone strainer and 4" FD (“SIZE HOLD”) on NC bypass not installed. Install; engineering to release size hold. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01001-26 | HAY-PID-01001 | “Missing” (×2) — same missing 4" cone strainer + FD (SIZE HOLD) at X-12001 letdown bypass. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01001-27 | HAY-PID-01001 | “Wire” — complete loop wiring. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-28 | HAY-PID-01001 | “Wire” — complete loop wiring incl. level safety switches. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01001-29 | HAY-PID-01001 | Red slashes across dashed signal lines + “Wire” — pull signal wiring. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-30 | HAY-PID-01001 | “Install pipe shoes (3)” — install three pipe shoes. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-31 | HAY-PID-01001 | “Grout + Ground” — grout saddles and install grounding. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-32 | HAY-PID-01001 | “Add valves (2) – SC#1 + SC#2” — add one IA isolation valve per slug catcher. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-34 | HAY-PID-01001 | Large hatched cloud over meter-run instruments + sketch of orifice run: “Installing Orifice Meter or RO + FIT ?” — engineering to confirm metering design; install per answer. (Eng. Question Q1) | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-35 | HAY-PID-01001 | “Add” — red-drawn valves: 2" (×2) + ½" (×1) — install. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-36 | HAY-PID-01001 | “U/G” break-arcs — record underground segments (as-built). | CLOSED — mark not on current redline set (2026-08-12) | LOW
01001-39 | HAY-PID-01001 | Red cloud + curved arrow — relocate PT-1001B tap to adjacent riser. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-40 | HAY-PID-01001 | Red/pink highlight along line to Dehy Train I & II + “U/G” — record underground routing (as-built). | CLOSED — mark not on current redline set (2026-08-12) | LOW
01001-41 | HAY-PID-01001 | “Wire + Tubing” — complete wiring/tubing in blowdown drain area. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01001-42 | HAY-PID-01001 | “wire” — wire position switches on ESD blowdown valve. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01001-43 | HAY-PID-01001 | “U/G” + break-arc — record underground transition (as-built). | CLOSED — mark not on current redline set (2026-08-12) | LOW
01003-01 | HAY-PID-01003 | “Missing U-bolt (2)” — install two 10" U-bolts at inlet ESD station. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-02 | HAY-PID-01003 | “Secure 2 U-bolt / Missing 1 U-bolt” — secure two existing U-bolts, install one missing. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-03 | HAY-PID-01003 | “Tubing” — complete pneumatic tubing at solenoid/quick-connect. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01003-04 | HAY-PID-01003 | “Add Gate Valve” — install 2" gate valve in bypass leg of inlet station. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-05 | HAY-PID-01003 | “Add platform (AR)” — access platform as required. | CLOSED — mark not on current redline set (2026-08-12) | MED
01003-06 | HAY-PID-01003 | “Missing” + pink highlight over ENTIRE PSV package (PSV, 3" vent to ATM, 1½"-GH-0030-F2AS inlet, ½" bleed) — supply & install complete relief assembly (set per V-22001, 1435 PSIG design). | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
01003-08 | HAY-PID-01003 | Red “LT” circle + “3X2” capped-stub sketch — mount LIT-1004 on 3"x2" reducer with cap. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-13 | HAY-PID-01003 | “Torque” — torque manway bolting to spec. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-14 | HAY-PID-01003 | “Ground” — install vessel grounding. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-16 | HAY-PID-01003 | “Missing 3" blind + ½" valve” — install 3" blind flange (w/ gasket & bolting) and ½" valve at bridle drain below lower nozzle. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01003-17 | HAY-PID-01003 | “Shim pipe shoe” — shim shoe downstream of V-22001 outlet valve. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-18 | HAY-PID-01003 | “Missing pipe shoe + shim” — install shoe + shim at FC letdown station. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-19 | HAY-PID-01003 | “lift pipe & put shoe on beam” (1) — reset shoe onto beam. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-20 | HAY-PID-01003 | “lift pipe & put shoe on beam” (2) — reset shoe at letdown station. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
01003-21 | HAY-PID-01003 | “Tubing + lower latching switch to grade (Tubing)” — run tubing; relocate latching switch to grade. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
01003-22 | HAY-PID-01003 | Red note “2"-LH-0009-F2AS / P&ID-02001” + circled 1 — line continues to HAY-PID-02001; update drawing continuity (mate of 02001-14). | MERGED — duplicate of 02001-14 | LOW
02001-02 | HAY-PID-02001 | “Remove Wood block” — remove shipping block from 10" FC valve. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02001-03 | HAY-PID-02001 | “Missing” + pink highlight over full assembly (PSV set 1440 PSIG fire, 2" TO ATM tail, 2"x1" reducer, ½" bleed, 2" CSO block) — supply & install. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
02001-04 | HAY-PID-02001 | “Conduit Installed, Need to pull wire” — pull & terminate wire to heated enclosure/stream splitter. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02001-05 | HAY-PID-02001 | “Rotate Due West” — reorient controller. | CLOSED — mark not on current redline set (2026-08-12) | MED
02001-06 | HAY-PID-02001 | “Rotate Due East” — reorient controller. | CLOSED — mark not on current redline set (2026-08-12) | MED
02001-08 | HAY-PID-02001 | “Tubing” — complete pneumatic tubing. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02001-09 | HAY-PID-02001 | “Tubing” — complete tubing on vertical 2" run/header connections. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02001-10 | HAY-PID-02001 | “shoe” — install one pipe shoe. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02001-11 | HAY-PID-02001 | “Ground vessel + skid” — install grounding. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02001-12 | HAY-PID-02001 | “Grout” — grout vessel base. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02001-15 | HAY-PID-02001 | “U/G” + break — record underground segment of gas outlet header (as-built). | CLOSED — mark not on current redline set (2026-08-12) | LOW
02002-01 | HAY-PID-02002 | “Confirm” — verify set pressure 1440 PSIG (fire) against nameplate. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02002-02 | HAY-PID-02002 | “Missing” + pink highlight — install 2" PSV vent tailpipe to ATM. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
02002-03 | HAY-PID-02002 | “Add Brace” — brace/support the vent tailpipe. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02002-04 | HAY-PID-02002 | “Missing” + pink highlight along full ½" SS tubing run (top to bottom tap) — install dP impulse tubing (~55 ft + fittings). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02002-05 | HAY-PID-02002 | “Secure U-bolt” — secure U-bolt on lean amine line near N3. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02002-06 | HAY-PID-02002 | “Torque after Inspection” — torque lower manway after internal inspection. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02002-07 | HAY-PID-02002 | “Rotate 90° so Valve is Horizontal” — reorient inlet valve. | CLOSED — mark not on current redline set (2026-08-12) | MED
02002-09 | HAY-PID-02002 | “Grout” — grout baseplate. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02002-10 | HAY-PID-02002 | “Confirm” — verify restriction orifice bore 1.5" per datasheet. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02003-01 | HAY-PID-02003 | “Confirm” — verify set pressure 1440 PSIG (fire, 1D2 orifice) against nameplate. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02003-02 | HAY-PID-02003 | “Add Brace” — brace 2" atmospheric vent riser. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02003-04 | HAY-PID-02003 | “Torque” — torque manway cover. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02003-05 | HAY-PID-02003 | “Grout” — grout vessel base. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02003-06 | HAY-PID-02003 | “Install platform” — access platform for level valve/instrument area. | CLOSED — mark not on current redline set (2026-08-12) | MED
02003-07 | HAY-PID-02003 | “Missing” + pink highlight over printed “CHOKE NIPPLE / 3/8" BORE” — install 1" choke nipple, 3/8" bore, on condensate to flash tank. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02003A-01 | HAY-PID-02003A | “Tubing” — install pneumatic tubing from TY AC-4 to automated louver actuator. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02004-02 | HAY-PID-02004 | “Confirm” — verify set pressure 150 PSIG (6R8) against nameplate. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02004-03 | HAY-PID-02004 | Red “1"” + cap mark — change upstream bleed valve to 1", cap outlet. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02004-04 | HAY-PID-02004 | Printed ¾" struck, “1"” + cap — change downstream bleed to 1", cap outlet. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02004-08 | HAY-PID-02004 | “Secure Wire” (two arrows) — secure wire/heat-trace along bridle standpipe. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02004-09 | HAY-PID-02004 | “Wire” — complete/terminate wiring at transmitter. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02004-11 | HAY-PID-02004 | “Grout (2)” — grout both saddles. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02004-12 | HAY-PID-02004 | “Install Platform” — access platform at level-instrument end. | CLOSED — mark not on current redline set (2026-08-12) | MED
02005-01 | HAY-PID-02005 | “Add 2" valve / (CSO)” — install 2" CSO valve at skid-edge vent to drain system. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02005-02 | HAY-PID-02005 | “Confirm” — verify set 150 PSIG (fire, 1½F2). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02005-03 | HAY-PID-02005 | “Missing ½" Tubing” + pink highlight — install ½" SS tubing run (check valve to ½"-V-0060-A1 tie-in). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02005-04 | HAY-PID-02005 | Red-drawn 2" valve w/ X at skid boundary above rich-amine entry — pictorial for 02005-05; install with it. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02005-05 | HAY-PID-02005 | “Add 2" check + Block” — install 2" check valve + 2" block valve at scope break (flush/aux connection). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02005-06 | HAY-PID-02005 | “Confirm” — verify orifice bore 2.0". | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02005-09 | HAY-PID-02005 | “Tighten ½" Tubing Ferrule” — tighten compression fitting. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02006-03 | HAY-PID-02006 | Red “2-DR-0100-A2” filled into blank continuation flag over HAY-PID-02005 — correct drawing (mate of 02005-13). | MERGED — duplicate of 02005-13 | LOW
02007-04 | HAY-PID-02007 | “plug” — install ½" plug on open connection below valve near PSV F-4. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02007-07 | HAY-PID-02007 | “Remove 2x4 & Adjust support” — remove temporary lumber, install permanent support. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02008-01 | HAY-PID-02008 | “Add shoes (4)” — install four pipe shoes on antifoam line at skid-edge run. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02008-02 | HAY-PID-02008 | “Missing” + pink highlight — install MPLX-supplied 2" static mixer X-2 (Note 1). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02008-03 | HAY-PID-02008 | Pink highlight on note “1) SUPPLIED BY MPLX.” — cross-reference to 02008-02 (locate MPLX-supplied material). | CLOSED — mark not on current redline set (2026-08-12) | MED
02008-05 | HAY-PID-02008 | Red “2" / Add” + drawn gate valve — install 2" block valve at Skid #1 limit crossing. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02009-01 | HAY-PID-02009 | “Confirm” — verify pilot-operated PSV set 100 PSIG. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02009-03 | HAY-PID-02009 | “Missing” — install ½" CB203 vent (top) and ½" CB203 drain (bottom) on gauge bridle. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02009-04 | HAY-PID-02009 | Red “CSC” beside printed CSO — car-seal-closed per field; reconcile CSO vs CSC with engineering. (Eng. Question Q10) | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02009-06 | HAY-PID-02009 | Red “CSC” — same car-seal reconciliation at bottom drain. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02009-07 | HAY-PID-02009 | “Torque After Inspection” — torque after internal inspection. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02009-08 | HAY-PID-02009 | “Grout” — grout base ring. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02009-09 | HAY-PID-02009 | “Install platform” — access platform at reflux line/valve area. | CLOSED — mark not on current redline set (2026-08-12) | MED
02009-10 | HAY-PID-02009 | “Electrical Cover” — install missing transmitter housing cover. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02009-11 | HAY-PID-02009 | “Tubing” — install instrument air tubing (I/P to valve). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02009-12 | HAY-PID-02009 | “Install platform” — access platform at 8" acid gas control station. | CLOSED — mark not on current redline set (2026-08-12) | MED
02010-01 | HAY-PID-02010 | “Missing” + pink highlight — install PSV AC-1 (2"x1½", set 150 PSIG, check-valve-failure case) and relief route via 3"-V-0102-A2. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
02010-02 | HAY-PID-02010 | Red “CSO” — car-seal-open the isolation valve. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02010-03 | HAY-PID-02010 | “Tubing” — install I/P-to-louver-actuator tubing. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02010-04 | HAY-PID-02010 | “Tubing” — install tubing to AC-2 louver actuator. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02010-05 | HAY-PID-02010 | “Cleanup Area” — housekeeping. | CLOSED — mark not on current redline set (2026-08-12) | MED
02011-01 | HAY-PID-02011 | Red “3" / Add” + drawn gate valve — install 3" block valve before the drain-system flag. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02011-02 | HAY-PID-02011 | “Discharge Pressure? Goes to 165# MAWP Vessel” — engineering must verify 1440 PSIG relief routing to low-pressure drain vessel. (Eng. Question Q3) | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
02011-03 | HAY-PID-02011 | “Confirm” — verify pilot-operated PSV set 1440 PSIG (blocked flow). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02011-04 | HAY-PID-02011 | “Missing” + pink highlight — install ½"x⅜" SS tubing run to P-3A discharge valve string. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02011-06 | HAY-PID-02011 | “Wire” + cloud — pull/terminate wiring. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02011-07 | HAY-PID-02011 | “Wire” — wire loop. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02011-09 | HAY-PID-02011 | “Wire” — wire loop. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02011-10 | HAY-PID-02011 | “Bolt up After Alignment” — final bolt-up of 4" 900# discharge spool and 6" 150# suction flange after alignment. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02011-11 | HAY-PID-02011 | “Bolt up After Alignment” — same at P-3B. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02011-12 | HAY-PID-02011 | “Valve Handle” — install missing handwheel at P-3A discharge block. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02011-13 | HAY-PID-02011 | “Valve Handle” — install missing handwheel at P-3B discharge block. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02011-15 | HAY-PID-02011 | “Confirm” — verify orifice bore 3.5" per datasheet. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02012-02 | HAY-PID-02012 | “Platform Grating” — install missing grating at reboiler platform. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02012-03 | HAY-PID-02012 | “Missing” + cloud — install 2"x1" thermal PSV, set 150 PSIG. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
02012-04 | HAY-PID-02012 | “Wire” — wire both level transmitters. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02012-05 | HAY-PID-02012 | “Wire” — wire temperature transmitter. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02012-06 | HAY-PID-02012 | “Secure” — support/secure 1" drain line. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02012-08 | HAY-PID-02012 | “Grout supports” — grout at containment. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02012-09 | HAY-PID-02012 | “Shim pipe shoes (3)” — shim three shoes at hot-oil control station. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02012-12 | HAY-PID-02012 | “Wire” — wire fuel-gas metering cluster. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02013-03 | HAY-PID-02013 | “Remove plastic/wood” — remove shipping covers from stack outlet. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02013-04 | HAY-PID-02013 | “Wire (By Zeeco)” — flame scanner/rod wiring to JB-101, vendor scope. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02013-06 | HAY-PID-02013 | “Missing wire pulled” + pink highlight — install PSV-301 (set 100 psig, vent SIZE HOLD), PG-301 + ½" MNV, full level-switch stack; terminate wiring. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
02013-09 | HAY-PID-02013 | “14" Add” + drawn valve + pink highlight — install 14" 150# valve d/s of XV-301. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02013-10 | HAY-PID-02013 | “Missing wire pulled” + pink highlight — install PSV-401 (set 15 psig), PG-401, level-switch stack; terminate wiring. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
02013-11 | HAY-PID-02013 | “Add / 3"” + drawn valve d/s of XV-401 — install 3" 150# valve. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02013-12 | HAY-PID-02013 | “Grout (2)” — grout two base points. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02013-13 | HAY-PID-02013 | “Grout” — grout base. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02013-14 | HAY-PID-02013 | “wire + ground” — power wiring and grounding. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-01 | HAY-PID-02014 | “Tubing” — install ¼" fuel-gas supply tubing run. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-02 | HAY-PID-02014 | “Missing Tubing” + pink highlight — install tubing PY-1001A → diffuser at condenser inlet. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-04 | HAY-PID-02014 | “Add 2" Valve (CSO)” — install at condenser vapor outlet near PSV-1100A. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-05 | HAY-PID-02014 | Red X + pink highlight — install PCV-2002A regulator (set 100 psig) with tubing (see -11). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-06 | HAY-PID-02014 | “1" Add valve” — install 1" valve in flame-arrestor branch. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-07 | HAY-PID-02014 | “3" Add valve” — install 3" valve at skid edge. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-08 | HAY-PID-02014 | “Missing” + pink highlight — install gauge glass + 2×¾" isolation, ½" vent, ½" drain valves. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-09 | HAY-PID-02014 | “plug” — plug open 1½" connection. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02014-11 | HAY-PID-02014 | “Missing Tubing” — install ½" tubing riser + header to ABV-1000A and ½"-PV-2054-A2. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-12 | HAY-PID-02014 | “Wire” — wire actuated 3-way valve. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-13 | HAY-PID-02014 | “Tubing” — install tubing for reset/vent circuit to B outlet. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02014-14 | HAY-PID-02014 | “2" Add Valve” — install 2" valve in drain to slop tank. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02115-03 | HAY-PID-02115 | “Remove Wood/Plastic” — remove shipping covers. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02115-04 | HAY-PID-02115 | “wire (By Zeeco)” — flame scanner wiring to JB-101, vendor scope. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02115-06 | HAY-PID-02115 | “Missing” + pink highlight — install PSV-302 (set 100 psig, vent SIZE HOLD), PG-302 + ½" MNV, level-switch stack. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
02115-08 | HAY-PID-02115 | “Missing” — install gauge glass + 2×1" BAV isolation valves + ½" vents. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02115-10 | HAY-PID-02115 | “Install U-bolt” — install 14" U-bolt on vent header. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02115-11 | HAY-PID-02115 | “14" Add” + drawn valve d/s of XV-302 — install 14" 150# valve. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02115-12 | HAY-PID-02115 | “Missing” + pink highlight — install PSV-402 (set 15 psig) + level-switch stack. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
02115-13 | HAY-PID-02115 | “3" Add” + drawn valve d/s of XV-402 — install 3" 150# valve. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02115-14 | HAY-PID-02115 | “wire (pulled)” — terminate TE-402/403 (TAHH @ 250°F). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02115-15 | HAY-PID-02115 | “Install 1" IA Plug This Area” — locate open IA connection, install 1" plug. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02115-16 | HAY-PID-02115 | “Grout (2)” — grout two base points. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02115-17 | HAY-PID-02115 | “Grout” — grout base. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02115-18 | HAY-PID-02115 | “Wire + Ground” — power wiring and grounding. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02015A-01 | HAY-PID-02015A | “Wire” — wire inlet temperature loop. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02015A-02 | HAY-PID-02015A | “Wire” — wire control thermocouple (TIC-27002A loop). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02015A-04 | HAY-PID-02015A | “Missing PI, Requires Tap on 8"” — hot-tap/weld ½" threadolet on 8" outlet line for the PI. (with -03) | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02015A-05 | HAY-PID-02015A | “Torque (By Sigma Thermal ?)” — torque three 4" 300# orifice-flange sets; confirm responsibility. (Eng. Question Q8) | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02015A-06 | HAY-PID-02015A | “Grout + ground” — grout base, install grounding. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02015A-07 | HAY-PID-02015A | “Shim Blow Motor & Remove straps” — shim motor, remove shipping straps. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02015A-08 | HAY-PID-02015A | “Missing 2" seal off cover” — install. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02015A-09 | HAY-PID-02015A | “Remove instrumentation plastic” — remove shipping wrap. | CLOSED — mark not on current redline set (2026-08-12) | MED
02015A-10 | HAY-PID-02015A | “Missing 2-1" & 2-2" electrical Covers” — install two 1" and two 2" covers. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02015A-11 | HAY-PID-02015A | “Bolt up Blower 8" (by Sigma Thermal ? Need Garlock gasket)” — bolt up; procure 8" Garlock gasket; confirm responsibility. (Eng. Question Q8) | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02015A-12 | HAY-PID-02015A | Pink highlight on “SHIPPED LOOSE BY SIGMA THERMAL AND INSTALLED IN PIPING BY MPLX” — locate all shipped-loose items and install. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02015B-01 | HAY-PID-02015B | Red tick at tee — marks tap point for 1" side-stream supply (see -02). | CLOSED — mark not on current redline set (2026-08-12) | MED
02015C-04 | HAY-PID-02015C | “Confirm” — verify set 25 PSIG. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02015C-05 | HAY-PID-02015C | “Wire” — wire low-level interlock (wiring by MPLX, Note 6). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
02015D-01 | HAY-PID-02015D | “Missing (see 2015C)” + pink highlight — install fuel-gas blanket branch off 3"-GH-7008-A2 (pairs with 02015C-01/-02). | MERGED — duplicate of 02015C-02 | CRITICAL
02016-01 | HAY-PID-02016 | “upsize to 1" and/or support” — upsize condensate line to 1" and/or add supports; engineering to confirm. (Eng. Question Q11) | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02016-02 | HAY-PID-02016 | “Add” + drawn valve before drop to N4 — install isolation valve. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02016-04 | HAY-PID-02016 | “Install” — install pressure indicator. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02016-05 | HAY-PID-02016 | “3" Add” + drawn valve — install 3" valve on vent header drop. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02016-06 | HAY-PID-02016 | “Add” — install external level-gauge bridle: standpipe, gauge, ½" top + ½" bottom isolation valves. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02016-07 | HAY-PID-02016 | “Delete” + hatched cloud — remove from scope (with ¾" nozzle). | CLOSED — mark not on current redline set (2026-08-12) | MED
02016-08 | HAY-PID-02016 | Hatched cloud — delete (replaced by external bridle -06). | CLOSED — mark not on current redline set (2026-08-12) | MED
02016-09 | HAY-PID-02016 | Hatched cloud over small capped fitting — delete. | CLOSED — mark not on current redline set (2026-08-12) | MED
02016-10 | HAY-PID-02016 | Red-drawn 2" line: “Elevate, Keep within Containment, Add Truck Connection” — install elevated 2" truck-out w/ 2" valve + capped truck connection. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02016-11 | HAY-PID-02016 | “Missing” + pink highlight — install level gauge (½"×½"). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
02016-12 | HAY-PID-02016 | Red-drawn pump-out w/ “½"x2"” swage: “Elevate & Keep within Containment” — install per sketch (2" pipe, valve, cap). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-01 | HAY-PID-03001 | “Add Isolation Valves” — install ¾" isolation valve at top connection. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-02 | HAY-PID-03001 | Same note — install ¾" isolation valve at bottom connection. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-04 | HAY-PID-03001 | Printed bore struck; red “0.1505"” — orifice bore 0.1505"; procure/verify plate. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-06 | HAY-PID-03001 | “Secure” — secure/support atmospheric vent stack (SIZE HOLD noted). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-07 | HAY-PID-03001 | “Add Isolation Valves” — install ¾" isolation valve at upper tap. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-08 | HAY-PID-03001 | Same note — install ¾" isolation valve at lower tap (nozzle G). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-09 | HAY-PID-03001 | “Grout” — grout base. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-13 | HAY-PID-03001 | Bore struck; red “0.1505"” — orifice bore 0.1505"; procure/verify plate. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-14 | HAY-PID-03001 | Red-drawn IA detail: 1" plugged tee valve + “plug”, 1" end valve — install per sketch. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03001-15 | HAY-PID-03001 | “U-bolt” — install U-bolt supports on IA supply run. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-01 | HAY-PID-03002 | “Confirm” — verify set 1440 PSIG (E orifice). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
03002-03 | HAY-PID-03002 | “Missing / Need RO + FIT / Wire pulled” + pink highlight — install orifice plate + FIT-1240A; terminate pulled wire. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
03002-04 | HAY-PID-03002 | “Wire” — wire temperature element. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-06 | HAY-PID-03002 | “Add valve” — install ½" gauge isolation valve. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-07 | HAY-PID-03002 | “Torque” — torque manway. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-08 | HAY-PID-03002 | “Hookup (Wire or Tubing?)” — complete hookup; engineering to confirm electric vs pneumatic. (Eng. Question Q14) | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-09 | HAY-PID-03002 | “Add Isolation valves” — install ¾" valve, upper connection. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-10 | HAY-PID-03002 | Same — install ¾" valve, lower connection. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-11 | HAY-PID-03002 | “Do we Need this platform?” — RFI to engineering on service platform. (Eng. Question Q15) | CLOSED — mark not on current redline set (2026-08-12) | MED
03002-12 | HAY-PID-03002 | “Grout” — grout base. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-13 | HAY-PID-03002 | “XX” bore struck; red “0.7394"” — orifice bore 0.7394"; procure/verify plate. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-14 | HAY-PID-03002 | Same — bore 0.7394"; procure/verify plate. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-15 | HAY-PID-03002 | “1" Add valve (CSO)” — install 1" CSO valve on PSV-3001 vent to catch tank. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
03002-16 | HAY-PID-03002 | “Add ½" bleed valve (CSO)” — install at 1" CSO isolation (SIZE HOLD noted). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-17 | HAY-PID-03002 | Red cloud over analyzer package + arc to 16" corner — complete GC package hookup (with -18). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03002-18 | HAY-PID-03002 | “Missing Tap + Tubing” — install analyzer probe tap (GENIE probe) + sample tubing to GC. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03003-01 | HAY-PID-03003 | “Missing” + pink highlight — install thermowell + temperature indicator. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03003-02 | HAY-PID-03003 | “plug” — install 1" plug in BTEX vapour glow plug connection. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03003-03 | HAY-PID-03003 | “Add Isolation Valves” — install both 1"x½" gauge isolation valves. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03004-02 | HAY-PID-03004 | “Add Isolation valves” — install both ½" tubing-gauge isolation valves. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03004-03 | HAY-PID-03004 | “Add Isolation Valves” — install both isolation valves. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03004-04 | HAY-PID-03004 | “Add valve. (CSO)” “1"” — install 1" CSO valve on charcoal-filter PSV discharge (set 125 psig). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
03004-05 | HAY-PID-03004 | “Add Valve (CSO)” “1"” — install 1" CSO valve on sock-filter PSV discharge. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
03004-07 | HAY-PID-03004 | “Add valve (CSO)” “1"” — install 1" CSO valve on PSV-1400 discharge. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
03004-08 | HAY-PID-03004 | “1½" Add Valve” — install 1½" isolation valve at Cimarron/MPLX scope break (rich glycol). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
03004-09 | HAY-PID-03004 | “1½" Add Valve” — install 1½" isolation valve at scope break (lean glycol). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
04001-01 | HAY-PID-04001 | “Wire” — wire level transmitter + switch. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
04001-02 | HAY-PID-04001 | “Wire” — wire. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
04001-03 | HAY-PID-04001 | “Wire” — wire. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
04001-04 | HAY-PID-04001 | “Wire” — wire. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
04001-11 | HAY-PID-04001 | “Remove wood” — remove dunnage from containment. | CLOSED — mark not on current redline set (2026-08-12) | MED
04001-12 | HAY-PID-04001 | “Wire” — wire ESD valve solenoid + position switches. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
04001-13 | HAY-PID-04001 | “Ground All Tanks” — ground/bond TK-41001–41004. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
04001-14 | HAY-PID-04001 | “Missing” — supply & install grounding station assembly. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
04001-15 | HAY-PID-04001 | “Install Enviro Box” — install environmental containment box at 4" valve/spec-blind station. | CLOSED — mark not on current redline set (2026-08-12) | MED
07001-04 | HAY-PID-07001 | Red “1"” + magenta — install/upsize drain train to 1". | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-08 | HAY-PID-07001 | Red “1"” — upsize drain train to 1". | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-12 | HAY-PID-07001 | Red “1"” — upsize drain train to 1". | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-13 | HAY-PID-07001 | “Missing plugs” — install NPT plugs in open spare nozzles. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
07001-14 | HAY-PID-07001 | “Missing” + large cloud — install COMPLETE relief station: PSV-7002 (1"x2", set 121 psig), 2" CSO block, 2"x1" reducer, ½" bleed, vent pipe. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
07001-15 | HAY-PID-07001 | “Missing” — install four missing ½" valves at regulator manifold (set 110 psig). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-16 | HAY-PID-07001 | “3" U-bolt” — install at air distribution flag. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-17 | HAY-PID-07001 | “Ground 3 Vessels + Building” — install grounding. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-18 | HAY-PID-07001 | “Missing ½" Tubing” + magenta — install tubing: skid boundary to timer drains, below VS-70004, and to TK-70001 hookup. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-19 | HAY-PID-07001 | Red cloud + strikes over “HOSE CONNECTION”/2" valve/2"-IA-7042-L2 — remove hose connection; update drawing. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-20 | HAY-PID-07001 | “Missing” + magenta — install level gauge + two 1" isolation valves. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-21 | HAY-PID-07001 | “Elevate & Keep Within Containment” “2"” — install elevated 2" line w/ valve, end hook inside containment. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07001-22 | HAY-PID-07001 | Red “1X2” + drawn expander at containment boundary — install 1"x2" swage. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07002-01 | HAY-PID-07002 | “Add Support @ Double 90°” — install pipe support at vertical double-elbow drop (near PI/PCV-7101/7102). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07002-02 | HAY-PID-07002 | Red cloud + “✱✱” — all four methanol pumps flagged; see Q7 (meaning of asterisks to be confirmed). | CLOSED — mark not on current redline set (2026-08-12) | MED
07002-03 | HAY-PID-07002 | Red “✱” at discharge assembly — pump flagged for attention (Q7). | CLOSED — mark not on current redline set (2026-08-12) | MED
07002-04 | HAY-PID-07002 | Red “✱” — flagged (Q7). | CLOSED — mark not on current redline set (2026-08-12) | MED
07002-05 | HAY-PID-07002 | Red “✱” — flagged (Q7). | CLOSED — mark not on current redline set (2026-08-12) | MED
07002-06 | HAY-PID-07002 | Red “✱” — flagged (Q7). | CLOSED — mark not on current redline set (2026-08-12) | MED
07002-07 | HAY-PID-07002 | Cloud: “Connect, IA Currently Hooked up Here” — instrument air is wrongly connected to the methanol inlet port; remove IA, connect methanol supply. Cross-connection hazard. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
07002-08 | HAY-PID-07002 | “Connect + support OVHD 1" IA” — run and support 1" overhead instrument-air line to the skid (correct IA landing). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
07002-09 | HAY-PID-07002 | Red “✱✱” at header — cross-reference flag (with -02/-08); confirm intent. | CLOSED — mark not on current redline set (2026-08-12) | MED
07003-01 | HAY-PID-07003 | “Missing” + pink highlight — install PSV vent tailpipe TO ATM (SIZE HOLD — engineering to release). | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
07003-02 | HAY-PID-07003 | “Confirm” — verify set 275 PSIG (fire, 1D2). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
07003-03 | HAY-PID-07003 | “Add support” — support 2" inlet line. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07003-04 | HAY-PID-07003 | “Add Support (2)” — two supports upstream of N1. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07003-10 | HAY-PID-07003 | “XX” struck; red “0.1031"” — orifice bore 0.1031"; procure/verify plate. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07003-11 | HAY-PID-07003 | Same — bore 0.1031"; procure/verify plate. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07003-12 | HAY-PID-07003 | “wire” — wire meter-run instrumentation (heated enclosure). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07003-13 | HAY-PID-07003 | “Install Platform” — access platform. | CLOSED — mark not on current redline set (2026-08-12) | MED
07004-03 | HAY-PID-07004 | “1" Add” + drawn valve at battery limit — install 1" valve. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07004-04 | HAY-PID-07004 | “Add 1" Valve” — install 1" IA isolation valve. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07004-05 | HAY-PID-07004 | “1" Add” + drawn valve at PRO GAS ¦ MPLX boundary — install 1" valve. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07004-06 | HAY-PID-07004 | “Add 2"” + drawn valve at A2AS¦F2AS spec break — install 2" valve. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07004-08 | HAY-PID-07004 | “Installed Backwards” — check valve at F2¦F2AS break is reversed; reinstall in correct flow direction. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
07004-09 | HAY-PID-07004 | “Add support” — install 2" pipe support at MPLX¦PRO GAS boundary. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07004-14 | HAY-PID-07004 | “support @ P.R.” — install support at pressure-reducing station. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07004-15 | HAY-PID-07004 | “Secure 1" IA pipe + Wire + Tubing” — secure IA pipe; complete wiring & tubing at ESD group. | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
07004-16 | HAY-PID-07004 | “U/G” + arc upstream of outlet-header flag — record underground routing (mate of 01001-38). | CLOSED — mark not on current redline set (2026-08-12) | LOW
07005-01 | HAY-PID-07005 | “Ground” — install tank grounding/bonding (flammable service). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
07005-02 | HAY-PID-07005 | “support” — add pipe support(s) at mid-span of long 1" methanol run. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07005-03 | HAY-PID-07005 | Cloud: “Connect to JT Skid” — tie methanol line in at JT skid (companion of 07002-07). | CLOSED — mark not on current redline set (2026-08-12) | CRITICAL
07006-01 | HAY-PID-07006 | “Missing” + pink highlight — install PSV-7006 (PCV-failure case, SIZE HOLD) + vent to ATM. | CLOSED — mark not on current redline set (2026-08-12) — SAFETY: field-confirm before startup (see report Section 7) | CRITICAL
07006-02 | HAY-PID-07006 | “U/G” — record underground takeoff (Note 3). | CLOSED — mark not on current redline set (2026-08-12) | LOW
07006-03 | HAY-PID-07006 | “Add Valve” — install 3" valve at Y-strainer assembly. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07006-04 | HAY-PID-07006 | “U/G” — record underground segment. | CLOSED — mark not on current redline set (2026-08-12) | LOW
07006-05 | HAY-PID-07006 | “U/G” — record underground takeoff. | CLOSED — mark not on current redline set (2026-08-12) | LOW
07006-06 | HAY-PID-07006 | “Add valve” — install 3" valve at Y-strainer. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
07006-07 | HAY-PID-07006 | “U/G” — record underground takeoff. | CLOSED — mark not on current redline set (2026-08-12) | LOW
07006-08 | HAY-PID-07006 | “Add Valve” — install 3" valve at Y-strainer. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08001-01 | HAY-PID-08001 | “support” — install pipe support on 2" heat-traced discharge line. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08002-01 | HAY-PID-08002 | “support” — install 2" pipe support. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08003-01 | HAY-PID-08003 | “support” — install 2" pipe support. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08004-01 | HAY-PID-08004 | “Delete” + large hatched cloud — remove/do-not-install entire truck-unload fill line incl. 2" check, 2" ball valve, truck connection, 2"x3" roof fill. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08004-02 | HAY-PID-08004 | “Missing” + red-drawn gauge column — install external level gauge with 1" top & bottom isolation valves. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08004-03 | HAY-PID-08004 | “Delete” + cloud — remove existing 3" bottom outlet valve assembly. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08004-04 | HAY-PID-08004 | Red-drawn replacement: 2" header off bottom outlet w/ 2" break, 2" valve, hose/truck-fill stub, LG tie-in (1" valve), and new 1" suction run to P-81010 — install per sketch; verify fitting types in field. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08004-05 | HAY-PID-08004 | “Delete” + cloud — remove/do-not-install old heat-traced suction line (superseded by -04). | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08005-01 | HAY-PID-08005 | “Tubing” — run air-supply tubing from 2" valve (PCV-8401 station) to pump air inlet. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08005-02 | HAY-PID-08005 | “Missing” + red oval — install 2" check valve downstream of discharge flex. | CLOSED — mark not on current redline set (2026-08-12) | HIGH
08005-03 | HAY-PID-08005 | “support” — install pipe support mid-run (heat-traced). | CLOSED — mark not on current redline set (2026-08-12) | HIGH